## Cover Sheet
Anodiam
Product Backlog
Rolling Versions
Version | Editor | Reviewer | Date | Note
1.0 | AC |  | 2020-06-20 | Initial version

## ProductBacklog
Item # | Item Type | Item Size | As a… | I want to be able to… | So that… | Acceptance Criteria | Estimates (Sum of Story Points of Tasks) | Business Value | Priority | Status | Sprint Number
1 | Enabler | Story |  | Create CRUD functionality in a REST API web service in a .jar file using JPA and MySQL. |  | GET, POST, DELETE should work through Postman tool on a local desktop machine. | 8 | 5 | 0.625 | Scheduled | 1
2 | Enabler | Story |  | Containerize the .jar file of Item # 1 in a docker container |  | Item # 3 below should be properly doable | 8 | 5 | 0.625 | Scheduled | 1
3 | Enabler | Story |  | Deploy the Docker container on a Kubernetes Cluster in GCP |  | GET, POST, DELETE should work through Postman while the application runs on GCP cluster. | 8 | 1 | 0.125 | Scheduled | 1
4 | Enabler | Story | [5 empty] | 1 | 0 | Initial
5 | Feature | Epic | [5 empty] | 1 | 0 | Initial
6 | Enabler | Epic | [5 empty] | 1 | 0 | Initial
7 | Feature | Story | Student | sign up | I can see the free courses and best options for me before buying | can access free |  | 5 | 0 | Scheduled | 1
8 | Enabler | Story | Student | Login | I can go to my profile | login validation |  | 5 | 0 | Scheduled | 1
9 | Feature | Epic | Student | put secure Password | my profile is secure | password validation, forget password option |  | 3 | 0 | Initial
10 | Enabler | Epic | Student | access forget password | able to access password if forgotton/change password |  |  | 4 | 0 | Initial
11 | Feature | Story |  |  | able to understand the steps to retrive password |  |  | 5 | 0 | Initial
12 | Enabler | Story | [5 empty] | 1 | 0 | Initial
13 | Feature | Epic | [5 empty] | 3 | 0 | Initial
14 | Enabler | Epic | [5 empty] | 4 | 0 | Initial
15 | Feature | Story | [5 empty] | 5 | 0 | Initial
16 | Enabler | Story | [5 empty] | 1 | 0 | Initial
17 | Feature | Epic | [5 empty] | 2 | 0 | Initial
18 | Enabler | Epic | [5 empty] | 3 | 0 | Initial
19 | Feature | Story | [5 empty] | 4 | 0 | Initial
20 | Enabler | Story | [5 empty] | 5 | 0 | Initial
21 | Feature | Epic | [5 empty] | 1 | 0 | Initial
22 | Enabler | Epic | [5 empty] | 2 | 0 | Initial
23 | Feature | Story | [5 empty] | 3 | 0 | Initial