## Cover Sheet
Anodiam
MVP Product Backlog
Rolling Versions
Version | Editor | Reviewer | Date | Note
0.1 | AC |  | 2020-05-04 | Initial version

## MVPProductBacklog
Item # | Item Type | Item Size | As a… | I want to be able to… | So that… | Acceptance Criteria | Notes / References | Task Estimates (Story Points) | Business Value | Priority | Status | Sprint Number
1 | Feature | Story | Unsigned user | Visit the home page of anodiam.com | I can view the Anodiam home page containing link to register and a login section. | Given I am an unsigned user When I type anodiam.com on a web browser Then I should be able to view the Anodiam home page: containing link to register and a login section. | 004MVPStudentAppWireframes.pptx >> Student Login Page | 2 | 5 | 2.5 | Scheduled | 1
2 | Feature | Story | Unsigned user | Click on the Register link on the home page of anodiam.com | I can view the Anodiam registration page containing a link to login page and a registration section. | Given I am an unsigned user When I click on the Register for free link on the home page of anodiam.com Then I should be able to view the Anodiam registration page: containing a link to login page and a registration section. | 004MVPStudentAppWireframes.pptx >> Student Login Page | 1 | 5 | 5 | Scheduled | 1
3 | Feature | Story | Unsigned user | Fill up all the fields: (username, password, confirm password, email) (all mandatory) with valid informations in the registration section of the Student Registration Page and click on the Register button. | I can register myself as a student with anodiam.com. Upon successful registration, I get a message on top of the registration page saying Student registration successful!. | Given I am an unsigned user When I fill up all the fields: (username, password, confirm password, email) (all mandatory) in the registration section of the Student Registration Page with valid inputs and click on the Register button Then I should be able to register myself as a student with anodiam.com. Upon successful registration, I get a message on top of the registration page saying Student registration successful!. | 004MVPStudentAppWireframes.pptx >> Student Registration Page | 5 | 5 | 1 | Scheduled | 1
3.1 | Enabler | Story |  |  | Cyber Security, Non-negotiable | User registration fields (username, password, email) may contain personal information and must be encrypted at rest and inflight at all times |  | 3 | 5 | 1.6667 | Scheduled | 1
3.2.1 | Feature | Story | Unsigned user | Enter invalid username (Less than 8 characters long) in the registration section of the Student Registration Page and click on the Register button. | I cannot register myself as a student with anodiam.com. I must receive error message: Student registration failure! Username should be 8 or more characters long. | Given I am an unsigned user When I enter invalid username (Less than 8 characters long) in the registration section of the Student Registration Page and click on the Register button Then I should not be able to register myself as a student with anodiam.com. I should receive error message: Student registration failure! Username should be 8 or more characters long. | 004MVPStudentAppWireframes.pptx >> Student Registration Page | 2 | 5 | 2.5 | Scheduled | 1
3.2.2 | Feature | Story | Unsigned user | Enter an already existing Anodiam username in the registration section of the Student Registration Page and click on the Register button. | I cannot register myself as a student with anodiam.com. I must receive error message: Student registration failure! This username is already taken by another user. Please try some other username. | Given I am an unsigned user When I enter invalid username (an already existing username) in the registration section of the Student Registration Page and click on the Register button Then I should not be able to register myself as a student with anodiam.com. I should receive error message: Student registration failure! This username is already taken by another user. Please try some other username. | 004MVPStudentAppWireframes.pptx >> Student Registration Page | 2 | 5 | 2.5 | Scheduled | 1
3.2.3 | Feature | Story | Unsigned user | Enter blank username in the registration section of the Student Registration Page and click on the Register button. | I cannot register myself as a student with anodiam.com. I must receive error message: Student registration failure! Username cannot be blank. | Given I am an unsigned user When I enter blank username in the registration section of the Student Registration Page and click on the Register button Then I should not be able to register myself as a student with anodiam.com. I should receive error message: Student registration failure! Username cannot be blank. | 004MVPStudentAppWireframes.pptx >> Student Registration Page | 2 | 5 | 2.5 | Scheduled | 1
3.3.1 | Feature | Story | Unsigned user | Enter invalid password Less than 8 characters in the registration section of the Student Registration Page and click on the Register button. | I cannot register myself as a student with anodiam.com. I must receive following error message: Student registration failure! Invalid password. Password should be 8 to 20 characters long. | Given I am an unsigned user When I enter invalid password Less than 8 characters in the registration section of the Student Registration Page and click on the Register button. Then I should not be able to register myself as a student with anodiam.com. I should receive error message: Student registration failure! Invalid password. Password should be 8 to 20 characters long. | 004MVPStudentAppWireframes.pptx >> Student Registration Page | 2 | 5 | 2.5 | Scheduled | 1
3.3.2 | Feature | Story | Unsigned user | Enter invalid password More than 20 characters in the registration section of the Student Registration Page and click on the Register button. | I cannot register myself as a student with anodiam.com. I must receive following error message: Student registration failure! Invalid password. Password should be 8 to 20 characters long. | Given I am an unsigned user When I enter invalid password More than 20 characters in the registration section of the Student Registration Page and click on the Register button. Then I should not be able to register myself as a student with anodiam.com. I should receive error message: Student registration failure! Invalid password. Password should be 8 to 20 characters long. | 004MVPStudentAppWireframes.pptx >> Student Registration Page | 2 | 5 | 2.5 | Scheduled | 1
3.3.3 | Feature | Story | Unsigned user | Enter invalid password that contains the username string within the password in the registration section of the Student Registration Page and click on the Register button. | I cannot register myself as a student with anodiam.com. I must receive following error message: Student registration failure! Invalid password. Password should not contain your username. | Given I am an unsigned user When I enter invalid password that contains the username string within the password in the registration section of the Student Registration Page and click on the Register button. Then I should not be able to register myself as a student with anodiam.com. I should receive error message: Student registration failure! Invalid password. Password should not contain your username. | 004MVPStudentAppWireframes.pptx >> Student Registration Page | 2 | 5 | 2.5 | Scheduled | 1
3.3.4 | Feature | Story | Unsigned user | Enter invalid password Does not contain at least one small alphabet (a-z), at least one capital alphabet (A-Z), at least one numeric (0-9) and at least one special character among (@,#,$,%,^,&,+,=) in the registration section of the Student Registration Page and click on the Register button. | I cannot register myself as a student with anodiam.com. I must receive following error message: Student registration failure! Invalid password. Password must contain at least one small alphabet (a-z), at least one capital alphabet (A-Z),at least one numeric (0-9) and at least one special character among (@,#,$,%,^,&,+,=) | Given I am an unsigned user When I enter invalid password Does not contain at least one small alphabet (a-z), at least one capital alphabet (A-Z), at least one numeric (0-9) and at least one special character among (@,#,$,%,^,&,+,=) in the registration section of the Student Registration Page and click on the Register button. Then I should not be able to register myself as a student with anodiam.com. I should receive error message: Student registration failure! Invalid password. Password must contain at least one small alphabet (a-z), at least one capital alphabet (A-Z),at least one numeric (0-9) and at least one special character among (@,#,$,%,^,&,+,=) | 004MVPStudentAppWireframes.pptx >> Student Registration Page | 2 | 5 | 2.5 | Scheduled | 1
3.4.1 | Feature | Story | Unsigned user | Enter invalid email address 1. Does not contain exactly one '@' character. 2. Does not contain one or more '.' characters after the '@' character. 3. Does not contain any alphabet (a-z, A-Z) before '@'. 4. Does not contain any alphabet (a-z, A-Z) in between '@' and '.'. 5. Does not contain any alphabet (a-z, A-Z) after the last '.' character. in the registration section of the Student Registration Page and click on the Register button. | I cannot register myself as a student with anodiam.com. I must receive following error message: Student registration failure! Invalid email address. | Given I am an unsigned user When I enter invalid email address 1. Does not contain exactly one '@' character. 2. Does not contain one or more '.' characters after the '@' character. 3. Does not contain any alphabet (a-z, A-Z) before '@'. 4. Does not contain any alphabet (a-z, A-Z) in between '@' and '.'. 5. Does not contain any alphabet (a-z, A-Z) after the last '.' character in the registration section of the Student Registration Page and click on the Register button Then I should not be able to register myself as a student with anodiam.com. I should receive respective error message: Student registration failure! Invalid email address | 004MVPStudentAppWireframes.pptx >> Student Registration Page | 2 | 5 | 2.5 | Scheduled | 1
3.4.2 | Feature | Story | Unsigned user | Enter already existing Anodiam user email address in the registration section of the Student Registration Page and click on the Register button. | I cannot register myself as a student with anodiam.com. I must receive following error message: Student registration failure! An user with the same email address is already registered. | Given I am an unsigned user When I enter an already existing username in the Student Registration Page and click on the Register button Then I should not be able to register myself as a student with anodiam.com. I should receive respective error message: Student registration failure! An user with the same email address is already registered. | 004MVPStudentAppWireframes.pptx >> Student Registration Page | 2 | 5 | 2.5 | Scheduled | 1
3.5 | Feature | Story | Unsigned User | Enter wrong Confirm Password in the Student Registration Page and click on the Register button. | I cannot register myself as a student with anodiam.com. I must receive following error message: Password and Confirm Password fields do not match. | Given I am an unsigned user When I enter wrong Confirm Password in the Student Registration Page and click on the Register button. Then I should not be able to register myself as a student with anodiam.com. I should receive error message: Password and Confirm Password fields do not match. | 004MVPStudentAppWireframes.pptx >> Student Registration Page | 2 | 3 | 1.5 | Scheduled | 1
3.6 | Feature | Story | Unsigned User | Try to copy or paste in the Password or Confirm Pasword fields of the Registration page | I am not allowed to Copy or paste in the Password or Confirm Pasword fields of the Registration page | Given I am an unsigned user When Try to copy or paste in the Password or Confirm Pasword fields of the Registration page. Then I am not allowed to Copy or paste in the Password or Confirm Pasword fields of the Registration page. | 004MVPStudentAppWireframes.pptx >> Student Registration Page | 2 | 1 | 0.5 | Scheduled | 1
3.7 | Feature | Story | Unsigned User | Try to copy or paste in the Password field of the Login page | I am not allowed to Copy or paste in the Password field of the Login page | Given I am an unsigned user When Try to copy or paste in the Password field of the Login page. Then I am not allowed to Copy or paste in the Password field of the Login page. | 004MVPStudentAppWireframes.pptx >> Student Login Page | 2 | 1 | 0.5 | Scheduled | 1
4 | Feature | Story | Unsigned user | Click on the Already registered? Login link on the registration page of anodiam.com | I can view the Anodiam home page containing link to register and a login section. | Given I am an unsigned user When I Click on the Already registered? Login link on the registration page of anodiam.com Then I should be able to view the Anodiam home page: containing link to register and a login section. | 004MVPStudentAppWireframes.pptx >> Student Registration Page | 2 | 5 | 2.5 | Scheduled | 1
5 | Feature | Story | Unsigned registered user | Fill up the valid username and password fields in the login page and click on the Login button. | I can log in to anodiam.com and view the Student Home Page. | Given I am an unsigned but registered user When I fill up the username and password fields in the login page and click on the Login button Then I should be able to view the Anodiam Student Home Page: containing a welcome message with my (first and last) name at the top. | 004MVPStudentAppWireframes.pptx >> Student Login Page | 5 | 5 | 1 | Scheduled | 1
5.1 | Feature | Story | Unsigned registered user | Fill up the username and password fields with invalid username in the login page and click on the Login button. | I can not log in to anodiam.com and view the Student Home Page. I must be sent back to the login page with a login validation message (Login failure. Not a valid Anodiam username.) displayed on top in red. | Given I am an unsigned but registered user When I fill up the username and password fields invalid username in the login page and click on the Login button Then I should be not able to view the Anodiam Student Home Page. I must be sent back to the login page with a login validation message (Login failure. Not a valid Anodiam username.) displayed on top in red. | 004MVPStudentAppWireframes.pptx >> Student Login Page | 5 | 5 | 1 | Scheduled | 1
5.2 | Feature | Story | Unsigned registered user | Fill up the username and password fields with balid username but invalid password in the login page and click on the Login button. | I can not log in to anodiam.com and view the Student Home Page. I must be sent back to the login page with a login validation message (Login failure! Incorrect password.) displayed on top in red. | Given I am an unsigned but registered user When I fill up the username and password fields invalid username in the login page and click on the Login button Then I should be not able to view the Anodiam Student Home Page. I must be sent back to the login page with a login validation message (Login failure! Incorrect password.) displayed on top in red. | 004MVPStudentAppWireframes.pptx >> Student Login Page | 5 | 5 | 1 | Scheduled | 1
6 | Feature | Epic | Unsigned user | Email Verification of student registration |  |  |  | 13 | 5 | 0.38462 | Initial
6.2 | Feature | Story | Unsigned User | Password Strength Meter |  |  |  | 5 | 1 | 0.2
7 | Feature | Story | Signed in user | Change the Class, Subject or Board filters in the Student Home Page | I can view the Student Home Page with the paginated list of courses according to the selected Class, Subject or Board, sans the courses I have already subscribed for (purchased), order by rating and total number of students | Given I am a signed in user When I change the Class, Subject or Board filters in the Student Home Page Then I should be able to view the paginated list of courses according to the selected Class, Subject or Board, sans the courses I have already subscribed for (purchased), order by rating and total number of students | 004MVPStudentAppWireframes.pptx >> Student Home Page |  |  | 0
8 | Feature | Story | Signed in user | Click on the Home hyperlink or Anodiam logo image on the menu bar of any page in anodiam.com | I can view the Student Home Page. The details of the fields visible for each course will be according to the wireframe diagram in 004MVPStudentAppWireframes.pptx >> Student Home Page | Given I am a signed in user When I click on the Home hyperlink or Anodiam logo image on the menu bar of any page in anodiam.com Then I should be able to view the Anodiam Student Home Page: containing a welcome message with my (first and last) name at the top, a menu bar and a paginated list of courses recommended for me according to my Board, and Class, sans the courses I have already subscribed for (purchased), order by rating and total number of students. The details of the fields visible for each course will be according to the wireframe diagram in 004MVPStudentAppWireframes.pptx >> Student Home Page | 004MVPStudentAppWireframes.pptx >> All logged in pages >> Top menu bar |  |  | 0
9 | Feature | Story | Signed in user | Click on the Logout hyperlink on the menu bar of any page in anodiam.com | I can log out of anodiam.com and view the Student Login Page. | Given I am a signed in user When I click on the Logout hyperlink on the menu bar of any page in anodiam.com Then I should be able to log out of anodiam.com and view the Student Login Page | 004MVPStudentAppWireframes.pptx >> All logged in pages >> Top menu bar |  |  | 0
10 | Feature | Story | Signed in user | Enter a search string in the search field and click on the search (magnifying glass) icon on the menu bar of any page in anodiam.com | I can view the Student Home Page with the paginated list of courses, matching my search string and ordered by course rating and total number of students. The details of the fields visible for each course will be according to the wireframe diagram in 004MVPStudentAppWireframes.pptx >> Student Home Page | Given I am a signed in user When I enter a search string in the search field and click on the search (magnifying glass) icon on the menu bar of any page in anodiam.com Then I should be able to view the Student Home Page with the paginated list of courses, matching my search string and ordered by course rating and total number of students. The details of the fields visible for each course will be according to the wireframe diagram in 004MVPStudentAppWireframes.pptx >> Student Home Page | 004MVPStudentAppWireframes.pptx >> All logged in pages >> Top menu bar & Student Home Page |  |  | 0
11 | Feature | Story | Signed in user | Click on the My Account hyperlink on the menu bar of any page in anodiam.com | I can view the Student Detail Tab of the Student Detail Page and edit any of the fields of my personal information | Given I am a signed in user When I click on the My Account hyperlink on the menu bar of any page in anodiam.com Then I should be able to view the Student Detail Tab of the Student Detail Page and edit any of the fields of my personal information | 004MVPStudentAppWireframes.pptx >> All logged in pages >> Top menu bar |  |  | 0
12 | Feature | Story | Signed in user | Click on the Study Dashboard tab on the Student Detail Page in anodiam.com | I can view the analytics report (now blank) of my studies in the Study Dashboard tab on the Student Detail Page | Given I am a signed in user When I click on the Study Dashboard tab on the Student Detail Page Then I should be able to view the analytics report (now blank) of my studies in the Study Dashboard tab on the Student Detail Page | 004MVPStudentAppWireframes.pptx >> Student Detail Page
13 | Feature | Story | Signed in user | Click on the Student Details tab on the Student Detail Page in anodiam.com | I can view the Student Detail Tab of the Student Detail Page and edit any of the fields of my personal information | Given I am a signed in user When I click on the Student Detail tab on the Student Detail Page Then I should be able to view the Student Detail Tab of the Student Detail Page and edit any of the fields of my personal information | 004MVPStudentAppWireframes.pptx >> Student Detail Page
14 | Feature | Story | Signed in user | Edit my personal details on the Student Details tab on the Student Detail Page and click on the Save button | The edited (changed) Student Detail personal information gets saved and I can view the updated personal information on the Student Detail Tab of the Student Detail Page | Given I am a signed in user When I edit my personal details on the Student Details tab on the Student Detail Page and click on the Save button Then the edited (changed) Student Detail personal information should get saved and I should be able to view the updated personal information on the Student Detail Tab of the Student Detail Page | 004MVPStudentAppWireframes.pptx >> Student Detail Page
15 | Feature | Story | Signed in user | Double click on any of the courses in the Student Home Page | I can view the Course Detail page for the respective course. The details of the fields visible for each course will be according to the wireframe diagram in 004MVPStudentAppWireframes.pptx >> Course Detail Page | Given I am a signed in user When I Double click on any of the courses in the Student Home Page Then I should be able to view the Course Detail Page with the details of the selected course in the first section. It will be followed by a second section containing a carousel 4 courses at a time of all the courses recommended for me according to my Class and Board, sans the one on the top section and the courses I have already subscribed for (purchased), order by rating and total number of students. The details of the fields visible for each course in either of the two sections will be according to the wireframe diagram in 004MVPStudentAppWireframes.pptx >> Course Detail Page | 004MVPStudentAppWireframes.pptx >> Student Home Page & Course Detail Page
16 | Feature | Story | Signed in user | Click on a course from the list of Recommended for You! on the Course Detail Page | I can view the Course Detail page for the respective course. The details of the fields visible for each course will be according to the wireframe diagram in 004MVPStudentAppWireframes.pptx >> Course Detail Page | Given I am a signed in user When I click on a course from the list of Recommended for You! on the Course Detail Page Then I should be able to view the Course Detail Page with the details of the selected course in the first section. It will be followed by a second section containing a carousel 4 courses at a time of all the courses recommended for me according to my Class and Board, sans the one on the top section and the courses I have already subscribed for (purchased), order by rating and total number of students. The details of the fields visible for each course in either of the two sections will be according to the wireframe diagram in 004MVPStudentAppWireframes.pptx >> Course Detail Page | 004MVPStudentAppWireframes.pptx >> Course Detail Page
17 | Feature | Story | Signed in user | Click on the Buy button on the Course Detail Page | I can view the Buy Course Page | Given I am a signed in user When I click on the Buy button on the Course Detail Page Then I should be able to view the Buy Course Page with the Payment summary of Course Name, details and original, discounted and final price displayed. Aso the final payable price should be displayed. | 004MVPStudentAppWireframes.pptx >> Course Detail Page & Buy Course Page
18 | Feature | Story | Signed in user | Select one or more courses in the Student Home Page and click on the Buy Selected Courses button | I can view the Buy Course Page | Given I am a signed in user When I select one or more courses in the Student Home Page and click on the Buy Selected Courses button Then I should be able to view the Buy Course Page with the Payment summary of all the Course Names, details and original, discounted and final prices displayed. Aso the final payable price should be displayed. | 004MVPStudentAppWireframes.pptx >> Student Home Page & Buy Course Page
19 | Feature | Story | Signed in user | Enter my valid Credit / Debit Card or PayPal account details and click on the Proceed to Pay button. | I can view the My Courses Page with all my subscribed (purchased) courses in the order of recent access. The last purchased courses should be at the top of the list. The details of the fields visible for each course will be according to the wireframe diagram in 004MVPStudentAppWireframes.pptx >> My Courses Page | Given I am a signed in user When I click on the My courses hyperlink on the menu bar of any page in anodiam.com Then I should be able to view the My Courses Page with all my subscribed (purchased) courses in the order of recent access. The last purchased courses should be at the top of the list. The details of the fields visible for each course will be according to the wireframe diagram in 004MVPStudentAppWireframes.pptx >> My Courses Page | 004MVPStudentAppWireframes.pptx >> Buy Course Page & My Courses Page
20 | Feature | Story | Signed in user | Click on any of the courses on My Courses Page | I can view the Course Page | Given I am a signed in user When I click on any of the courses on My Courses Page Then I should be able to view the Course Page with all the following details 1. The header bar should display the Name, Board, Class & Subject of the Course; a logo that is a hyperlink to the Student's Home page; and percentage completion (videos checked or completed divided by the total number of videos in the course) by the student 2. The body section will display the video contents. It will have the following controls: A. Stop Pause video toggle control B. Video Speed control (0.25x, 0.5x, 1x, 1.5x & 2x) C. 5 seconds forward & 5 backword control D. Volume (sound) control E. Full screen and normal screen video display toggle control F. Resolution control up to HD 3. The right section display the contents of the course, broken down into sections and videos 4. The bottom section will hold the following tabs: About this chapter (selected by default), Teacher's Notes (non video contents) and Queries and Resolutions. 5. The right bottom section will be the rating and comments section for the course 004MVPStudentAppWireframes.pptx >> Course Page | 004MVPStudentAppWireframes.pptx >> Course Page
21 | Feature | Story | Signed in user | Click on the About this Chapter tab at the bottom section of the Course Page | I can view the details of the chapter in the About this Chapter tab. This should not refresh the entire Course Page | Given I am a signed in user When I click on the About this Chapter tab at the bottom section of the Course Page Then I should be able to view the contents of the About this Chapter tab at the bottom section of Course Page. This will be a text document supplied by the teacher, similar to a text book contents. . This should not refresh the entire Course Page | 004MVPStudentAppWireframes.pptx >> Course Page
22 | Feature | Story | Signed in user | Click on the Teacher's Notes tab at the bottom section of the Course Page | I can view the Teacher's Notes on the chapter in this tab | Given I am a signed in user When I click on the Teacher's Notes tab at the bottom section of the Course Page Then I should be able to view the contents of the Teacher's Notes tab at the bottom section of Course Page. This will be the non video contents on this chapter supplied by the teacher. It will cobtain important diagrams, notes, points to remember, mneumonics etc. | 004MVPStudentAppWireframes.pptx >> Course Page
23 | Feature | Story | Signed in user | Click on the Queries & Resolutions tab at the bottom section of the Course Page | I can view the Queries & Resolutions on the chapter in this tab. This should not refresh the entire Course Page | Given I am a signed in user When I click on the Queries & Resolutions tab at the bottom section of the Course Page Then I should be able to view the contents of the Queries & Resolutions tab at the bottom section of Course Page. This should not refresh the entire Course Page. This will contain of 2 sections: 1. The top section will display all the queries raised by all the students in a recent first order (with student name, date, attachment) and also each query (if already answered) followed by the answer / resolution provided by the teacher (with attachment, datetime of resolution). If the query is not yet ansererd then I should be able to see just the query. 2. The bottom section will contain the form to raise a new query. | 004MVPStudentAppWireframes.pptx >> Course Page
24 | Feature | Story | Signed in user | I can write a new query, attach a supporting image / text / docx file and click on the Post button in the bottom section of the Queris & Resolutions tab at the bottom section of the Course Page | My query gets saved and attachment file stored in the system and everyone can view the query I raised. This should not refresh the entire Course Page | Given I am a signed in user When I write a new query, attach a supporting image / text / docx file and click on the Post button in the bottom section of the Queris & Resolutions tab at the bottom section of the Course Page Then My query gets saved and attachment file stored in the system. This should not refresh the entire Course Page. Everyone should now be able to view the query I raised along with the attachment and date time of my query and my name. Once it is answered, everyone should also be able to view the resolution, datetime and attachemt (if any resolution is put in by a teacher). | 004MVPStudentAppWireframes.pptx >> Course Page
25 | Feature | Story | Signed in user | Click on any of the video lessons under any of the units in the right section of the Course Page | I can start viewing the same video lesson on the main section of the Course Page | Given I am a signed in user When I click on any of the video lessons under any of the units in the right section of the Course Page Then I should be able to start viewing the same video lesson on the main section of the Course Page. The checkbox on the immidiate left side of this listing of the video lesson on the right panel shows checked. | 004MVPStudentAppWireframes.pptx >> Course Page
26 | Feature | Story | Signed in user | Complete viewing any video lessons under any of the units in the right section of the Course Page | I can start viewing the next video lesson according to the list on the right panel until the last video lesson I reached. | Given I am a signed in user When I complete viewing any video lessons under any of the units in the right section of the Course Page Then I should be able to start viewing the next video lesson according to the list on the right panel until the last video lesson I reached. If the next video corresponds to a new section, the new section should show openned in the right section of the main page. Also the checkbox on the immidiate left side of this listing of the next video lesson on the right panel shows checked. | 004MVPStudentAppWireframes.pptx >> Course Page
27 | Feature | Story | Signed in user | Click on any of the 5 stars at the right bottom of the Course Page to rate the course | My rating gets saved and I can view my rating now on. The rating is no longer ediatble any more. This should not refresh the entire Course Page | Given I am a signed in user When I click on any of the 5 stars at the right bottom of the Course Page to rate the course Then my rating gets saved and I can view my rating now on. The rating is no longer ediatble any more. This should not refresh the entire Course Page | 004MVPStudentAppWireframes.pptx >> Course Page
28 | Feature | Story | Signed in user | Write a comment on the respective text area at the right bottom of the Course Page to rate the course | My comment gets saved and I can view my comment now on. The comment is no longer ediatble any more. This should not refresh the entire Course Page | Given I am a signed in user When I write a comment on the respective text area at the right bottom of the Course Page to rate the course Then my comment gets saved and I can view my comment now on. The comment is no longer ediatble any more. This should not refresh the entire Course Page | 004MVPStudentAppWireframes.pptx >> Course Page
29 | Feature | Story | Signed in user | Click on Change This Rating link on the right bottom of the Course Page | The ratings section (5 stars) becomes editable again I can select another rating for this course. This should not refresh the entire Course Page | Given I am a signed in user When I click on Change This Rating link on the right bottom of the Course Page to rate the course Then the ratings section becomes editable again I can select another rating for this course. This should not refresh the entire Course Page | 004MVPStudentAppWireframes.pptx >> Course Page
30 | Feature | Story | Signed in user | Click on Change This Comment link on the right bottom of the Course Page | The comments text area becomes editable and is prepopulated with my previous comment for this course. This should not refresh the entire Course Page | Given I am a signed in user When I click on Change This Comment link on the right bottom of the Course Page Then the comments text area becomes editable and is prepopulated with my previous comment for this course. This should not refresh the entire Course Page | 004MVPStudentAppWireframes.pptx >> Course Page
31 | Feature | Story | Signed in user | Click a check box on the immediate left of a video lesson in the list of videos in the course | The video lesson's status can toggle between completed (checked) and incomplete (unchecked). This should not refresh the entire Course Page. The percentage completion dial on the top band of the page also shows the changed count | Given I am a signed in user When I click a check box on the immediate left of a video lesson in the list of videos in the course Then the video lesson's status can toggle between completed (checked) and incomplete (unchecked). This should not refresh the entire Course Page. The percentage completion dial on the top band of the page also shows the changed count | 004MVPStudentAppWireframes.pptx >> Course Page
Note on G1: Help: Acceptance Criteria in Product Backlog comprises of 3 fields, namely: Given, When Then. Here all 4 fields should be colated into one. E.g. Acceptance criteria for following should be as below: User Story: As a logged out User I want to be able to sign into the website, so that I can see my profile. Acceptance Criteria: Scenario: Registered User Signs with valid username and password. Given: I am logged out of website. When: I fill in the username and password fields with my valid credentials and click in sign in button Then: I get signed into the website. Here, Acceptance Criteria could be written in 1 sentence as below: Given I am logged out of website, if I fill in the username and password fields with my valid credentials and click in sign in button, I should get signed into the website.
Note on I1: Help: XS : 1 Story Point : 0 to 2 person hours S : 2 Story Points : 2 to 4 person hours M : 3 Story Points : 4 to 8 person hours L : 5 Story Points : 1 to 1.5 person days XL : 8 Story Points : 1.5 to 2.5 person days XXL : 13 Story Points : 0.5 to 1 person weeks XXXL : 21 Story Points : Larger and never used