## Cover Sheet
StudioSetup
Administrative Planning for Anodiam Studio Setup
Version | Editor | Reviewer | Date | Note
1.0 | Anirban | Avishek | 2021-07-11 | Initial version

## ItemList
Sl # | Item Group | Item | Item Count | Item Description | Studio Floor | Room | Type | Status | Last Action Date | Actioned By | Next Action Date | Assigned To | Estimate ₹738950 | Revised Estimate ₹211150 | Notes
1 |  | 15 Amp plug point | 3 | On one wall | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Electrical | Planned | 2021-07-10 | Anirban | 2021-07-18 | Arati | 2100 | 2100 | Ask electritian to install
2 |  | 5 Amp plug point | 4 | 2 on the board of 15 amp points, 2 on opposite wall | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Electrical | Planned | 2021-07-10 | Anirban | 2021-07-18 | Arati | 2000 | 2000 | Ask electritian to install
3 |  | Tube light | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Electrical | Planned | 2021-07-10 | Anirban | 2021-07-18 | Arati | 1500 | 1500 | Ask electritian to install
4 |  | Bulb | 1 | On opposite wall of tube light | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Electrical | Planned | 2021-07-10 | Anirban | 2021-07-18 | Arati | 1000 | 1000 | Ask electritian to install
5 |  | Ceiling fan | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Electrical | Planned | 2021-07-10 | Anirban | 2021-07-18 | Arati | 3000 | 3000 | Ask electritian to install
6 |  | Split Air Con | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Appliance | Planned | 2021-07-10 | Anirban | 2021-07-18 | Arati | 40000 |  | Ask electritian to install infrastructure
7 |  | Sound Proofing | 1 | Wall covering @ ₹55/- per sqft | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Videography | Planned | 2021-07-16 | Anirban |  |  | 50000
10 | Glass Board | Sleek minimalist chair | 1 | This is a prop and will come in film | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | Planned | 2021-07-10 | Anirban |  |  | 1500 | 1500
11 | Glass Board | Plastic stool | 1 | Can be used by videographer / director | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | Planned | 2021-07-10 | Anirban |  |  | 300 | 300
12 | Glass Board | Green screen | 1 | To be provided by glass board vendor | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Videography | Planned | 2021-07-10 | Anirban |  |  |  |  | To be procured with glass board / light board
13 | Glass Board | White screen | 1 | To be provided by glass board vendor | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Videography | Planned | 2021-07-10 | Anirban |  |  |  |  | To be procured with glass board / light board
14 | Glass Board | Black screen | 1 | To be provided by glass board vendor | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Videography | Planned | 2021-07-10 | Anirban |  |  |  |  | To be procured with glass board / light board
15 | Glass Board | Screen hanger set | 1 | One hanger set for all 3 screens. To be provided by glass board vendor. | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Videography | Planned | 2021-07-10 | Anirban |  |  |  |  | To be procured with glass board / light board
16 | Glass Board | Glass board (light board) | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Videography | Planned | 2021-07-10 | Anirban |  |  | 60000 | 60000
17 | Glass Board | Glass board (light board) marker set (Black, Green, Blue, Red + duster + eraser spray) |  | To be provided by glass board vendor | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Stationaries | Planned | 2021-07-10 | Anirban |  |  |  |  | To be procured with glass board / light board
18 | Glass Board | Glass board wall paper / poster | 2-3 | 7ft x 7ft each: * White - fancy brick texture / sky * Natural setting - forest / beach * Dark - night sky / astronomy / texture | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Videography | Planned | 2021-07-10 | Anirban |  |  | 9000 | 9000
19 | Glass Board | Glass board wall paper / poster hanger with clips | 1 | * Will not be required if wall papers are glued to walls. * Height to be adjusted so that the top of wallpaper / poster is at 7'. Dependency: can be instlled only after procuring wall paper / poster | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Videography | Planned | 2021-07-10 | Anirban |  |  | 1000 | 1000
20 | Flat Background | White brick texture wall paper | 1 | Example Flat Background | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Videography | Planned | 2021-07-10 | Anirban |  |  | 3000 | 3000
21 | Flat Background | Office chair | 1 | Moderatly good quality | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | Planned | 2021-07-10 | Anirban |  |  | 10000 | 10000
22 | Flat Background | Sleek computer table | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | Planned | 2021-07-10 | Anirban |  |  | 3000 | 3000
23 | Flat Background | Chest of drawers | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | Planned | 2021-07-10 | Anirban |  |  | 3000 | 3000
24 | Flat Background | Photo frame | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | Planned | 2021-07-10 | Anirban |  |  | 1000 | 1000
25 | Flat Background | Indoor plants | 2 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | Planned | 2021-07-10 | Anirban |  |  | 1000 | 1000
26 | Flat Background | Fancy table lamp | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | Planned | 2021-07-10 | Anirban |  |  | 1000 | 1000
27 | Flat Background | Fancy computer monitor | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Computing | Planned | 2021-07-10 | Anirban |  |  | 7000 | 7000
28 | Flat Background | Keyboard | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Computing | Planned | 2021-07-10 | Anirban |  |  | 1000 | 1000
29 | Flat Background | Mouse | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Computing | Planned | 2021-07-10 | Anirban |  |  | 500 | 500
30 | Flat Background | Mouse pad | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Computing | Planned | 2021-07-10 | Anirban |  |  | 200 | 200
31 | Flat Background | Fancy water bottle | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Stationaries | Planned | 2021-07-10 | Anirban |  |  | 300 | 300
32 | Flat Background | Fancy pencil stand | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Stationaries | Planned | 2021-07-10 | Anirban |  |  | 200 | 200
33 | Flat Background | Flower vase / small sculpture | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | Planned | 2021-07-10 | Anirban |  |  | 500 | 500
34 |  | Thick doormat | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | House keeping | Planned | 2021-07-10 | Anirban |  |  | 300 | 300
44 | Touch screen monitor board | Sleek minimalist chair | 1 | This is a prop and will come in film | 1: PL1 - Level 1 Patuli | Shooting Room 2 | Furniture | Planned | 2021-07-10 | Anirban |  |  | 1500
45 | Touch screen monitor board | Plastic stool | 1 | Can be used by videographer / director | 1: PL1 - Level 1 Patuli | Shooting Room 2 | Furniture | Planned | 2021-07-10 | Anirban |  |  | 300
46 | Touch screen monitor board | Touch screen monitor board | 1 | 60" plus | 1: PL1 - Level 1 Patuli | Shooting Room 2 | Electronics | Planned | 2021-07-10 | Anirban |  |  | 200000
47 | Touch screen monitor board | Touch screen stylus set | 2 |  | 1: PL1 - Level 1 Patuli | Shooting Room 2 | Electronics | Planned | 2021-07-10 | Anirban
48 | Touch screen monitor board | Touch screen stylus holder | 1 | Preferably fixed at the bottom of the touch screen board | 1: PL1 - Level 1 Patuli | Shooting Room 2 | Stationaries | Planned | 2021-07-10 | Anirban |  |  | 1000
49 | White board | White board | 1 | 6 ft x 4 ft | 1: PL1 - Level 1 Patuli | Shooting Room 2 | Stationaries | Planned | 2021-07-10 | Anirban |  |  | 5000 | 5000
50 | White board | White board wall hanger | 1 | Height to be adjusted so that the top of white board is at 6'6". Dependency: can be wall-mounted only after procuring white board | 1: PL1 - Level 1 Patuli | Shooting Room 2 | Furniture | Planned | 2021-07-10 | Anirban |  |  | 1000 | 1000
51 | White board | White board marker set (Black, Green, Blue, Red + duster + eraser spray) | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 2 | Stationaries | Planned | 2021-07-10 | Anirban |  |  | 1500 | 1500
52 | White board | White board marker, duster stand / platform | 1 | Preferably fixed at the bottom of the white board. | 1: PL1 - Level 1 Patuli | Shooting Room 2 | Furniture | Planned | 2021-07-10 | Anirban |  |  | 1000 | 1000
53 | Corner background | Bookshelf 5ft x 3ft x 1ft | 1 | Example Corner Background | 1: PL1 - Level 1 Patuli | Shooting Room 2 | Furniture | Planned | 2021-07-10 | Anirban |  |  | 8000 | 8000
54 | Corner background | Books | 40-50 | About size of a standard diary each | 1: PL1 - Level 1 Patuli | Shooting Room 2 | Stationaries | [5 empty] | 4000 | 4000
55 | Corner background | Indoor plants | 8-10 | Different sizes, 6" to 2' | 1: PL1 - Level 1 Patuli | Shooting Room 2 | Furniture | Planned | 2021-07-10 | Anirban |  |  | 2500 | 2500
56 | Corner background | Fancy lantern | 1 | Small size | 1: PL1 - Level 1 Patuli | Shooting Room 2 | Furniture | Planned | 2021-07-10 | Anirban |  |  | 1000 | 1000
57 | Corner background | Rock salt lamp | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 2 | Furniture | Planned | 2021-07-10 | Anirban |  |  | 1500 | 1500
58 | Corner background | Sculpture / vase | 1 | 1' | 1: PL1 - Level 1 Patuli | Shooting Room 2 | Furniture | Planned | 2021-07-10 | Anirban |  |  | 1000 | 1000
59 | Corner background | Painting / wall calendar | 1 | 1'6" x 2' | 1: PL1 - Level 1 Patuli | Shooting Room 2 | Furniture | Planned | 2021-07-10 | Anirban |  |  | 1000 | 1000
60 | Corner background | Artificial vintage window | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 2 | Furniture | Planned | 2021-07-10 | Anirban |  |  | 3000 | 3000
62 |  | 15 Amp plug point | 2 | On one wall | 1: PL1 - Level 1 Patuli | Changing Room | Electrical | Planned | 2021-07-10 | Anirban | 2021-07-18 | Arati | 1500 | 1500 | Ask electritian to install
63 |  | 5 Amp plug point | 4 | 2 on the board of 15 amp points, 2 on opposite wall | 1: PL1 - Level 1 Patuli | Changing Room | Electrical | Planned | 2021-07-10 | Anirban | 2021-07-18 | Arati | 2000 | 2000 | Ask electritian to install
64 |  | Window Air Con | 1 |  | 1: PL1 - Level 1 Patuli | Changing Room | Appliance | Planned | 2021-07-10 | Anirban | 2021-07-18 | Arati | 30000 |  | Ask electritian to install infrastructure
65 |  | Tube light | 1 |  | 1: PL1 - Level 1 Patuli | Changing Room | Electrical | Planned | 2021-07-10 | Anirban | 2021-07-18 | Arati | 1500 | 1500 | Ask electritian to install
66 |  | Table fan | 1 |  | 1: PL1 - Level 1 Patuli | Changing Room | Electrical | Planned | 2021-07-10 | Anirban | 2021-07-18 | Arati | 1500 | 1500 | Ask electritian to install
67 |  | Window curtain hangers | 1 |  | 1: PL1 - Level 1 Patuli | Changing Room | Furniture | Planned | 2021-07-10 | Anirban | 2021-07-18 | Arati | 2000 | 2000 | Ask electritian to install
68 |  | Window curtain | 1 | Dependency: can be instlled only after installing hangers | 1: PL1 - Level 1 Patuli | Changing Room | Furniture | Planned | 2021-07-10 | Anirban | 2021-07-18 | Arati | 1000 | 1000 | Ask electritian to install
69 |  | Vanity Dressing Table set with light + mirror + stool | 1 | Example3 | 1: PL1 - Level 1 Patuli | Changing Room | Furniture | Planned | 2021-07-10 | Anirban |  |  | 15000
70 |  | Clothes rack | 1 |  | 1: PL1 - Level 1 Patuli | Changing Room | Furniture | Planned | 2021-07-10 | Anirban |  |  | 3000 | 3000
71 |  | Hangers | 12 |  | 1: PL1 - Level 1 Patuli | Changing Room | Furniture | Planned | 2021-07-10 | Anirban |  |  | 300 | 300
72 |  | Wardrobe with locker | 1 | Very small size | 1: PL1 - Level 1 Patuli | Changing Room | Furniture | Planned | 2021-07-10 | Anirban |  |  | 4000 | 4000
73 |  | Dust bin | 1 |  | 1: PL1 - Level 1 Patuli | Changing Room | House keeping | Planned | 2021-07-10 | Anirban |  |  | 500 | 500
74 |  | Bin bag packets | 1 |  | 1: PL1 - Level 1 Patuli | Changing Room | House keeping | Planned | 2021-07-10 | Anirban |  |  | 200 | 200
75 |  | Thick doormat | 1 |  | 1: PL1 - Level 1 Patuli | Changing Room | House keeping | Planned | 2021-07-11 | Anirban |  |  | 300 | 300
76 |  | Wash basin | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | Plumbing | Planned | 2021-07-11 | Anirban |  |  | 4000 | 4000
77 |  | Liquid soap bottle | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | Planned | 2021-07-11 | Anirban |  |  | 200 | 200
78 |  | Soap dispenser | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | Planned | 2021-07-11 | Anirban |  |  | 100 | 100
79 |  | Mug | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | Planned | 2021-07-11 | Anirban |  |  | 50 | 50
80 |  | Bucket | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | Planned | 2021-07-11 | Anirban |  |  | 400 | 400
81 |  | Dust bin | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | Planned | 2021-07-11 | Anirban |  |  | 500 | 500
82 |  | Bin bag packets | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | Planned | 2021-07-11 | Anirban |  |  | 100 | 100
83 |  | Broom stick | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | Planned | 2021-07-11 | Anirban |  |  | 400 | 400
84 |  | Dust pan | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | Planned | 2021-07-11 | Anirban |  |  | 200 | 200
85 |  | Cleaning mop | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | Planned | 2021-07-11 | Anirban |  |  | 600 | 600
86 |  | Vaccum cleaner | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | Planned | 2021-07-11 | Anirban |  |  | 10000
87 |  | Feather duster | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | Planned | 2021-07-11 | Anirban |  |  | 300 | 300
88 |  | Phynile | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | Planned | 2021-07-11 | Anirban |  |  | 200 | 200
89 |  | Acid | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | Planned | 2021-07-11 | Anirban |  |  | 100 | 100
90 |  | Cleaning soap | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | Planned | 2021-07-11 | Anirban |  |  | 200 | 200
91 |  | Hand sanitizer | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | Planned | 2021-07-11 | Anirban |  |  | 1000 | 1000
92 |  | Hand sanitizer dispenser | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | Planned | 2021-07-11 | Anirban |  |  | 500 | 500
93 |  | Toilet paper packs | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | Planned | 2021-07-11 | Anirban |  |  | 1000 | 1000
94 |  | Tissue dispenser | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | Planned | 2021-07-11 | Anirban |  |  | 2000 | 2000
93 |  | C folds | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | Planned | 2021-07-11 | Anirban |  |  | 1000 | 1000
94 |  | C folds dispenser | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | Planned | 2021-07-11 | Anirban |  |  | 2000 | 2000
95 |  | Thick doormat | 1 |  | 1: PL1 - Level 1 Patuli | Toilet | House keeping | Planned | 2021-07-11 | Anirban |  |  | 300 | 300
96 |  | 15 Amp plug point | 2 | On one wall | 1: PL1 - Level 1 Patuli | Office | Electrical | Planned | 2021-07-10 | Anirban | 2021-07-18 | Arati | 1500 | 1500 | Ask electritian to install
97 |  | 5 Amp plug point | 8 | 4 on the board of 15 amp points, 4 on opposite wall | 1: PL1 - Level 1 Patuli | Office | Electrical | Planned | 2021-07-10 | Anirban | 2021-07-18 | Arati | 4000 | 4000 | Ask electritian to install
98 |  | Window Air Con | 1 |  | 1: PL1 - Level 1 Patuli | Office | Appliance | Planned | 2021-07-10 | Anirban | 2021-07-18 | Arati | 30000 |  | Ask electritian to install infrastructure
99 |  | Hard big table | 1 | Conference / dining table | 1: PL1 - Level 1 Patuli | Office | Furniture | Planned | 2021-07-11 | Anirban |  |  | 2000 | 2000
100 |  | Plactic Chairs | 4 |  | 1: PL1 - Level 1 Patuli | Office | Furniture | Planned | 2021-07-11 | Anirban |  |  | 2000 | 2000
101 |  | Common computer | 1 |  | 1: PL1 - Level 1 Patuli | Office | Computing | Planned | 2021-07-11 | Anirban |  |  | 50000
102 |  | CC TV | 1 |  | 1: PL1 - Level 1 Patuli | Office | Computing | Planned | 2021-07-11 | Anirban |  |  | 100000
103 |  | Wifi | 1 |  | 1: PL1 - Level 1 Patuli | Office | Computing | Planned | 2021-07-11 | Anirban |  |  | 5000 | 5000
104 |  | Thick doormat | 1 |  | 1: PL1 - Level 1 Patuli | Office | House keeping | Planned | 2021-07-11 | Anirban |  |  | 300 | 300
105 |  | 15 Amp plug point | 2 | On one wall | 1: PL1 - Level 1 Patuli | Kitchen | Electrical | Planned | 2021-07-10 | Anirban | 2021-07-18 | Arati | 1500 | 1500 | Ask electritian to install
106 |  | 5 Amp plug point | 4 | all 4 on the board of 15 amp points | 1: PL1 - Level 1 Patuli | Kitchen | Electrical | Planned | 2021-07-10 | Anirban | 2021-07-18 | Arati | 2000 | 2000 | Ask electritian to install
107 |  | Table top surface | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | Furniture | Planned | 2021-07-10 | Anirban |  |  | 3000 | 3000
108 |  | Microwave oven | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | Appliance | Planned | 2021-07-10 | Anirban |  |  | 6000 | 6000
109 |  | Electric Kettle | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | Appliance | Planned | 2021-07-10 | Anirban |  |  | 1500 | 1500
110 |  | Tea sieve | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | Planned | 2021-07-10 | Anirban |  |  | 100 | 100
111 |  | Cups | 6 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | Planned | 2021-07-10 | Anirban |  |  | 300 | 300
112 |  | Coffee mugs | 6 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | Planned | 2021-07-10 | Anirban |  |  | 300 | 300
113 |  | Glasses | 6 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | Planned | 2021-07-10 | Anirban |  |  | 300 | 300
114 |  | Plates | 6 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | Planned | 2021-07-10 | Anirban |  |  | 600 | 600
115 |  | Spoons | 6 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | Planned | 2021-07-10 | Anirban |  |  | 150 | 150
116 |  | Fork | 6 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | Planned | 2021-07-10 | Anirban |  |  | 150 | 150
117 |  | Utensils tray | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | Planned | 2021-07-10 | Anirban |  |  | 300 | 300
118 |  | Scrub | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | Planned | 2021-07-10 | Anirban |  |  | 100 | 100
119 |  | Dish washing liquid | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | Planned | 2021-07-10 | Anirban |  |  | 100 | 100
120 |  | Sugar container | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | Planned | 2021-07-10 | Anirban |  |  | 100 | 100
121 |  | Sugar | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | Food/Baverage | Planned | 2021-07-10 | Anirban |  |  | 100 | 100
122 |  | Tea container | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | Planned | 2021-07-10 | Anirban |  |  | 100 | 100
123 |  | Tea bags | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | Food/Baverage | Planned | 2021-07-10 | Anirban |  |  | 200 | 200
124 |  | Dairy creamer container | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | Planned | 2021-07-10 | Anirban |  |  | 100 | 100
125 |  | Dairy creamer | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | Food/Baverage | Planned | 2021-07-10 | Anirban |  |  | 200 | 200
126 |  | Coffee Container | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | Planned | 2021-07-10 | Anirban |  |  | 100 | 100
127 |  | Coffee | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | Food/Baverage | Planned | 2021-07-10 | Anirban |  |  | 500 | 500
128 |  | Biscuits container | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | Planned | 2021-07-10 | Anirban |  |  | 100 | 100
129 |  | Biscuits | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | Food/Baverage | Planned | 2021-07-10 | Anirban |  |  | 200 | 200
130 |  | Water dispenser | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | Planned | 2021-07-10 | Anirban |  |  | 200 | 200
131 |  | Water barrel (20ltr) | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | Food/Baverage | Planned | 2021-07-10 | Anirban |  |  | 200 | 200
132 |  | Mops & wipes | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | Planned | 2021-07-10 | Anirban |  |  | 300 | 300
133 |  | Dust bin | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | Planned | 2021-07-10 | Anirban |  |  | 500 | 500
134 |  | Bin bag packets | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | Planned | 2021-07-10 | Anirban |  |  | 200 | 200
135 |  | Wash basin | 1 | At ground floor entrance | 1: PL1 - Level 1 Patuli | Other | Plumbing | Planned | 2021-07-10 | Anirban |  |  | 4000 | 4000
136 |  | Liquid soap bottle | 1 | At ground floor entrance | 1: PL1 - Level 1 Patuli | Other | House keeping | Planned | 2021-07-11 | Anirban |  |  | 200 | 200
137 |  | Soap dispenser | 1 | At ground floor entrance | 1: PL1 - Level 1 Patuli | Other | House keeping | Planned | 2021-07-11 | Anirban |  |  | 100 | 100
138 |  | Hand sanitizer | 1 | At ground floor entrance | 1: PL1 - Level 1 Patuli | Other | House keeping | Planned | 2021-07-11 | Anirban |  |  | 1000 | 1000
139 |  | Hand sanitizer dispenser | 1 | At ground floor entrance | 1: PL1 - Level 1 Patuli | Other | House keeping | Planned | 2021-07-11 | Anirban |  |  | 500 | 500
140 |  | Toilet paper packs | 1 | At ground floor entrance | 1: PL1 - Level 1 Patuli | Other | House keeping | Planned | 2021-07-11 | Anirban |  |  | 1000 | 1000
141 |  | Tissue dispenser | 1 | At ground floor entrance | 1: PL1 - Level 1 Patuli | Other | House keeping | Planned | 2021-07-11 | Anirban |  |  | 2000 | 2000
142 |  | Dust bin | 1 | At ground floor entrance | 1: PL1 - Level 1 Patuli | Other | House keeping | Planned | 2021-07-10 | Anirban |  |  | 500 | 500
143 |  | Bin bag packets | 1 | At ground floor entrance | 1: PL1 - Level 1 Patuli | Other | House keeping | Planned | 2021-07-10 | Anirban |  |  | 200 | 200

## MVPItemList
Sl # | Item Group | Item | Item Count | Item Description | Studio Floor | Room | Type | Revised Estimate ₹174650 | Notes
7 | Glass Board | Glass board (light board) | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Videography | 50000
8 | Glass Board | Glass board (light board) marker set (Black, Green, Blue, Red + duster + eraser spray) |  | To be provided by glass board vendor | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Stationaries |  | Available with Glass board
9 | Glass Board | Glass board wall paper / poster | 2-3 | 7ft x 7ft each: * White - fancy brick texture / sky * Natural setting - forest / beach * Dark - night sky / astronomy / texture | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Videography | 6000
10 | Glass Board | Glass board wall paper / poster hanger with clips | 1 | * Will not be required if wall papers are glued to walls. * Height to be adjusted so that the top of wallpaper / poster is at 7'. Dependency: can be instlled only after procuring wall paper / poster | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Videography | 1500
1 | Glass Board | Sleek minimalist chair | 1 | This is a prop and will come in film | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | 1500
2 | Glass Board | Plastic stool | 1 | Can be used by videographer / director | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | 300
3 | Glass Board | Green screen | 1 | To be provided by glass board vendor | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Videography |  | Available with Glass board
4 | Glass Board | White screen | 1 | To be provided by glass board vendor | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Videography |  | Available with Glass board
5 | Glass Board | Black screen | 1 | To be provided by glass board vendor | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Videography |  | Available with Glass board
6 | Glass Board | Screen hanger set | 1 | One hanger set for all 3 screens. To be provided by glass board vendor. | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Videography |  | Available with Glass board
11 | Flat Background | White brick texture wall paper | 1 | Example Flat Background | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Videography |  | Reuse glassboard wall paper
12 | Flat Background | Office chair | 1 | Moderatly good quality | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | 7000
13 | Flat Background | Sleek computer table | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | 3000
14 | Flat Background | Photo frame | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | 1000
15 | Flat Background | Indoor plants | 2 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | 1000
16 | Flat Background | Fancy table lamp | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | 1000
17 | Flat Background | Fancy computer monitor | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Computing | 6000
18 | Flat Background | Keyboard | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Computing | 1000
19 | Flat Background | Mouse | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Computing | 300
20 | Flat Background | Mouse pad | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Computing | 200
21 | Flat Background | Fancy water bottle | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Stationaries | 300
22 | Flat Background | Fancy pencil stand | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Stationaries | 200
23 | Flat Background | Flower vase / small sculpture | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | 500
24 | White board | White board | 1 | 6 ft x 4 ft | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Stationaries | 4000
25 | White board | White board wall hanger | 1 | Height to be adjusted so that the top of white board is at 6'6". Dependency: can be wall-mounted only after procuring white board | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | 1000
26 | White board | White board marker set (Black, Green, Blue, Red + duster + eraser spray) | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Stationaries | 1500
27 | White board | White board marker, duster stand / platform | 1 | Preferably fixed at the bottom of the white board. | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | 1000
28 | Corner background | Bookshelf 5ft x 3ft x 1ft | 1 | Example Corner Background | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | 8000
29 | Corner background | Books | 40-50 | About size of a standard diary each | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Stationaries |  | Arrange from home
30 | Corner background | Indoor plants | 8-10 | Different sizes, 6" to 2' | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | 2000
31 | Corner background | Fancy lantern | 1 | Small size | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | 1000
32 | Corner background | Rock salt lamp | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | 1000
33 | Corner background | Sculpture / vase | 1 | 1' | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | 1000
34 | Corner background | Painting / wall calendar | 1 | 1'6" x 2' | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | 1000
35 | Corner background | Artificial vintage window | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | 2500
36 |  | 15 Amp plug point | 3 | On one wall | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Electrical | 2100
37 |  | 5 Amp plug point | 4 | 2 on the board of 15 amp points, 2 on opposite wall | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Electrical | 2000
38 |  | Tube light | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Electrical | 1500
39 |  | Bulb | 1 | On opposite wall of tube light | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Electrical | 1000
40 |  | Ceiling fan | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Electrical | 3000
41 |  | Thick doormat | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | House keeping | 300
42 |  | 15 Amp plug point | 2 | On one wall | 1: PL1 - Level 1 Patuli | Changing Room | Electrical | 1500
43 |  | 5 Amp plug point | 4 | 2 on the board of 15 amp points, 2 on opposite wall | 1: PL1 - Level 1 Patuli | Changing Room | Electrical | 2000
44 |  | Tube light | 1 |  | 1: PL1 - Level 1 Patuli | Changing Room | Electrical | 1500
45 |  | Table fan | 1 |  | 1: PL1 - Level 1 Patuli | Changing Room | Electrical | 1500
46 |  | Window curtain hangers | 1 |  | 1: PL1 - Level 1 Patuli | Changing Room | Furniture | 2000
47 |  | Window curtain | 1 | Dependency: can be instlled only after installing hangers | 1: PL1 - Level 1 Patuli | Changing Room | Furniture | 1000
48 |  | Vanity Dressing Table set with light + mirror + stool | 1 | Example3 | 1: PL1 - Level 1 Patuli | Changing Room | Furniture |  | Arrange from home
49 |  | Clothes rack | 1 |  | 1: PL1 - Level 1 Patuli | Changing Room | Furniture |  | Arrange from home
50 |  | Hangers | 12 |  | 1: PL1 - Level 1 Patuli | Changing Room | Furniture |  | Arrange from home
51 |  | Dust bin | 1 |  | 1: PL1 - Level 1 Patuli | Changing Room | House keeping | 500
52 |  | Bin bag packets | 1 |  | 1: PL1 - Level 1 Patuli | Changing Room | House keeping | 200
53 |  | Thick doormat | 1 |  | 1: PL1 - Level 1 Patuli | Changing Room | House keeping | 300
54 |  | Wash basin | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | Plumbing | 4000
55 |  | Liquid soap bottle | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | 200
56 |  | Soap dispenser | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | 100
57 |  | Mug | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | 50
58 |  | Bucket | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | 400
59 |  | Dust bin | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | 500
60 |  | Bin bag packets | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | 100
61 |  | Broom stick | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | 400
62 |  | Dust pan | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | 200
63 |  | Cleaning mop | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | 600
64 |  | Vaccum cleaner | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping |  | Arrange from home
65 |  | Feather duster | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | 300
66 |  | Phynile | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | 200
67 |  | Acid | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | 100
68 |  | Cleaning soap | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | 200
69 |  | Hand sanitizer | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | 1000
70 |  | Hand sanitizer dispenser | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | 500
71 |  | Toilet paper packs | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | 1000
72 |  | Tissue dispenser | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | 2000
73 |  | C folds | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | 1000
74 |  | C folds dispenser | 1 | Toilet / Housekeeping / Cleaning | 1: PL1 - Level 1 Patuli | Toilet | House keeping | 2000
75 |  | Thick doormat | 1 |  | 1: PL1 - Level 1 Patuli | Toilet | House keeping | 300
76 |  | 15 Amp plug point | 2 | On one wall | 1: PL1 - Level 1 Patuli | Office | Electrical | 1500
77 |  | 5 Amp plug point | 8 | 4 on the board of 15 amp points, 4 on opposite wall | 1: PL1 - Level 1 Patuli | Office | Electrical | 4000
78 |  | Hard big table | 1 | Conference / dining table | 1: PL1 - Level 1 Patuli | Office | Furniture | 2000
79 |  | Plactic Chairs | 4 |  | 1: PL1 - Level 1 Patuli | Office | Furniture | 2000
80 |  | Wifi | 1 |  | 1: PL1 - Level 1 Patuli | Office | Computing | 5000
81 |  | Thick doormat | 1 |  | 1: PL1 - Level 1 Patuli | Office | House keeping | 300
82 |  | 15 Amp plug point | 2 | On one wall | 1: PL1 - Level 1 Patuli | Kitchen | Electrical | 1500
83 |  | 5 Amp plug point | 4 | all 4 on the board of 15 amp points | 1: PL1 - Level 1 Patuli | Kitchen | Electrical | 2000
84 |  | Table top surface | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | Furniture | 3000
85 |  | Microwave oven | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | Appliance | 6000
86 |  | Electric Kettle | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | Appliance | 1500
87 |  | Tea sieve | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | 100
88 |  | Cups | 6 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | 300
89 |  | Coffee mugs | 6 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | 300
90 |  | Glasses | 6 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | 300
91 |  | Plates | 6 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | 600
92 |  | Spoons | 6 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | 150
93 |  | Fork | 6 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | 150
94 |  | Utensils tray | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | 300
95 |  | Scrub | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | 100
96 |  | Dish washing liquid | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | 100
97 |  | Sugar container | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | 100
98 |  | Sugar | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | Food/Baverage | 100
99 |  | Tea container | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | 100
100 |  | Tea bags | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | Food/Baverage | 200
101 |  | Dairy creamer container | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | 100
102 |  | Dairy creamer | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | Food/Baverage | 200
103 |  | Coffee Container | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | 100
104 |  | Coffee | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | Food/Baverage | 500
105 |  | Biscuits container | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | 100
106 |  | Biscuits | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | Food/Baverage | 200
107 |  | Water dispenser | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | 200
108 |  | Water barrel (20ltr) | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | Food/Baverage | 200
109 |  | Mops & wipes | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | 300
110 |  | Dust bin | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | 500
111 |  | Bin bag packets | 1 |  | 1: PL1 - Level 1 Patuli | Kitchen | House keeping | 200
112 |  | Wash basin | 1 | At ground floor entrance | 1: PL1 - Level 1 Patuli | Other | Plumbing | 4000
113 |  | Liquid soap bottle | 1 | At ground floor entrance | 1: PL1 - Level 1 Patuli | Other | House keeping | 200
114 |  | Soap dispenser | 1 | At ground floor entrance | 1: PL1 - Level 1 Patuli | Other | House keeping | 100
115 |  | Hand sanitizer | 1 | At ground floor entrance | 1: PL1 - Level 1 Patuli | Other | House keeping | 1000
116 |  | Hand sanitizer dispenser | 1 | At ground floor entrance | 1: PL1 - Level 1 Patuli | Other | House keeping | 500
117 |  | Toilet paper packs | 1 | At ground floor entrance | 1: PL1 - Level 1 Patuli | Other | House keeping | 1000
118 |  | Tissue dispenser | 1 | At ground floor entrance | 1: PL1 - Level 1 Patuli | Other | House keeping | 2000
119 |  | Dust bin | 1 | At ground floor entrance | 1: PL1 - Level 1 Patuli | Other | House keeping | 500
120 |  | Bin bag packets | 1 | At ground floor entrance | 1: PL1 - Level 1 Patuli | Other | House keeping | 200

## ActionList
Sl # | Action | Planned Date | Revised Date | Studio Floor | Room | Type | Status | Assigned To | Notes
1 | Electritian
2 | Plumbing
3 | Cleaning
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250

## MasterData
Studio Floor | Room | Area (sqmt) | Type | Status | Admin Team | Item Group
1: PL1 - Level 1 Patuli | Shooting Room 1 | 10.675 | Appliance | Planned | Amit
2: PL2 - Level 2 Patuli | Shooting Room 2 | 10.3106 | Computing | Assigned | Anirban
3: PL3 - Level 3 Patuli | Office |  | Electrical | Issue | Arati
4: VA1 - Arena 1 V Park | Changing Room | 9.5325 | Electronics | Complete | Avishek
5: VA2 - Arena 2 V Park | Kitchen |  | Food/Baverage |  | Other |  | 3500 | 11 | 5.7953
6: VA3 - Arena 3 V Park | Toilet |  | Furniture |  |  |  | 3050 | 10 | 0.07874
| Other |  | House keeping |  |  |  | 925 | 3 | 0.41732
|  |  | Plumbing |  |  |  | 2575 | 8 | 5.378
|  |  | Stationaries |  |  |  | 2125 | 6 | 11.6614
Videography
Other