## Cover Sheet
StudioSetup
Administrative Planning for Anodiam Studio Setup
Version | Editor | Reviewer | Date | Note
1.0 | AC | AM | 2021-07-19 | Initial version

## ItemList
Sl # | Item | Item Count | Item Description | Studio Floor | Room | Type | Status | Last Action Date | Actioned By | Next Action Date | Assigned To | Notes
1 | 15 Amp plug point | 3 | On one wall | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Electrical | Planned | 2021-07-10 | Anirban | 2021-07-18 | Arati | Ask electritian to install
2 | 5 Amp plug point | 4 | 2 on the board of 15 amp points, 2 on opposite wall | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Electrical | Planned | 2021-07-10 | Anirban | 2021-07-18 | Arati | Ask electritian to install
3 | Tube light | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Electrical | Planned | 2021-07-10 | Anirban | 2021-07-18 | Arati | Ask electritian to install
4 | Bulb | 1 | On opposite wall of tube light | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Electrical | Planned | 2021-07-10 | Anirban | 2021-07-18 | Arati | Ask electritian to install
5 | Ceiling fan | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Electrical | Planned | 2021-07-10 | Anirban | 2021-07-18 | Arati | Ask electritian to install
6 | Split Air Con | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Appliance | Planned | 2021-07-10 | Anirban | 2021-07-18 | Arati | Ask electritian to install infrastructure
7 | Window curtain hangers | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | Planned | 2021-07-10 | Anirban | 2021-07-18 | Arati | Ask electritian to install
8 | Window curtain | 1 | Dependency: can be instlled only after installing hangers | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | Planned | 2021-07-10 | Anirban | 2021-07-18 | Arati | To be installed
9 | Sleek minimalist chair | 1 | This is a prop and will come in film | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | Planned | 2021-07-10 | Anirban
10 | Plastic stool | 1 | can be used by videographer / director | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Furniture | Planned | 2021-07-10 | Anirban
11 | Green screen | 1 | To be provided by glass board vendor | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Videography | Planned | 2021-07-10 | Anirban |  |  | To be procured with glass board / light board
12 | White screen | 1 | To be provided by glass board vendor | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Videography | Planned | 2021-07-10 | Anirban |  |  | To be procured with glass board / light board
13 | Black screen | 1 | To be provided by glass board vendor | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Videography | Planned | 2021-07-10 | Anirban |  |  | To be procured with glass board / light board
14 | Screen hanger set | 1 | One hanger set for all 3 screens. To be provided by glass board vendor. | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Videography | Planned | 2021-07-10 | Anirban |  |  | To be procured with glass board / light board
15 | Glass board (light board) | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Videography | Planned | 2021-07-10 | Anirban
16 | Glass board (light board) marker set (Black, Green, Blue, Red + duster + eraser spray) |  | To be provided by glass board vendor | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Videography | Planned | 2021-07-10 | Anirban |  |  | To be procured with glass board / light board
17 | Glass board wall paper / poster | 2-3 | 7ft x 7ft each: * White - fancy brick texture / sky * Natural setting - forest / beach * Dark - night sky / astronomy / texture | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Videography | Planned | 2021-07-10 | Anirban
18 | Glass board wall paper / poster hanger with clips | 1 | * Will not be required if wall papers are glued to walls. * Height to be adjusted so that the top of wallpaper / poster is at 7'. Dependency: can be instlled only after procuring wall paper / poster | 1: PL1 - Level 1 Patuli | Shooting Room 1 | Videography | Planned | 2021-07-10 | Anirban
19 | 1 flat background + study desk setup |  |  | 1: PL1 - Level 1 Patuli | Shooting Room 1
20 |  |  |  | 1: PL1 - Level 1 Patuli | Shooting Room 1
21 |  |  |  | 1: PL1 - Level 1 Patuli | Shooting Room 1
22 |  |  |  | 1: PL1 - Level 1 Patuli | Shooting Room 1
23 | Thick doormat | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | House keeping
24 | 15 Amp plug point |  |  | 1: PL1 - Level 1 Patuli | Shooting Room 2
25 | 5 Amp plug point |  |  | 1: PL1 - Level 1 Patuli | Shooting Room 2
26 | Tube light |  |  | 1: PL1 - Level 1 Patuli | Shooting Room 2
27 | Bulb |  |  | 1: PL1 - Level 1 Patuli | Shooting Room 2
28 | Ceiling fan |  |  | 1: PL1 - Level 1 Patuli | Shooting Room 2
29 | Split Air Con |  |  | 1: PL1 - Level 1 Patuli | Shooting Room 2
30 | Window curtain |  |  | 1: PL1 - Level 1 Patuli | Shooting Room 2
31 | Window curtain hangers |  |  | 1: PL1 - Level 1 Patuli | Shooting Room 2
32 | Sleek minimalist chair | 1 | This is a prop and will come in film | 1: PL1 - Level 1 Patuli | Shooting Room 2
33 | Touch screen monitor board set () |  |  | 1: PL1 - Level 1 Patuli | Shooting Room 2
34 | Background #1 |  | Example2 | 1: PL1 - Level 1 Patuli | Shooting Room 2
35 | Background #2 |  | Example1 | 1: PL1 - Level 1 Patuli | Shooting Room 2
36 | White board | 1 | 6 ft x 4 ft | 1: PL1 - Level 1 Patuli | Shooting Room 2
37 | White board wall hanger | 1 | Height to be adjusted so that the top of white board is at 6'6". Dependency: can be wall-mounted only after procuring white board | 1: PL1 - Level 1 Patuli | Shooting Room 2
38 | White board marker set (Black, Green, Blue, Red + duster + eraser spray) | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 2
39 | White board marker, duster stand / platform | 1 | Preferably fixed at the bottom of the white board. | 1: PL1 - Level 1 Patuli | Shooting Room 2
40 | 1 corner background + bookshelf setup
41
42
43
44
45 | Thick doormat | 1 |  | 1: PL1 - Level 1 Patuli | Shooting Room 1 | House keeping
46
47
48
49
50
51
52
53 | Thick doormat
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250

## ActionList
Sl # | Action | Planned Date | Revised Date | Studio Floor | Room | Type | Status | Assigned To | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250

## MasterData
Studio Floor | Room | Type | Status | Admin Team
1: PL1 - Level 1 Patuli | Shooting Room 1 | Appliance | Planned | Amit
2: PL2 - Level 2 Patuli | Shooting Room 2 | Computing | Assigned | Anirban
3: PL3 - Level 3 Patuli | Office | Electrical | Issue | Arati
4: VA1 - Arena 1 V Park | Changing Room | Electronics | Complete | Avishek
5: VA2 - Arena 2 V Park | Kitchen | Food/Baverage |  | Other
6: VA3 - Arena 3 V Park | Toilet | Furniture
| Other | House keeping
Plumbing
Stationaries
Videography
Other