## Cover Sheet
Anodiam
Product Backlog
Rolling Versions
Version | Editor | Reviewer | Date | Note
0.1 | AC |  | 2020-06-20 | Initial version
1.0 | AC | AM | 2020-07-03 | Backlog Refining done For Sprint 2.0

## OldProductBacklog
Item # | Item Type | Item Size | As a… | I want to be able to… | So that… | Acceptance Criteria (inserta note) | Notes / References | Task Estimates (Story Points) | Business Value | Priority | Status | Sprint Number
1 | Feature | Story | Unsigned User (intending to be student) | visit the home page of anodiam.com | I can view image links to few best rated courses and a link to Sign up and another link to log in. | Given I am an unsigned user When I type anodiam.com on a web browser Then I should be able to see the Anodiam home page: containing image links to few best rated courses and a valid link to Sign up to anodiam.com and another link to log in. | ..\ProjectExecution\BA\SpecsWireframes\001Wireframes.pptx | 13 | 5 | 0.38462 | Scheduled | 2
1.1 | Enabler | Story | Home Page Responsive HTML, Image and fonts selection |  |  |  | ..\ProjectExecution\BA\Functional requirements | 8 | 4 | 0.5 | Scheduled | 2
2 | Feature | Story | Unsigned User (intending to be student) | Enter my personal details to Sign up to anodiam.com | I can register myself to create my User Id and Password in Anodiam. | Given I am an unsigned user When I visit sign up link on Anodiam home page and enter my valid personal details Then I must be registered into Anodiam with my userid & passwrd |  | 13 | 5 | 0.38462 | Scheduled | 2
2.1 | Enabler | Story | Security of Sign Up page |  |  |  |  | 13 | 5 | 0.38462 | Scheduled | 2
3 | Feature | Story | signed up but unloggedin User (student) | Enter my registered userid and password to Log in to Anodiam. | I can view the user account page | Given I'm an unloggedin but signed up user When I enter my valid login details in the login page Then I must be able to login to anodiam and view my Anodiam user account page |  | 8 | 5 | 0.625 | Initial
3.1 | Enabler | Story | After user enters login and password, the credential gets validated from backend, then JWT token gets generated in the backend. The token is sent back to client. |  |  | Given a successful login happens into Anodiam through Postman Tool When I enter my valid login details in the Postman Tool Then I should be able to view the valid token in Postman Tool |  | 8 | 5 | 0.625
4 | Feature | Story | As a logged in Student user | View my Anodiam user account page | So that I can view my list of enrolled courses, Search for new courses and see a logout link in my Anodiam user account | Given I am a logged in Student user When I log into Anodiam Then I shall be able to see my Anodiam user account page containing my list of enrolled courses, Search for new courses and see a logout link |  | 5 | 5 | 1 | Initial
5 | Feature | Story | As a logged in Student user | View Course Details (a list of all videos) inside each enrolled course in my Anodiam user account | I can play the video lessons inside that particular course | Given I am a logged in Student user When I view any course inside my Anodiam user account Then I should be able to see a list of all video lessons inside that particular course. |  | 5 | 5 | 1 | Initial
6 | Feature | Story | As a logged in Student user | Play each video from the list of videos displayed in each enrolled course under my Anodiam user account | I can watch each of the video lessons | Given I am a logged in Student user When I click on each of the videos from the list of videos displayed in each enrolled course under my Anodiam user account Then the particular video must play completely and I should be able to watch the video lesson. |  | 5 | 5 | 1 | Initial
7 | Enabler | Story | Into a single stand alone (Dev) Kubernetes cluster in GCP, deploy seed APP (containing basic features in Items 1 through 6, namely, Home page, Sign up, Login, User Account, Course Details and Play Video). |  |  | Given a Student User (intended, signed up or logged in) When I test all acceptance criterias for items 1 through 6 Then each should pass for the app deployed in GCP K8s. |  | 8 | 5 | 0.625 | Initial
8 | Enabler | Story | Create a CI / CD pipeline containing Dev, Test, Staging and Prod environments (K8s clusters on GCP) and deploy the seed APP. |  |  | Given a Student User(intended, signed up or logged in) When I test all acceptance criterias for items 1 through 6 Then each one should pass for the app deployed in all the 4 environments in GCP K8s (Dev, Test, Staging and Prod). |  | 13 | 5 | 0.38462 | Initial
| Feature | Story | Unsigned User (intending to be teacher) | visit the page of anodiam.com/teacher | I can view link to sign up (for teacher registration) and a form to login (for registered teachers) | Given I am an unsigned user (intending to be teacher) When I type anodiam.com/teacher on a web browser Then I should be able to see the page: containing a form to log in (for registered teachers) and also a link to Sign up as a teacher to teacher application. |  |  | 5
9 | Feature | Story | Unsigned User (intending to be teacher) | Click on the sign up as teacher link | I can access the teacher sign up form | Given I am an unsigned user (intending to be teacher) When I click the sign up as teacher link Then I should be able to see the Teacher Signup form with all its relevent fields, a control to upload my CV, the terms and conditions and a submit button. |  | 13 | 5 | 0.38462 | Initial
| Feature | Story | Unsigned User (intending to be teacher) | Click on the Submit button in the Teacher Signup form after filling up the relevent fields including choosing my user id, uploading my CV, and accepting the terms and conditions | Anodiam admin app will be notified to contact me to accept or reject my teacher's expression of interest to join Anodiam. | Given I am an unsigned user (intending to be teacher) When I key in all the details in the form including choosing my user id, attach my CV, accept the terms and conditions and click on the Submit button Then I should be able to see a page saying that Anodiam admin will contact me. Also I should receive an email from Anodiam Admin stating the same.
| Feature | Story | This is an external dependency on the Anodiam Admin app. No action is required from any users of the Teacher's App. |  |  | Offline to the Anodiam Teacher app, Anodiam Admin app users will be able to accept or reject the above (intending to be) teacher's expression of interest to join Anodiam
| Feature | Story | Unsigned User (intending to be teacher) Rejected by Anodiam Admin | Receive a regret email from Anodiam Admin about the status (rejection) of my above teacher's expression of interest to join Anodiam. | I can know the reason for rejection and the date before which I should not try to reapply. | Given I am an unsigned user rejected by Anodiam Admin to become a teacher When I receive a regret email from Anodiam Admin Then I should be able to know the reason for my rejection and the date before which I should not try to reapply.
| Feature | Story | Unsigned User (intending to be teacher) Accepted by Anodiam Admin | Receive a congratulations email from Anodiam Admin about the status (acceptance) of my above teacher's expression of interest. | I can get link to create passord for my chosen user id. | Given I am an unsigned user accepted by Anodiam Admin to become a teacher When I receive a Acceptance email from Anodiam Admin Then I should be able to see a link to create password for my user id.
| Feature | Story | Unsigned User (intending to be teacher) Accepted by Anodiam Admin | Click on the link to visit the page to create password for my user id. | I can visit the page to create my password where "enter password", "confirm password" (both in hide password format) and "submit button" will be displayed. | Given I am an unsigned user accepted by Anodiam Admin to become a teacher When I click on the link to visit the page to create password for my user id Then I should be able to visit the page to create my password.
| Feature | Story | Unsigned User (intending to be teacher) Accepted by Anodiam Admin | Create the password putting my details in the given fields | I can create my password and save it for the future use by clicking on the save button. | Given I am an unsigned user accepted by Anodiam Admin to become a teacher When I create the password putting my details in the given fields Then I should be able to create my password and save it for the future use by clicking on the save button.
10 | Feature | Story | As a logged in teacher user | login into anodiam.com | So that I can view and upload my list of course videos and question papers, see a logout link in my Anodiam user account | Given I am a logged in teacher user When I log into Anodiam Then I shall be able to see my Anodiam user account page containing my list of uploaded courses,question papers and see a logout link |  | 13 | 5 | 0.38462 | Initial
11 | Feature | Story | As a logged in teacher user | View my Anodiam user account page | So that I can view answer sheets submitted by each student | Given I am a logged in teacher user When I log into Anodiam Then I shall be able to see answer sheet submitted by each student. |  | 13 | 5 | 0.38462 | Initial
0
12 | [6 empty] | Old Password,New Pass word,Confirm Password,Submit button and Cancel button |  |  | 0
13 | Feature | Story | Student | see comment if put wrong password | I can change password | given I put wrong password , when the password I give doesn’t match with my saved password then I'll receive a comment saying my password is wrong and then I can click on forget password button to change password | Emaild Id,Submit button and Cancel Button. |  | 4 | 0 | Initial
14 | Feature | Story | Student | access forget password | able to access password if forgotton/change password | given I want to change my password or I forget the password , when I click on forget password button then I'll be able to validate my account by giving the email id I provided in the website during account creation so that the password change link can be sent in my email and I can change the password by clicking in the link and get in to the website | After hitting Submit button , system will generate unique Student Code which will be mailed student and gurdian. |  |  | 0
15 | Feature | Story | Student | get a unique identification number | only me or my designated gurdian or one of the parent's can access my profile | given I want to study thorugh the website when I create my profile with validated criteria then an unique student number will be generated | 1) Drop Down Box for Standard 2)Drop Down Box for Board or University 3)Other if nothing matches in drop down for board/University, he/she can write 4) Multiple select for subjects |  | 5 | 0 | Initial
16 | Feature | Story | Student | have my own profile | I can put my personal details | given I want to make my profile , when I give my details in the form like Name, DOB, Standard, Board, Subjects then I am creating my basic profile |  |  | 1 | 0 | Initial
17 | Feature | Story | Student | have my own profile | I can put some further details | given I put further details in my profile for assistance , when I select which subject I'm best in and I'm weak in from the drop down menu then I'll be able to get assistance for the best courses designed for me | 1) Check Box for accessibility |  |  | 0
18 | Feature | Story | Student | set the access of my profile | the private things in my profile are not visible by others | given I'm in my rpofile and I'm adult, when I'll set the access as private then no one can see my profile |  |  |  | 0
19 | Feature | Story | Student | set the access of my profile | I can set access public | given I'm in my profile and I'm minor when I'll set the access to parents/gurdian then one of the parents (who is liked with the profile) or gurdian (who is linked with the profile) can see my profile |  |  |  | 0
20 |  |  |  | purchase a course | [5 empty] | 0
21 |  |  |  | purchase videos | [5 empty] | 0
22 |  |  |  | Examination Details |  |  | Entry of Student Details in Edit Mode |  | 3 | 0 | Initial
23 | Feature | Story | Student | have my own profile | I can see my courses which I've entered data | given I'm inside my profile when I buy courses then I can see them inside my profile |  |  | 4 | 0 | Initial
24 | Feature | Story | Student | have my own profile | I can see the videos I bought or got free | given I'm inside my profile when I buy videos then I can see them inside my profile | Edit screen of Examination Details and result data given by Teacher |  | 5 | 0 | Initial
25 | Feature | Story | Student | have my own profile | I can see my test papers of all subjects which ive appeared for and results of all of them | given I'm inside my profile when I give tests on one or many subjects or many tests in on esubjects then the results should be there with the test papers in my profile |  |  | 1 | 0 | Initial
26 | Feature | Story | Student | have my own profile | I can see the remarks given by the teacher on test papers | given I'm inside my profile when I will see my checked test papers then I can see the special notes from teachers | 2 Note Fields. 1) One for Student and 2)One for Teacher |  | 2 | 0 | Initial
27 | Feature | Story | Student | have my own profile | I can make notes for future reference | given I'm inside my profile when I will make notes about which area to improve based on teacher's remarks so that I can refer it when I appear for the test next time then I'll be able to make the notes with the subject as a tag or comment |  |  | 3 | 0 | Initial
28 | Feature | Story | Student | have my own profile | I can make notes for teachers to check | given im inside a subject in my profile when I want to keep note for the teacher about any clarification then I can see that |  |  | 4 | 0 | Initial
29 | Feature | Story | Student | have my own profile | I can make notes with date and time mentioned | given I'm inside my profile when I'm making notes for the teacher's reference then a date and time should be metioned for further reference |  |  | 5 | 0 | Initial
30 | Feature | Story | Student | have my own profile | I can see the notes from teachers with date and time reference | given I'm inside my profile , when I'll check the response of my notes then I'll be able to see answers from the teacher's with date and time reference |  |  |  | 0
31 | Feature | Story | Student | edit my profile | I can change details when needed | given I'm editing my profile, when I change/add or alter details in m profile then I'll be able to edit them by clicking on edit profile button |  |  | 1 | 0 | Initial
32 | Feature | Story | Student | see my rating given by the teachers | I can be motivated | given I'm inside my profile when I'm given rating by teachers then I'll be able to see it |  |  | 2 | 0 | Initial
33 | Feature | Story | Student | get rewarded from Anodiam | I can be motivated | rewaards can be given by Anodiam as a free course or badge which can be shared in social media |  |  |  | 0
34 | Feature | Story | Student | not download the videos | I can always see the videos online | given I'm watching the video when I want to save or download the video then it should not be downloaded or saved in the local mechine |  |  |  | 0
35 | Feature | Story | Student | not take the screenshot | I can not keep any document saved | given I'm taking screen shot when I'll try to capture then it should not allow to take the screen shot. |  |  |  | 0
36 | Feature | Story | Student | not copy and paste from the document | I can not keep any document saved | given I'm copying the text when I'll copy and paste the text then it wont allow to do so |  |  |  | 0
37 |  |  | Student | Sign Out | [5 empty] | 0
38 | Feature | Story | Teacher | signup | I can register | given I'm signing up for the website when I sign up with fulfilling valid criteria like name, date of birth, email id and click in the sign up button then I will be able to sign up in to the website. |  |  |  | 0
39 | Feature | Story | Teacher | login | I can go to my profile | given I,m logged in to the website , when I fill in the user name and password field with my valid cridentials and click in the sign in button then I get signed into the website. |  |  |  | 0
40 | Feature | Story | Teacher | create password | I can get into my profile | given I'm creating my password when I'm putting password followed by the instructions like one capital letter, one character, one numner and minimum eight character then the password is created |  |  |  | 0
41 | Feature | Story | Teacher | confirm password | I can get into my profile | given I've created password when I'll confirm the password in confirm password firld then I'll be able to access my profile |  |  |  | 0
42 | Feature | Story | Teacher | have a secure password | my profile is secure | given I'm putting the password in the password field, when I give my valid password and click in the password button then I'll be able to go to my profile after validation . |  |  |  | 0
43 | Feature | Story | Teacher | access Forget Password | able to access password if forgotton/change password | given I want to change my password or I forget the password , when I click on forget password button then I'll be able to validate my account by giving the email id I provided in the website during account creation so that the password change link can be sent in my email and I can change the password by clicking in the link and get in to the website |  |  |  | 0
44 | Feature | Story | Teacher | have my own profile | I can put my personal details | given I want to make my profile , when I give my details in the form like Name, DOB, profession, experience, Subjects that I teach then I am creating my basic profile |  |  |  | 0
45 | Feature | Story | Teacher | have edit profile option | I can change/add or alter my personal details if needed | given I'm editing my profile, when I change/add or alter details in my profile regarding my personal data like experience, qualification, then I'll be able to edit them by clicking on edit profile button |  |  |  | 0
46 | Feature | Story | Teacher | have direction to upload course/videos | I can make the videos available for students | given I upload videos/course meterials, when I'll follow the instructions how to upload a video/course meterial then I'll be able to upload the course/videos |  |  |  | 0
47 | Feature | Story | Teacher | get options where to place my videos/course meterials | my videos/course meterials can be viewed by the students | given I want to place my video in the website, when I'll choose the proper option like free videos/paid videos then students can see the videos in the proper place |  |  |  | 0
48 | Feature | Story | Teacher | upload videos | videos are visible to the audience | given I'm in my profile when I will upload videos after fulfilling criteries likefree or paid and subject check, board check, class check, standard (easy or hard) check then I can upload videos |  |  |  | 0
49 | Feature | Story | Teacher | edit videos before publish | I can publish only error free videos | given I'm uploading my video when I'll check it before clicking publish button then my error checking is done |  |  |  | 0
50 | Feature | Story | Teacher | see the remarks by students | I can answer their remarks | given I'm in my profile when students will ask any question through remarks then I can view them and able to answer |  |  |  | 0
51 | Feature | Story | Student | see the remarks date and time | I can answer accordingly | given I'm viewing the remarks by the students when I click on the remarks then I can see the date and time |  |  |  | 0
52 | Feature | Story | Student | see a notification in my mail | I can understand there is a remark in my profile | given I get a remarks notification when I get a remarks from the student with their UIN about asking any question then I get a system generated notification in my email about the remark so that I can keep a track of remarks from individual sudents. |  |  |  | 0
53 | Feature | Story | Teacher | see remarks by parents | I can answer accordingly | given I get a remark by a parent referring the student's UIN when I get a remark from a parent with their student's UIN then I'll receive a system generated notification in my email |  |  |  | 0
54 | Feature | Story | Teacher | check answers of the test papers | I can do the correction and give marks | given I'm checking a test paper when I'll check test papers for a subject of a class on a standard then I'll be able to correct wrong answers or give marks for right answers |  |  |  | 0
55 | Feature | Story | Teacher | rate students | students get motivation | given I'm rating a student when I student can satisfy certain criteria like course complication within time frame/ getting "A" grade marks in a subject / completing test after finishing course within a time frame then the student will be rated stars |  |  |  | 0
56 | Feature | Story | Teacher | not edit or delete any video or course meterial | editing option is not with me | given I want to delete an uploaded video or course meterial when I try to do this then I should get access denied option |  |  |  | 0
User preference and predicting the most suitable courses for individual user in their home screen
Note on G1: Help: Acceptance Criteria in Product Backlog comprises of 4 fields, namely: Scenerio, Given, When Then. Here all 4 fields should be colated into one. E.g. Acceptance criteria for following should be as below: User Story: As a logged out User I want to be able to sign into the website, so that I can see my profile. Acceptance Criteria: Scenario: Registered User Signs with valid username and password. Given: I am logged out of website. When: I fill in the username and password fields with my valid credentials and click in sign in button Then: I get signed into the website. Here, Acceptance Criteria could be written in 1 sentence as below: Given I am logged out of website, if I fill in the username and password fields with my valid credentials and click in sign in button, I should get signed into the website.
Note on I1: Help: XS : 1 Story Point : 0 to 2 person hours S : 2 Story Points : 2 to 4 person hours M : 3 Story Points : 4 to 8 person hours L : 5 Story Points : 1 to 1.5 person days XL : 8 Story Points : 1.5 to 2.5 person days XXL : 13 Story Points : 0.5 to 1 person weeks XXXL : 21 Story Points : Larger and never used

## ProductBacklog
Item # | Item Type | Item Size | As a… | I want to be able to… | So that… | Acceptance Criteria (inserta note) | Notes / References | Task Estimates (Story Points) | Business Value | Priority | Status | Sprint Number
1 | Feature | Story | Unsigned User (intending to be teacher) | visit the Signup / Login page at the link anodiam.com/teacher | I can view link to sign up (for teacher registration) and a form to login (for registered teachers) | Given I am an unsigned user (intending to be teacher) When I type anodiam.com/teacher on a web browser Then I should be able to see the page: containing a form to log in (for registered teachers) and also a link to Sign up as a teacher to the teacher application. | ..\ProjectExecution\BA\SpecsWireframes\003TeacherAppWireframes.pptx |  | 5 |  | Initial
2 | Feature | Story | Unsigned User (intending to be teacher) | Click on the sign up as teacher link | I can access the teacher sign up form | Given I am an unsigned user (intending to be teacher) When I click the sign up as teacher link Then I should be able to see the Teacher Signup form with all its relevent fields, a control to upload my CV, Cover letter, Profile photo, the terms and conditions and a submit button. | ..\ProjectExecution\BA\SpecsWireframes\004TeacherAppFunctionalSpecs.xlsx |  | 5 | 0 | Initial
3 | Feature | Story | Unsigned User (intending to be teacher) | Click on the Submit button in the Teacher Signup form after filling up the relevent fields including choosing my user id, uploading my CV, and accepting the terms and conditions | Anodiam admin app will be notified to accept or reject my teacher's expression of interest to join Anodiam. | Given I am an unsigned user (intending to be teacher) When I key in all the mandatory and other details in the form including choosing my user id, attach my CV, accept the terms and conditions and click on the Submit button Then I should be able to see a dialogue box saying that Anodiam admin will contact me. Also I should receive an email from Anodiam Admin stating the same. |  |  | 2 |  | Initial
4 | Feature | Story | This is an external dependency on the Anodiam Admin app. No action is required from any users of the Teacher's App. |  |  | Offline to the Anodiam Teacher app, Anodiam Admin app users will be able to accept or reject the above (intending to be) teacher's expression of interest to join Anodiam |  |  | 2 |  | Initial
5 | Feature | Story | Unsigned User (intending to be teacher) Rejected by Anodiam Admin | Receive a regret email from Anodiam Admin about the status (rejection) of my above teacher's expression of interest to join Anodiam. | I can know the reason for rejection and the date before which I should not try to reapply. | Given I am an unsigned user rejected by Anodiam Admin to become a teacher When I receive a regret email from Anodiam Admin Then I should be able to know the reason for my rejection and the date before which I should not try to reapply. |  |  | 2 |  | Initial
6 | Feature | Story | Unsigned User (intending to be teacher) Accepted by Anodiam Admin | Receive a congratulations email from Anodiam Admin about the status (acceptance) of my above teacher's expression of interest. The email should have a link to create password for my chosen user id. | I can create password for my chosen user id. | Given I am an unsigned user accepted by Anodiam Admin to become a teacher When I receive a Acceptance email from Anodiam Admin Then I should be able to see a link to create password for my user id. |  |  | 2
7 | Feature | Story | Unsigned User (intending to be teacher) Accepted by Anodiam Admin | Click on the link to visit the page to create password for my user id. | I can visit the Password Creation page to create my password where "enter password", "confirm password" (both in hide / show password format) and submit button will be displayed. | Given I am an unsigned user accepted by Anodiam Admin to become a teacher When I click on the link to visit the page to create password for my user id Then I should be able to visit the page to create my password. |  |  | 2
8 | Feature | Story | Unsigned User (intending to be teacher) Accepted by Anodiam Admin | Create the password putting my details in the "enter password" and "confirm password" fields and click on the submit button. | My password will be saved. | Given I am an unsigned user accepted by Anodiam Admin to become a teacher When I create the password Then by password will be saved |  |  | 5
9 | Feature | Story | Unsigned User (intending to be teacher) Accepted by Anodiam Admin | Create the password putting my details in the "enter password" and "confirm password" fields and click on the submit button. | I shall be forwarded to my Teacher Home page. | Given I am an unsigned user accepted by Anodiam Admin to become a teacher When I create the password and my password will be saved Then I must be forwarded to my Teacher Home page. |  |  | 5
10 | Feature | Story | As an (unsigned) user of Anodiam teacher app | visit the Signup / Login page at anodiam.com/teacher, key in my valid user id and password and click on the Login button. | Login to the teacher app | Given I am a logged in teacher user When I log into Anodiam Teacher App Then I shall be able to see my Anodiam teacher app's Teacher Home page |  |  | 5 | 0
11 | Feature | Story | Unsigned user with forgotton password of Anodiam teacher app | visit the Signup / Login page at anodiam.com/teacher, and find a link to create new password | I shall be able to click the link and visit the Forget Password page | Given I have forgotton my password for Anodiam Teacher app When I click on Forgot Password link in Anodiam Teacher app, Login / Signup page Then I shall be able to visit the Forget Password page | I shall be able to receive an Email in my valid Emai Id containing the link to go to Change/Forgot Password page in Teacher App. |  | 5 | 0
12 | Feature | Story | Unsigned user with forgotton password of Anodiam teacher app | visit the Forget Password page, fill up the required verification details and click on the Send Password button
12 | Feature | Story | As a(intending to Change Password) user of Anodiam teacher app | Click on the Forgot Password / Change Password link | I shall be able to Change Password in the Teacher App | Given I have clicked on the forgotton / chage my password link in my Valid Email Id When I click on "Forgot Password / Change Password" link in my valid Emai id Then I shall be able to go to the Forgot Password / Change Password page in the Teacher App. |  |  | 5 | 0
13 | Feature | Story | As a(intending tohave a new Password) user of Anodiam teacher app | Change the Password | I shall be able to Change Password in the Teacher App through creating a new password | Given I have typed new password in the "New Password field in "Forgot Password / Change Password" page When I type the new Password Then I shall be able to create a New Password the Teacher App. |  |  | 5 | 0
14 | Feature | Story | As a(intending to have a new Password) user of Anodiam teacher app | Confirme Password | I shall be able to Change Password in the Teacher App through confirming the new password | Given I have typed new password When I type the new Password Then I shall be able to create a New Password in the Teacher App. |  |  | 5 | 0
15 | Feature | Story | As a logged in teacher user | View my Anodiam Teacher Home page | I can view my welcome message on top (details in Finctional Spec) | Given I am a logged in teacher user When I log into Anodiam Teache App and view my Teacher Home page Then I shall be able to see my Anodiam teacher app's Teacher Home page with my welcome message on top (details in Finctional Spec) |  |  | 5
16 | Feature | Story | As a logged in teacher user | View my Anodiam Teacher Home page | I can view the Menu Bar. (Details of Menu Bar is explained in the functional specs) | Given I am a logged in teacher user When I log into Anodiam teacher app and view my Anodiam Teacher Home page Then I shall be able to see the Menu Bar |  |  | 5
17 | Feature | Story | As a logged in teacher user | View my Anodiam Teacher Home page | I can view the Course Titles gird of all the courses I have created. (Details of Course Title grid is explained in the functional specs) | Given I am a logged in teacher user When I log into Anodiam teacher app and view my Teacher Home page Then I shall be able to see the Course Titles gird of all the courses I have created |  |  | 5 | 0
18 | Feature | Story | As a logged in teacher user | Create a course by clicking the Create Course button in my Teacher Home page. | I can start creating a new course | Given I am a logged in teacher user When I click on the Create Course button in my Teacher Home page Then I shall be able to create a new course |  |  | 5
Note on G1: Help: Acceptance Criteria in Product Backlog comprises of 4 fields, namely: Scenerio, Given, When Then. Here all 4 fields should be colated into one. E.g. Acceptance criteria for following should be as below: User Story: As a logged out User I want to be able to sign into the website, so that I can see my profile. Acceptance Criteria: Scenario: Registered User Signs with valid username and password. Given: I am logged out of website. When: I fill in the username and password fields with my valid credentials and click in sign in button Then: I get signed into the website. Here, Acceptance Criteria could be written in 1 sentence as below: Given I am logged out of website, if I fill in the username and password fields with my valid credentials and click in sign in button, I should get signed into the website.
Note on I1: Help: XS : 1 Story Point : 0 to 2 person hours S : 2 Story Points : 2 to 4 person hours M : 3 Story Points : 4 to 8 person hours L : 5 Story Points : 1 to 1.5 person days XL : 8 Story Points : 1.5 to 2.5 person days XXL : 13 Story Points : 0.5 to 1 person weeks XXXL : 21 Story Points : Larger and never used