## Cover Sheet
Anodiam
Product Backlog
Rolling Versions
Version | Editor | Reviewer | Date | Note
0.1 | AC |  | 2020-06-20 | Initial version
1.0 | AC | AM | 2020-07-03 | Backlog Refining done For Sprint 2.0

## OldProductBacklog
Item # | Item Type | Item Size | As a… | I want to be able to… | So that… | Acceptance Criteria (inserta note) | Notes / References | Task Estimates (Story Points) | Business Value | Priority | Status | Sprint Number
1 | Feature | Story | Unsigned User (intending to be student) | visit the home page of anodiam.com | I can view image links to few best rated courses and a link to Sign up and another link to log in. | Given I am an unsigned user When I type anodiam.com on a web browser Then I should be able to see the Anodiam home page: containing image links to few best rated courses and a valid link to Sign up to anodiam.com and another link to log in. | ..\ProjectExecution\BA\SpecsWireframes\001Wireframes.pptx | 13 | 5 | 0.38462 | Scheduled | 2
1.1 | Enabler | Story | Home Page Responsive HTML, Image and fonts selection |  |  |  | ..\ProjectExecution\BA\Functional requirements | 8 | 4 | 0.5 | Scheduled | 2
2 | Feature | Story | Unsigned User (intending to be student) | Enter my personal details to Sign up to anodiam.com | I can register myself to create my User Id and Password in Anodiam. | Given I am an unsigned user When I visit sign up link on Anodiam home page and enter my valid personal details Then I must be registered into Anodiam with my userid & passwrd |  | 13 | 5 | 0.38462 | Scheduled | 2
2.1 | Enabler | Story | Security of Sign Up page |  |  |  |  | 13 | 5 | 0.38462 | Scheduled | 2
3 | Feature | Story | signed up but unloggedin User (student) | Enter my registered userid and password to Log in to Anodiam. | I can view the user account page | Given I'm an unloggedin but signed up user When I enter my valid login details in the login page Then I must be able to login to anodiam and view my Anodiam user account page |  | 8 | 5 | 0.625 | Initial
3.1 | Enabler | Story | After user enters login and password, the credential gets validated from backend, then JWT token gets generated in the backend. The token is sent back to client. |  |  | Given a successful login happens into Anodiam through Postman Tool When I enter my valid login details in the Postman Tool Then I should be able to view the valid token in Postman Tool |  | 8 | 5 | 0.625
4 | Feature | Story | As a logged in Student user | View my Anodiam user account page | So that I can view my list of enrolled courses, Search for new courses and see a logout link in my Anodiam user account | Given I am a logged in Student user When I log into Anodiam Then I shall be able to see my Anodiam user account page containing my list of enrolled courses, Search for new courses and see a logout link |  | 5 | 5 | 1 | Initial
5 | Feature | Story | As a logged in Student user | View Course Details (a list of all videos) inside each enrolled course in my Anodiam user account | I can play the video lessons inside that particular course | Given I am a logged in Student user When I view any course inside my Anodiam user account Then I should be able to see a list of all video lessons inside that particular course. |  | 5 | 5 | 1 | Initial
6 | Feature | Story | As a logged in Student user | Play each video from the list of videos displayed in each enrolled course under my Anodiam user account | I can watch each of the video lessons | Given I am a logged in Student user When I click on each of the videos from the list of videos displayed in each enrolled course under my Anodiam user account Then the particular video must play completely and I should be able to watch the video lesson. |  | 5 | 5 | 1 | Initial
7 | Enabler | Story | Into a single stand alone (Dev) Kubernetes cluster in GCP, deploy seed APP (containing basic features in Items 1 through 6, namely, Home page, Sign up, Login, User Account, Course Details and Play Video). |  |  | Given a Student User (intended, signed up or logged in) When I test all acceptance criterias for items 1 through 6 Then each should pass for the app deployed in GCP K8s. |  | 8 | 5 | 0.625 | Initial
8 | Enabler | Story | Create a CI / CD pipeline containing Dev, Test, Staging and Prod environments (K8s clusters on GCP) and deploy the seed APP. |  |  | Given a Student User(intended, signed up or logged in) When I test all acceptance criterias for items 1 through 6 Then each one should pass for the app deployed in all the 4 environments in GCP K8s (Dev, Test, Staging and Prod). |  | 13 | 5 | 0.38462 | Initial
| Feature | Story | Unsigned User (intending to be teacher) | visit the page of anodiam.com/teacher | I can view link to sign up (for teacher registration) and a form to login (for registered teachers) | Given I am an unsigned user (intending to be teacher) When I type anodiam.com/teacher on a web browser Then I should be able to see the page: containing a form to log in (for registered teachers) and also a link to Sign up as a teacher to teacher application. |  |  | 5
9 | Feature | Story | Unsigned User (intending to be teacher) | Click on the sign up as teacher link | I can access the teacher sign up form | Given I am an unsigned user (intending to be teacher) When I click the sign up as teacher link Then I should be able to see the Teacher Signup form with all its relevent fields, a control to upload my CV, the terms and conditions and a submit button. |  | 13 | 5 | 0.38462 | Initial
| Feature | Story | Unsigned User (intending to be teacher) | Click on the Submit button in the Teacher Signup form after filling up the relevent fields including choosing my user id, uploading my CV, and accepting the terms and conditions | Anodiam admin app will be notified to contact me to accept or reject my teacher's expression of interest to join Anodiam. | Given I am an unsigned user (intending to be teacher) When I key in all the details in the form including choosing my user id, attach my CV, accept the terms and conditions and click on the Submit button Then I should be able to see a page saying that Anodiam admin will contact me. Also I should receive an email from Anodiam Admin stating the same.
| Feature | Story | This is an external dependency on the Anodiam Admin app. No action is required from any users of the Teacher's App. |  |  | Offline to the Anodiam Teacher app, Anodiam Admin app users will be able to accept or reject the above (intending to be) teacher's expression of interest to join Anodiam
| Feature | Story | Unsigned User (intending to be teacher) Rejected by Anodiam Admin | Receive a regret email from Anodiam Admin about the status (rejection) of my above teacher's expression of interest to join Anodiam. | I can know the reason for rejection and the date before which I should not try to reapply. | Given I am an unsigned user rejected by Anodiam Admin to become a teacher When I receive a regret email from Anodiam Admin Then I should be able to know the reason for my rejection and the date before which I should not try to reapply.
| Feature | Story | Unsigned User (intending to be teacher) Accepted by Anodiam Admin | Receive a congratulations email from Anodiam Admin about the status (acceptance) of my above teacher's expression of interest. | I can get link to create passord for my chosen user id. | Given I am an unsigned user accepted by Anodiam Admin to become a teacher When I receive a Acceptance email from Anodiam Admin Then I should be able to see a link to create password for my user id.
| Feature | Story | Unsigned User (intending to be teacher) Accepted by Anodiam Admin | Click on the link to visit the page to create password for my user id. | I can visit the page to create my password where "enter password", "confirm password" (both in hide password format) and "submit button" will be displayed. | Given I am an unsigned user accepted by Anodiam Admin to become a teacher When I click on the link to visit the page to create password for my user id Then I should be able to visit the page to create my password.
| Feature | Story | Unsigned User (intending to be teacher) Accepted by Anodiam Admin | Create the password putting my details in the given fields | I can create my password and save it for the future use by clicking on the save button. | Given I am an unsigned user accepted by Anodiam Admin to become a teacher When I create the password putting my details in the given fields Then I should be able to create my password and save it for the future use by clicking on the save button.
10 | Feature | Story | As a logged in teacher user | login into anodiam.com | So that I can view and upload my list of course videos and question papers, see a logout link in my Anodiam user account | Given I am a logged in teacher user When I log into Anodiam Then I shall be able to see my Anodiam user account page containing my list of uploaded courses,question papers and see a logout link |  | 13 | 5 | 0.38462 | Initial
11 | Feature | Story | As a logged in teacher user | View my Anodiam user account page | So that I can view answer sheets submitted by each student | Given I am a logged in teacher user When I log into Anodiam Then I shall be able to see answer sheet submitted by each student. |  | 13 | 5 | 0.38462 | Initial
0
12 | [6 empty] | Old Password,New Pass word,Confirm Password,Submit button and Cancel button |  |  | 0
13 | Feature | Story | Student | see comment if put wrong password | I can change password | given I put wrong password , when the password I give doesn’t match with my saved password then I'll receive a comment saying my password is wrong and then I can click on forget password button to change password | Emaild Id,Submit button and Cancel Button. |  | 4 | 0 | Initial
14 | Feature | Story | Student | access forget password | able to access password if forgotton/change password | given I want to change my password or I forget the password , when I click on forget password button then I'll be able to validate my account by giving the email id I provided in the website during account creation so that the password change link can be sent in my email and I can change the password by clicking in the link and get in to the website | After hitting Submit button , system will generate unique Student Code which will be mailed student and gurdian. |  |  | 0
15 | Feature | Story | Student | get a unique identification number | only me or my designated gurdian or one of the parent's can access my profile | given I want to study thorugh the website when I create my profile with validated criteria then an unique student number will be generated | 1) Drop Down Box for Standard 2)Drop Down Box for Board or University 3)Other if nothing matches in drop down for board/University, he/she can write 4) Multiple select for subjects |  | 5 | 0 | Initial
16 | Feature | Story | Student | have my own profile | I can put my personal details | given I want to make my profile , when I give my details in the form like Name, DOB, Standard, Board, Subjects then I am creating my basic profile |  |  | 1 | 0 | Initial
17 | Feature | Story | Student | have my own profile | I can put some further details | given I put further details in my profile for assistance , when I select which subject I'm best in and I'm weak in from the drop down menu then I'll be able to get assistance for the best courses designed for me | 1) Check Box for accessibility |  |  | 0
18 | Feature | Story | Student | set the access of my profile | the private things in my profile are not visible by others | given I'm in my rpofile and I'm adult, when I'll set the access as private then no one can see my profile |  |  |  | 0
19 | Feature | Story | Student | set the access of my profile | I can set access public | given I'm in my profile and I'm minor when I'll set the access to parents/gurdian then one of the parents (who is liked with the profile) or gurdian (who is linked with the profile) can see my profile |  |  |  | 0
20 |  |  |  | purchase a course | [5 empty] | 0
21 |  |  |  | purchase videos | [5 empty] | 0
22 |  |  |  | Examination Details |  |  | Entry of Student Details in Edit Mode |  | 3 | 0 | Initial
23 | Feature | Story | Student | have my own profile | I can see my courses which I've entered data | given I'm inside my profile when I buy courses then I can see them inside my profile |  |  | 4 | 0 | Initial
24 | Feature | Story | Student | have my own profile | I can see the videos I bought or got free | given I'm inside my profile when I buy videos then I can see them inside my profile | Edit screen of Examination Details and result data given by Teacher |  | 5 | 0 | Initial
25 | Feature | Story | Student | have my own profile | I can see my test papers of all subjects which ive appeared for and results of all of them | given I'm inside my profile when I give tests on one or many subjects or many tests in on esubjects then the results should be there with the test papers in my profile |  |  | 1 | 0 | Initial
26 | Feature | Story | Student | have my own profile | I can see the remarks given by the teacher on test papers | given I'm inside my profile when I will see my checked test papers then I can see the special notes from teachers | 2 Note Fields. 1) One for Student and 2)One for Teacher |  | 2 | 0 | Initial
27 | Feature | Story | Student | have my own profile | I can make notes for future reference | given I'm inside my profile when I will make notes about which area to improve based on teacher's remarks so that I can refer it when I appear for the test next time then I'll be able to make the notes with the subject as a tag or comment |  |  | 3 | 0 | Initial
28 | Feature | Story | Student | have my own profile | I can make notes for teachers to check | given im inside a subject in my profile when I want to keep note for the teacher about any clarification then I can see that |  |  | 4 | 0 | Initial
29 | Feature | Story | Student | have my own profile | I can make notes with date and time mentioned | given I'm inside my profile when I'm making notes for the teacher's reference then a date and time should be metioned for further reference |  |  | 5 | 0 | Initial
30 | Feature | Story | Student | have my own profile | I can see the notes from teachers with date and time reference | given I'm inside my profile , when I'll check the response of my notes then I'll be able to see answers from the teacher's with date and time reference |  |  |  | 0
31 | Feature | Story | Student | edit my profile | I can change details when needed | given I'm editing my profile, when I change/add or alter details in m profile then I'll be able to edit them by clicking on edit profile button |  |  | 1 | 0 | Initial
32 | Feature | Story | Student | see my rating given by the teachers | I can be motivated | given I'm inside my profile when I'm given rating by teachers then I'll be able to see it |  |  | 2 | 0 | Initial
33 | Feature | Story | Student | get rewarded from Anodiam | I can be motivated | rewaards can be given by Anodiam as a free course or badge which can be shared in social media |  |  |  | 0
34 | Feature | Story | Student | not download the videos | I can always see the videos online | given I'm watching the video when I want to save or download the video then it should not be downloaded or saved in the local mechine |  |  |  | 0
35 | Feature | Story | Student | not take the screenshot | I can not keep any document saved | given I'm taking screen shot when I'll try to capture then it should not allow to take the screen shot. |  |  |  | 0
36 | Feature | Story | Student | not copy and paste from the document | I can not keep any document saved | given I'm copying the text when I'll copy and paste the text then it wont allow to do so |  |  |  | 0
37 |  |  | Student | Sign Out | [5 empty] | 0
38 | Feature | Story | Teacher | signup | I can register | given I'm signing up for the website when I sign up with fulfilling valid criteria like name, date of birth, email id and click in the sign up button then I will be able to sign up in to the website. |  |  |  | 0
39 | Feature | Story | Teacher | login | I can go to my profile | given I,m logged in to the website , when I fill in the user name and password field with my valid cridentials and click in the sign in button then I get signed into the website. |  |  |  | 0
40 | Feature | Story | Teacher | create password | I can get into my profile | given I'm creating my password when I'm putting password followed by the instructions like one capital letter, one character, one numner and minimum eight character then the password is created |  |  |  | 0
41 | Feature | Story | Teacher | confirm password | I can get into my profile | given I've created password when I'll confirm the password in confirm password firld then I'll be able to access my profile |  |  |  | 0
42 | Feature | Story | Teacher | have a secure password | my profile is secure | given I'm putting the password in the password field, when I give my valid password and click in the password button then I'll be able to go to my profile after validation . |  |  |  | 0
43 | Feature | Story | Teacher | access Forget Password | able to access password if forgotton/change password | given I want to change my password or I forget the password , when I click on forget password button then I'll be able to validate my account by giving the email id I provided in the website during account creation so that the password change link can be sent in my email and I can change the password by clicking in the link and get in to the website |  |  |  | 0
44 | Feature | Story | Teacher | have my own profile | I can put my personal details | given I want to make my profile , when I give my details in the form like Name, DOB, profession, experience, Subjects that I teach then I am creating my basic profile |  |  |  | 0
45 | Feature | Story | Teacher | have edit profile option | I can change/add or alter my personal details if needed | given I'm editing my profile, when I change/add or alter details in my profile regarding my personal data like experience, qualification, then I'll be able to edit them by clicking on edit profile button |  |  |  | 0
46 | Feature | Story | Teacher | have direction to upload course/videos | I can make the videos available for students | given I upload videos/course meterials, when I'll follow the instructions how to upload a video/course meterial then I'll be able to upload the course/videos |  |  |  | 0
47 | Feature | Story | Teacher | get options where to place my videos/course meterials | my videos/course meterials can be viewed by the students | given I want to place my video in the website, when I'll choose the proper option like free videos/paid videos then students can see the videos in the proper place |  |  |  | 0
48 | Feature | Story | Teacher | upload videos | videos are visible to the audience | given I'm in my profile when I will upload videos after fulfilling criteries likefree or paid and subject check, board check, class check, standard (easy or hard) check then I can upload videos |  |  |  | 0
49 | Feature | Story | Teacher | edit videos before publish | I can publish only error free videos | given I'm uploading my video when I'll check it before clicking publish button then my error checking is done |  |  |  | 0
50 | Feature | Story | Teacher | see the remarks by students | I can answer their remarks | given I'm in my profile when students will ask any question through remarks then I can view them and able to answer |  |  |  | 0
51 | Feature | Story | Student | see the remarks date and time | I can answer accordingly | given I'm viewing the remarks by the students when I click on the remarks then I can see the date and time |  |  |  | 0
52 | Feature | Story | Student | see a notification in my mail | I can understand there is a remark in my profile | given I get a remarks notification when I get a remarks from the student with their UIN about asking any question then I get a system generated notification in my email about the remark so that I can keep a track of remarks from individual sudents. |  |  |  | 0
53 | Feature | Story | Teacher | see remarks by parents | I can answer accordingly | given I get a remark by a parent referring the student's UIN when I get a remark from a parent with their student's UIN then I'll receive a system generated notification in my email |  |  |  | 0
54 | Feature | Story | Teacher | check answers of the test papers | I can do the correction and give marks | given I'm checking a test paper when I'll check test papers for a subject of a class on a standard then I'll be able to correct wrong answers or give marks for right answers |  |  |  | 0
55 | Feature | Story | Teacher | rate students | students get motivation | given I'm rating a student when I student can satisfy certain criteria like course complication within time frame/ getting "A" grade marks in a subject / completing test after finishing course within a time frame then the student will be rated stars |  |  |  | 0
56 | Feature | Story | Teacher | not edit or delete any video or course meterial | editing option is not with me | given I want to delete an uploaded video or course meterial when I try to do this then I should get access denied option |  |  |  | 0
User preference and predicting the most suitable courses for individual user in their home screen
Note on G1: Help: Acceptance Criteria in Product Backlog comprises of 4 fields, namely: Scenerio, Given, When Then. Here all 4 fields should be colated into one. E.g. Acceptance criteria for following should be as below: User Story: As a logged out User I want to be able to sign into the website, so that I can see my profile. Acceptance Criteria: Scenario: Registered User Signs with valid username and password. Given: I am logged out of website. When: I fill in the username and password fields with my valid credentials and click in sign in button Then: I get signed into the website. Here, Acceptance Criteria could be written in 1 sentence as below: Given I am logged out of website, if I fill in the username and password fields with my valid credentials and click in sign in button, I should get signed into the website.
Note on I1: Help: XS : 1 Story Point : 0 to 2 person hours S : 2 Story Points : 2 to 4 person hours M : 3 Story Points : 4 to 8 person hours L : 5 Story Points : 1 to 1.5 person days XL : 8 Story Points : 1.5 to 2.5 person days XXL : 13 Story Points : 0.5 to 1 person weeks XXXL : 21 Story Points : Larger and never used

## ProductBacklog
Item # | Item Type | Item Size | As a… | I want to be able to… | So that… | Acceptance Criteria (inserta note) | Notes / References | Task Estimates (Story Points) | Business Value | Priority | Status | Sprint Number
1 | Feature | Story | Unsigned User (intending to be teacher) | visit the Signup / Login page at the link anodiam.com/teacher | I can view link to sign up (for teacher registration) and a form to login (for registered teachers) and a link to Forget/Change password | Given I am an unsigned user (intending to be teacher) When I type anodiam.com/teacher on a web browser Then I should be able to see the page: containing a form to log in (for registered teachers) and also a link to Sign up here as a teacher and another link to Forget/Change password to the teacher application. | ..\ProjectExecution\BA\SpecsWireframes\003TeacherAppWireframes.pptx |  | 5 |  | Initial
2 | Feature | Story | Unsigned User (intending to be teacher) | Click on the sign up here link on the Signup / Login page | I can access the teacher sign up form | Given I am an unsigned user (intending to be teacher) When I click the sign up here link on the Signup / Login page Then I should be able to see the Teacher Signup form. | ..\ProjectExecution\BA\SpecsWireframes\004TeacherAppFunctionalSpecs.xlsx |  | 5 | 0 | Initial
3 | Feature | Story | Unsigned User (intending to be teacher) | Check availability of my entered user name in the Teacher Id field in the Teacher Signup form | I can check whether the Teacher Id is available or not | Given I am an unsigned user (intending to be teacher) When I entere user name in the Teacher Id field in the Teacher Signup form Then I should be able to check whether the Teacher Id is available or not.
4 | Feature | Story | Unsigned User (intending to be teacher) | Click on the Submit button in the Teacher Signup form after filling up the relevent fields | Anodiam admin app will be notified to accept or reject my teacher's expression of interest to join Anodiam. | Given I am an unsigned user (intending to be teacher) When I key in all the mandatory and other details in the Teachers Signup form click on the Submit button Then Anodiam admin app will be notified to accept or reject my teacher's expression of interest to join Anodiam. |  |  | 2 |  | Initial
5 | Feature | Story | Unsigned User (intending to be teacher) | Click on the Submit button in the Teacher Signup form after filling up the relevent fields | I should be able to see a message on the same Teachers Signup form saying that Anodiam admin will contact me. | Given I am an unsigned user (intending to be teacher) When I key in all the mandatory and other details in the Teachers Signup form click on the Submit button Then I should be able to see a message on the same Teachers Signup form saying that Anodiam admin will contact me.
6 | Feature | Story | Unsigned User (intending to be teacher) | Click on the Submit button in the Teacher Signup form after filling up the relevent fields | I should receive an email from Anodiam Admin stating that they have been notified and they will contact me soon. | Given I am an unsigned user (intending to be teacher) When I key in all the mandatory and other details in the Teachers Signup form click on the Submit button Then I should be able to receive an email from Anodiam Admin stating that they have been notified and they will contact me soon.
7 | Feature | Story | This is an external dependency on the Anodiam Admin app. No action is required from any users of the Teacher's App. |  |  | Offline to the Anodiam Teacher app, Anodiam Admin app users will be able to accept or reject the above (intending to be) teacher's expression of interest to join Anodiam |  |  | 2 |  | Initial
8 | Feature | Story | Unsigned User (intending to be teacher) Rejected by Anodiam Admin | Receive a regret email from Anodiam Admin about the status (rejection) of my above teacher's expression of interest to join Anodiam. | I can know the reason for rejection and the date before which I should not try to reapply. | Given I am an unsigned user rejected by Anodiam Admin to become a teacher When I receive a regret email from Anodiam Admin Then I should be able to know the reason for my rejection and the date before which I should not try to reapply. |  |  | 2 |  | Initial
9 | Feature | Story | Unsigned User (intending to be teacher) Accepted by Anodiam Admin | Receive a congratulations email from Anodiam Admin about the status (acceptance) of my above teacher's expression of interest. The email should have a link to create password for my chosen user id. | I can create password for my chosen user id. | Given I am an unsigned user accepted by Anodiam Admin to become a teacher When I receive a Acceptance email from Anodiam Admin Then I should be able to see a link to create password for my user id. |  |  | 2
10 | Feature | Story | Unsigned User (intending to be teacher) Accepted by Anodiam Admin | Click on the link to visit the page to create password for my user id. | I can visit the Create Password page to create my password. | Given I am an unsigned user accepted by Anodiam Admin to become a teacher When I click on the link to visit the page to create password for my user id Then I should be able to visit the Create Password page. |  |  | 2
11 | Feature | Story | Unsigned User (intending to be teacher) Accepted by Anodiam Admin | Click on the Forget Password/Change Password link on the Sign up / Login Page | I can visit the Forgot Password/Change Password page. | Given I am an unsigned user accepted by Anodiam Admin to become a teacher When I click on the link to Forgot Password/Change Password Then I should be able to visit the Forgot Password/Change Password page. |  |  | 2
12 | Feature | Story | Unsigned User (intending to be teacher) Accepted by Anodiam Admin | Provide my valid identification details including my registered email Id and click on the Submit button. | I can receive an email from Anodiam admin in my registered Email Id with a temporary Password Reset link. | Given I am an unsigned user accepted by Anodiam Admin to become a teacher When I Provide my valid identification details including my registered email Id and click on the submit button Then I should be able to receive an email from Anodiam admin in my registered Email Id with a temporary Password Reset link. |  |  | 2
13 | Feature | Story | Unsigned User (intending to be teacher) Accepted by Anodiam Admin | Click on the Password Reset Link in my Valid Email | I can go to the Create Password page. | Given I am an unsigned user accepted by Anodiam Admin to become a teacher When I click on the Reset Password Link in my valid Email Then I should be able to go to the Create Password Page in Teacher app. |  |  | 2
14 | Feature | Story | Unsigned User (intending to be teacher) Accepted by Anodiam Admin | Enter a new Valid Password and Confirm the new Password in the Create Password page and click Submit Button. | I can get the link on the same page saying Click here to Login. | Given I am an unsigned user accepted by Anodiam Admin to become a teacher When I enter a new Valid Password and Confirm the new Password in the Create Password page and click Submit Button Then I should be able toI can get the link on the same page saying Click here to Login.
15 | Feature | Story | Unsigned User (intending to be teacher) Accepted by Anodiam Admin | Click on the Click here to Login link in the Create Password page. | I can visit the Teacher Signup/Login page | Given I am an unsigned user accepted by Anodiam Admin to become a teacher When I Click on the Click here to Login link in the Create Password page. Then I should be able to visit the Teacher Signup/Login page
16 | Feature | Story | Unsigned User (intending to be teacher) Accepted by Anodiam Admin | Provide my Teacher Id and valid Password in Teacher Signup/Login page and click on Login Button | I can Login as a Teacher User In the Anodiam Teacher App | Given I am an unsigned user accepted by Anodiam Admin to become a teacher When I provide my Teacher Id and valid Password in Teacher Signup/Login page and click on Login Button Then I should be able to Login as a Teacher User In the Anodiam Teacher App.
17 | Feature | Story | Unsigned User (intending to be teacher) Accepted by Anodiam Admin | Provide my Teacher Id and valid Password in Teacher Signup/Login page and click on Login Button | I can go to the My Home Page in Teacher app | Given I am an unsigned user accepted by Anodiam Admin to become a teacher When I Provide my Teacher Id and valid Password in Teacher Signup/Login page and click on Login Button Then I should be able to Go to the My Teache Home page in Teacher app.
18 | Feature | Story | Unsigned Valid Teacher user who has forgotton password or wants to change password of Anodiam teacher app | Click on the Forgot Password / Change Password link in Signup / Login page | I can go to the Forget / Change Password page. | Given I have forgotton my password or want to change my password for Anodiam Teacher app When I click on the Forgot Password / Change Password link in Signup / Login page Then I shall be able to go to the Forget / Change Password page.
19 | Feature | Story | Unsigned Valid Teacher user who has forgotton password or wants to change password of Anodiam teacher app | Provide valid credentials and details along with the registered Email Id in the Forget Password / Change Password form in the Forget / Change password page and click on the submit button | I can receive an email from Anodiam admin in my registered Email Id with a temporary Password Reset link. | Given I have forgotton my password or want to change my password for Anodiam Teacher app When I provide valid credentials and details along with the registered Email Id in the Forget Password / Change Password form in the Forget / Change password page and click on the submit button Then I shall be able to receive an email from Anodiam admin in my registered Email Id with a temporary Password Reset link. |  |  | 5 | 0
20 | Feature | Story | Unsigned Valid Teacher user who has forgotton password or wants to change password of Anodiam teacher app | Click on the Password Reset link in my registered Email Id. | I can visit the create Password page. | Given I have forgotton my password or want to change my password for Anodiam Teacher app When click on the Password Reset link in my registered Email Id. Then I shall be able to visit the create Password page. |  |  | 5 | 0
21 | Feature | Story | Unsigned Valid Teacher user who has forgotton password or wants to change password of Anodiam teacher app | Fillup the create Password and conform password fileds with a new valid password and click on submit | The new Password is saved | Given I have forgotton my password for Anodiam Teacher app When fillup the create Password and conform password fileds with a new valid password and click on submit Then the new Password shoild be saved. |  |  | 5 | 0
22 | Feature | Story | Unsigned Valid Teacher user who has forgotton password or wants to change password of Anodiam teacher app | Fillup the create Password and conform password fileds with a new valid password and click on submit | Click here to login link is displayed on top of the same page | Given I have forgotton my password or want to change my password for Anodiam Teacher app When fillup the create Password and conform password fileds with a new valid password and click on submit Then click here to login link is displayed on top of the same page |  |  | 5 | 0
23 | Feature | Story | Unsigned Valid Teacher user who has forgotton password or wants to change password of Anodiam teacher app | Click on the Click here to Login link in the Create Password page. | I can go to the Sign up / Login page in the Teacher App | Given I have forgotton my password for Anodiam Teacher app When click on the Click here to Login link in the Create Password page. Then I shall be able to go to the Sign up / Login page in the Teacher App |  |  | 5 | 0
24 | Feature | Story | As a logged in teacher user | View my Anodiam Teacher Home / View all courses page | I can view my welcome message on top (details in Finctional Spec) | Given I am a logged in teacher user When I log into Anodiam Teache App and view my Teacher Home page Then I shall be able to see my Anodiam teacher app's Teacher Home page with my welcome message on top (details in Finctional Spec) |  |  | 5
27 | Feature | Story | As a logged in teacher user | Click on the Create a new Course button in my Teacher Home / View all courses page | Create course page outline tab page is displayed with Course Outline tab enabled with a form to be filled up | Given I am a logged in teacher user When I Click on the Create a new Course button in my Teacher Home / View all courses page Then I shall be able to view the Create course page outline tab page with Course Outline tab enabled with a form to be filled up. |  |  | 5
28 | Feature | Story | As a logged in teacher user | Fillup the Course Outline form with the valid informations | I can click on the save button to save the details I enteted in the course outline form | Given I am a logged in teacher user When I Fillup the Course Outline form with the valid informations Then I shall be able to click on the save button to save the details I enteted in the course outline form
29 | Feature | Story | As a logged in teacher user | Click on the cancel button | The recent activity doesn’t get saved and it restore the previous saved informtions | Given I am a logged in teacher user When I Click on the cancel button Then the recent activity doesn’t get saved and it restore the previous saved informtions
30 | Feature | Story | As a logged in teacher user | Click on the delete button | Delition confirmation dialogue box will appear | Given I am a logged in teacher user When I Click on the delete button Then delition confirmtion dialogue box will appear
| Feature | Story | As a logged in teacher user
Note on G1: Help: Acceptance Criteria in Product Backlog comprises of 4 fields, namely: Scenerio, Given, When Then. Here all 4 fields should be colated into one. E.g. Acceptance criteria for following should be as below: User Story: As a logged out User I want to be able to sign into the website, so that I can see my profile. Acceptance Criteria: Scenario: Registered User Signs with valid username and password. Given: I am logged out of website. When: I fill in the username and password fields with my valid credentials and click in sign in button Then: I get signed into the website. Here, Acceptance Criteria could be written in 1 sentence as below: Given I am logged out of website, if I fill in the username and password fields with my valid credentials and click in sign in button, I should get signed into the website.
Note on I1: Help: XS : 1 Story Point : 0 to 2 person hours S : 2 Story Points : 2 to 4 person hours M : 3 Story Points : 4 to 8 person hours L : 5 Story Points : 1 to 1.5 person days XL : 8 Story Points : 1.5 to 2.5 person days XXL : 13 Story Points : 0.5 to 1 person weeks XXXL : 21 Story Points : Larger and never used

## ToDoList
Sl# | Line Item | Priority | Status
| Multiple TEACHER_ROLE added: Bug to be resoled | 5 | Done
| Differentiate between Transaction and Master Tables | 5 | Done
| Only Admin / Super Admin User to access admin portal | 5 | Done
| Only Teacher User to access teacher portal | 5 | Done
| Cover letter and other okay files should be left saved if one attached file is bigger than permissible limits. | 5 | Closed
2 | Redirect user to MyProfile page after Application Submission Confirmation | 5 | Done
3 | Reverbose email to anodiam Admin, teacher after Teacher Application Submission | 5 | WIP
4 | Update notifications section of Admin App after Teacher Application Submission | 5
5 | Progress Meter of file upload during teacher application | 5
6 | Application in progress teacher. What they see in My Account Page | 5 | Done
7 | Manage Static info document editing from admin portal. Same docs will be stored in database and will be displayed readonly on teacher app. | 4
8 | View Teacher's job Applications from Admin App( read only) | 3
9 | Approve, send email, Archive Job Application data CV etc in one location. | 3
10 | Approved teacher can log in, link sent in email. What they see in My Account Page | 3
11 | Instructions to apply link at MyApplication page top. | 3
12 | Rejected teacher cannot log in, their application archived in database. | 3
13 | Update the static documents for the app and publish them. | 3
14 | Publish the 3 videos in the teacher app. | 2
15 | Logging of errors and events | 1
16 | Admin App, create new users. | 1
17 | K8s | 0
18 | Dockerization of Apps | 0
19 | Dockerization of DB | 0
20 | Email account for Admin | 0
21 | GKE | 0
22 | Auto scaling | 0
23 | Jenkins Create Test and Dev and Prod environments | 0
24 | Automation Pipeline | 0
25 | promethious | 0
26 | graphana | 0
27 | Backup recovery of app / Logs in Ansible | 0
28 | Backup recovery of database through Ansible. | 0
29 | Hiding passwords in Ansible lockers / Secrets | 0
30 | Junit | 0
31 | Automation Testing | 0
32 | Load Testing (of Scaling) | 0
33 | Database Creation through hibernate: Only admin portal will have : spring.jpa.hibernate.ddl-auto=update, Other Apps: None | 0

## MajorModules
Sl# | Sub Sl # | Topic | Sub Topic
A |  | Teacher Job Application
| 1 |  | Teacher App Apply for Job
| 2 |  | Admin App to Accept / Reject each Application
B |  | DevOps
| 3 |  | Junit
| 4 |  | Logging
| 5 |  | CI/CD Jenkins
| 6 |  | Docker
| 7 |  | Kubernetes
| 8 |  | Anodiam corporate email service
| 9 |  | Ingress and Domain Name
| 10 |  | Https
| 11 |  | Cyber Security
| 12 |  | Secrets
| 13 |  | Geaphana Dash Board
| 14 |  | Pronethious Monitoring
| 15 |  | Ansible Backup & Recovery of (DB and App)
| 16 |  | Automation Testing
| 17 |  | Load Test
| 18 |  | Pen Test
C |  | Course Buy & Sale
| 19 |  | Teacher Upload Video Material
| 20 |  | Teacher Upload Non Video Material (Text only)
| 21 |  | Admin App to Accept / Reject each Material
| 22 |  | Student Web Services
| 23 |  | Student Mobile App
| 24 |  | Students can Register to Student App
| 25 |  | Student can Buy Courses (BANK Transaction) module integration
| 26 |  | Student can Buy Courses (PAY APP) module integration
| 27 |  | Students can Consume Course
| 28 |  | Students stopped to download or do data leakage of course
D |  | Query Resolution
| 29 |  | Student Post Queries (Blogging)
| 30 |  | Teacher Post Resolutions
E |  | Supporting Partners Modules
| 31 |  | Videographer
| 32 |  | Film Director
| 33 |  | Grahic Artists
| 34 |  | Managers
| 35 |  | HR
| 36 |  | Office Admin
| 37 |  | Legal
| 38 |  | Accounting and Finance
F |  | Quality Control Modules
| 39 |  | Academic Reviewers
| 40 |  | Film Revierers
G |  | Finance and Accounts
| 41 |  | Partner Payout Module (BANKING Transactions)
| 42 |  | Cost Center Management Module
H |  | Practice Tests
| 43 |  | Automatic MCQ Test Modules
| 44 |  | Sample Long Questions Module
I |  | AI, Analytics & Reports
| 45 |  | Course Unit-Cost optimization
| 46 |  | Teacher Reporting abour their courses
| 47 |  | Corporate Reporting of course performances
| 48 |  | Patents, students reporting of student's performances