## Sheet1
2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-15 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22 | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 |  | Daily Scrum Call 8:00am-8:15am IST 12:30pm-12:45pm AEST
Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
|  | May Backlog Grooming 8:00am-1:00pm IST 12:30pm-5:30pm AEST |  |  |  |  | May Backlog Grooming 8:00am-1:00pm IST 12:30pm-5:30pm AEST |  |  |  |  | May Sprint Planning 8:00am-1:00pm IST 12:30pm-5:30pm AEST
2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-05-06 | 2022-05-09 | 2022-05-10 | 2022-05-11 | 2022-05-12 | 2022-05-13 | 2022-05-16 | 2022-05-17 | 2022-05-18 | 2022-05-19 | 2022-05-20 | 2022-05-23 | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-27 | 2022-05-30 | 2022-05-31 | 2022-06-01 | 2022-06-02 | 2022-06-03
Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
[7 empty] | June Backlog Grooming 8:00am-1:00pm IST 12:30pm-5:30pm AEST |  |  |  |  | June Backlog Grooming 8:00am-1:00pm IST 12:30pm-5:30pm AEST |  |  |  |  | June Sprint Planning 8:00am-1:00pm IST 12:30pm-5:30pm AEST |  |  |  |  | May Sprint Review 8:00am-1:00pm IST 12:30pm-5:30pm AEST | May Metrics Generation | May Sprint Retrospective 8:00am-1:00pm IST 12:30pm-5:30pm AEST
2022-06-06 | 2022-06-07 | 2022-06-08 | 2022-06-09 | 2022-06-10 | 2022-06-13 | 2022-06-14 | 2022-06-15 | 2022-06-16 | 2022-06-17 | 2022-06-20 | 2022-06-21 | 2022-06-22 | 2022-06-23 | 2022-06-24 | 2022-06-27 | 2022-06-28 | 2022-06-29 | 2022-06-30 | 2022-07-01
Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
|  | July Backlog Grooming 8:00am-1:00pm IST 12:30pm-5:30pm AEST |  |  |  |  | July Backlog Grooming 8:00am-1:00pm IST 12:30pm-5:30pm AEST |  |  |  |  | July Sprint Planning 8:00am-1:00pm IST 12:30pm-5:30pm AEST |  |  |  |  | June Sprint Review 8:00am-1:00pm IST 12:30pm-5:30pm AEST | June Metrics Generation | June Sprint Retrospective 8:00am-1:00pm IST 12:30pm-5:30pm AEST
2022-07-04 | 2022-07-05 | 2022-07-06 | 2022-07-07 | 2022-07-08 | 2022-07-11 | 2022-07-12 | 2022-07-13 | 2022-07-14 | 2022-07-15 | 2022-07-18 | 2022-07-19 | 2022-07-20 | 2022-07-21 | 2022-07-22 | 2022-07-25 | 2022-07-26 | 2022-07-27 | 2022-07-28 | 2022-07-29
Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
|  | August Backlog Grooming 8:00am-1:00pm IST 12:30pm-5:30pm AEST |  |  |  |  | August Backlog Grooming 8:00am-1:00pm IST 12:30pm-5:30pm AEST |  |  |  |  | August Sprint Planning 8:00am-1:00pm IST 12:30pm-5:30pm AEST |  |  |  |  | July Sprint Review 8:00am-1:00pm IST 12:30pm-5:30pm AEST | July Metrics Generation | July Sprint Retrospective 8:00am-1:00pm IST 12:30pm-5:30pm AEST
2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 | 2022-08-08 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12 | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 | 2022-08-22 | 2022-08-23 | 2022-08-24 | 2022-08-25 | 2022-08-26 | 2022-08-29 | 2022-08-30 | 2022-08-31 | 2022-09-01 | 2022-09-02
Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
[7 empty] | September Backlog Grooming 8:00am-1:00pm IST 12:30pm-5:30pm AEST |  |  |  |  | September Backlog Grooming 8:00am-1:00pm IST 12:30pm-5:30pm AEST |  |  |  |  | September Sprint Planning 8:00am-1:00pm IST 12:30pm-5:30pm AEST |  |  |  |  | August Sprint Review 8:00am-1:00pm IST 12:30pm-5:30pm AEST | August Metrics Generation | August Sprint Retrospective 8:00am-1:00pm IST 12:30pm-5:30pm AEST