## Cover Sheet
Anodiam
Sprint Backlog
Sprint002-2020071320200724
Version | Editor | Reviewer | Date | Note
1.0 | AC | AM | 2020-07-07 | Initial version

## SprintBacklog
Task # (Item# + Task#) | Item Description | Task Description | Estimates (Story Points) | Status | Impediments
1001 | Home Page | CSS Creation and Bootstrap Selection | 8 | Scheduled
1002 |  | HTML Page Creation | 5 | Scheduled
1003 |  | Responsive HTML page creation | 3 | Scheduled
1004 |  | Selecting Images for Carousel | 2 | Scheduled
1005 |  | Slecting the Blackboard Image | 1 | Scheduled
1006 |  | Selecting the headings and messages (including font and color) of the corousel images | 1 | Scheduled
2001 | Sign Up Page | Front End Design with Validation | 3 | Scheduled
2002 |  | Database and Fields Design | 1 | Scheduled
2003 |  | Java Code | 3 | Scheduled
2004 |  | Code Review | 3 | Scheduled
2005 |  | Testing | 3 | Scheduled
2006 |  | Encryption - Decryption Logic | 3 | Scheduled
2007 |  | Https Security Tokens | 8 | Scheduled
Note on D1: Help: XS : 1 Story Point : 0 to 2 person hours S : 2 Story Points : 2 to 4 person hours M : 3 Story Points : 4 to 8 person hours L : 5 Story Points : 1 to 1.5 person days XL : 8 Story Points : 1.5 to 2.5 person days XXL : 13 Story Points : 0.5 to 1 person weeks XXXL : 21 Story Points : Larger and never used