## Cover Sheet
Anodiam
Product Backlog
Rolling Versions
Version | Editor | Reviewer | Date | Note
0.1 | AC |  | 2020-06-20 | Initial version
1.0 | AC | AM | 2020-07-03 | Backlog Refining done For Sprint 2.0

## ProductBacklog
Item # | Item Type | Item Size | As a… | I want to be able to… | So that… | Acceptance Criteria (inserta note) | Notes / References | Task Estimates (Story Points) | Business Value | Priority | Status | Sprint Number
1 | Feature | Story | Unsigned User (intending to be student) | visit the home page of anodiam.com | I can view image links to few best rated courses and a link to Sign up and another link to log in. | Given I am an unsigned user When I type anodiam.com on a web browser Then I should be able to see the Anodiam home page: containing image links to few best rated courses and a valid link to Sign up to anodiam.com and another link to log in. | ..\ProjectExecution\BA\SpecsWireframes\new001Wireframes.pptx | 13 | 5 | 0.38462 | Scheduled | 2
1.1 | Enabler | Story | Home Page Responsive HTML, Image and fonts selection |  |  |  | ..\ProjectExecution\BA\Functional requirements | 8 | 4 | 0.5 | Scheduled | 2
2 | Feature | Story | Unsigned User (intending to be student) | Enter my personal details to Sign up to anodiam.com | I can register myself to create my User Id and Password in Anodiam. | Given I am an unsigned user When I visit sign up link on Anodiam home page and enter my valid personal details Then I must be registered into Anodiam with my userid & passwrd |  | 13 | 5 | 0.38462 | Scheduled | 2
2.1 | Enabler | Story | Security of Sign Up page |  |  |  |  | 13 | 5 | 0.38462 | Scheduled | 2
3 | Feature | Story | signed up but unloggedin User (student) | Enter my registered userid and password to Log in to Anodiam. | I can view the user account page | Given I'm an unloggedin but signed up user When I enter my valid login details in the login page Then I must be able to login to anodiam and view my Anodiam user account page |  | 8 | 5 | 0.625 | Initial
3.1 | Enabler | Story | After user enters login and password, the credential gets validated from backend, then JWT token gets generated in the backend. The token is sent back to client. |  |  | Given a successful login happens into Anodiam through Postman Tool When I enter my valid login details in the Postman Tool Then I should be able to view the valid token in Postman Tool |  | 8 | 5 | 0.625
4 | Feature | Story | As a logged in Student user | View my Anodiam user account page | So that I can view my list of enrolled courses, Search for new courses and see a logout link in my Anodiam user account | Given I am a logged in Student user When I log into Anodiam Then I shall be able to see my Anodiam user account page containing my list of enrolled courses, Search for new courses and see a logout link |  | 5 | 5 | 1 | Initial
5 | Feature | Story | As a logged in Student user | View Course Details (a list of all videos) inside each enrolled course in my Anodiam user account | I can play the video lessons inside that particular course | Given I am a logged in Student user When I view any course inside my Anodiam user account Then I should be able to see a list of all video lessons inside that particular course. |  | 5 | 5 | 1 | Initial
6 | Feature | Story | As a logged in Student user | Play each video from the list of videos displayed in each enrolled course under my Anodiam user account | I can watch each of the video lessons | Given I am a logged in Student user When I click on each of the videos from the list of videos displayed in each enrolled course under my Anodiam user account Then the particular video must play completely and I should be able to watch the video lesson. |  | 5 | 5 | 1 | Initial
7 | Enabler | Story | Into a single stand alone (Dev) Kubernetes cluster in GCP, deploy seed APP (containing basic features in Items 1 through 6, namely, Home page, Sign up, Login, User Account, Course Details and Play Video). |  |  | Given a Student User (intended, signed up or logged in) When I test all acceptance criterias for items 1 through 6 Then each should pass for the app deployed in GCP K8s. |  | 8 | 5 | 0.625 | Initial
8 | Enabler | Story | Create a CI / CD pipeline containing Dev, Test, Staging and Prod environments (K8s clusters on GCP) and deploy the seed APP. |  |  | Given a Student User(intended, signed up or logged in) When I test all acceptance criterias for items 1 through 6 Then each one should pass for the app deployed in all the 4 environments in GCP K8s (Dev, Test, Staging and Prod). |  | 13 | 5 | 0.38462 | Initial
9 | Feature | Story | Unsigned User (intending to be teacher) | visit the home page of anodiam.com | I can view image links to few best rated courses and a link to Sign up and another link to log in. | Given I am an unsigned user When I type anodiam.com on a web browser Then I should be able to see the Anodiam home page: containing image links to few best rated courses and a valid link to Sign up to anodiam.com and another link to log in. |  | 13 | 5 | 0.38462 | Initial
10 | Feature | Story | As a logged in teacher user | View my Anodiam user account page | So that I can view and upload my list of course videos and question papers, see a logout link in my Anodiam user account | Given I am a logged in teacher user When I log into Anodiam Then I shall be able to see my Anodiam user account page containing my list of uploaded courses,question papers and see a logout link |  | 13 | 5 | 0.38462 | Initial
11 | Feature | Story | As a logged in teacher user | View my Anodiam user account page | So that I can view answer sheets submitted by each student | Given I am a logged in teacher user When I log into Anodiam Then I shall be able to see answer sheet submitted by each student. |  | 13 | 5 | 0.38462 | Initial
0
12 | [6 empty] | Old Password,New Pass word,Confirm Password,Submit button and Cancel button |  |  | 0
13 | Feature | Story | Student | see comment if put wrong password | I can change password | given I put wrong password , when the password I give doesn’t match with my saved password then I'll receive a comment saying my password is wrong and then I can click on forget password button to change password | Emaild Id,Submit button and Cancel Button. |  | 4 | 0 | Initial
14 | Feature | Story | Student | access forget password | able to access password if forgotton/change password | given I want to change my password or I forget the password , when I click on forget password button then I'll be able to validate my account by giving the email id I provided in the website during account creation so that the password change link can be sent in my email and I can change the password by clicking in the link and get in to the website | After hitting Submit button , system will generate unique Student Code which will be mailed student and gurdian. |  |  | 0
15 | Feature | Story | Student | get a unique identification number | only me or my designated gurdian or one of the parent's can access my profile | given I want to study thorugh the website when I create my profile with validated criteria then an unique student number will be generated | 1) Drop Down Box for Standard 2)Drop Down Box for Board or University 3)Other if nothing matches in drop down for board/University, he/she can write 4) Multiple select for subjects |  | 5 | 0 | Initial
16 | Feature | Story | Student | have my own profile | I can put my personal details | given I want to make my profile , when I give my details in the form like Name, DOB, Standard, Board, Subjects then I am creating my basic profile |  |  | 1 | 0 | Initial
17 | Feature | Story | Student | have my own profile | I can put some further details | given I put further details in my profile for assistance , when I select which subject I'm best in and I'm weak in from the drop down menu then I'll be able to get assistance for the best courses designed for me | 1) Check Box for accessibility |  |  | 0
18 | Feature | Story | Student | set the access of my profile | the private things in my profile are not visible by others | given I'm in my rpofile and I'm adult, when I'll set the access as private then no one can see my profile |  |  |  | 0
19 | Feature | Story | Student | set the access of my profile | I can set access public | given I'm in my profile and I'm minor when I'll set the access to parents/gurdian then one of the parents (who is liked with the profile) or gurdian (who is linked with the profile) can see my profile |  |  |  | 0
20 |  |  |  | purchase a course | [5 empty] | 0
21 |  |  |  | purchase videos | [5 empty] | 0
22 |  |  |  | Examination Details |  |  | Entry of Student Details in Edit Mode |  | 3 | 0 | Initial
23 | Feature | Story | Student | have my own profile | I can see my courses which I've entered data | given I'm inside my profile when I buy courses then I can see them inside my profile |  |  | 4 | 0 | Initial
24 | Feature | Story | Student | have my own profile | I can see the videos I bought or got free | given I'm inside my profile when I buy videos then I can see them inside my profile | Edit screen of Examination Details and result data given by Teacher |  | 5 | 0 | Initial
25 | Feature | Story | Student | have my own profile | I can see my test papers of all subjects which ive appeared for and results of all of them | given I'm inside my profile when I give tests on one or many subjects or many tests in on esubjects then the results should be there with the test papers in my profile |  |  | 1 | 0 | Initial
26 | Feature | Story | Student | have my own profile | I can see the remarks given by the teacher on test papers | given I'm inside my profile when I will see my checked test papers then I can see the special notes from teachers | 2 Note Fields. 1) One for Student and 2)One for Teacher |  | 2 | 0 | Initial
27 | Feature | Story | Student | have my own profile | I can make notes for future reference | given I'm inside my profile when I will make notes about which area to improve based on teacher's remarks so that I can refer it when I appear for the test next time then I'll be able to make the notes with the subject as a tag or comment |  |  | 3 | 0 | Initial
28 | Feature | Story | Student | have my own profile | I can make notes for teachers to check | given im inside a subject in my profile when I want to keep note for the teacher about any clarification then I can see that |  |  | 4 | 0 | Initial
29 | Feature | Story | Student | have my own profile | I can make notes with date and time mentioned | given I'm inside my profile when I'm making notes for the teacher's reference then a date and time should be metioned for further reference |  |  | 5 | 0 | Initial
30 | Feature | Story | Student | have my own profile | I can see the notes from teachers with date and time reference | given I'm inside my profile , when I'll check the response of my notes then I'll be able to see answers from the teacher's with date and time reference |  |  |  | 0
31 | Feature | Story | Student | edit my profile | I can change details when needed | given I'm editing my profile, when I change/add or alter details in m profile then I'll be able to edit them by clicking on edit profile button |  |  | 1 | 0 | Initial
32 | Feature | Story | Student | see my rating given by the teachers | I can be motivated | given I'm inside my profile when I'm given rating by teachers then I'll be able to see it |  |  | 2 | 0 | Initial
33 | Feature | Story | Student | get rewarded from Anodiam | I can be motivated | rewaards can be given by Anodiam as a free course or badge which can be shared in social media |  |  |  | 0
34 | Feature | Story | Student | not download the videos | I can always see the videos online | given I'm watching the video when I want to save or download the video then it should not be downloaded or saved in the local mechine |  |  |  | 0
35 | Feature | Story | Student | not take the screenshot | I can not keep any document saved | given I'm taking screen shot when I'll try to capture then it should not allow to take the screen shot. |  |  |  | 0
36 | Feature | Story | Student | not copy and paste from the document | I can not keep any document saved | given I'm copying the text when I'll copy and paste the text then it wont allow to do so |  |  |  | 0
37 |  |  | Student | Sign Out | [5 empty] | 0
38 | Feature | Story | Teacher | signup | I can register | given I'm signing up for the website when I sign up with fulfilling valid criteria like name, date of birth, email id and click in the sign up button then I will be able to sign up in to the website. |  |  |  | 0
39 | Feature | Story | Teacher | login | I can go to my profile | given I,m logged in to the website , when I fill in the user name and password field with my valid cridentials and click in the sign in button then I get signed into the website. |  |  |  | 0
40 | Feature | Story | Teacher | create password | I can get into my profile | given I'm creating my password when I'm putting password followed by the instructions like one capital letter, one character, one numner and minimum eight character then the password is created |  |  |  | 0
41 | Feature | Story | Teacher | confirm password | I can get into my profile | given I've created password when I'll confirm the password in confirm password firld then I'll be able to access my profile |  |  |  | 0
42 | Feature | Story | Teacher | have a secure password | my profile is secure | given I'm putting the password in the password field, when I give my valid password and click in the password button then I'll be able to go to my profile after validation . |  |  |  | 0
43 | Feature | Story | Teacher | access Forget Password | able to access password if forgotton/change password | given I want to change my password or I forget the password , when I click on forget password button then I'll be able to validate my account by giving the email id I provided in the website during account creation so that the password change link can be sent in my email and I can change the password by clicking in the link and get in to the website |  |  |  | 0
44 | Feature | Story | Teacher | have my own profile | I can put my personal details | given I want to make my profile , when I give my details in the form like Name, DOB, profession, experience, Subjects that I teach then I am creating my basic profile |  |  |  | 0
45 | Feature | Story | Teacher | have edit profile option | I can change/add or alter my personal details if needed | given I'm editing my profile, when I change/add or alter details in my profile regarding my personal data like experience, qualification, then I'll be able to edit them by clicking on edit profile button |  |  |  | 0
46 | Feature | Story | Teacher | have direction to upload course/videos | I can make the videos available for students | given I upload videos/course meterials, when I'll follow the instructions how to upload a video/course meterial then I'll be able to upload the course/videos |  |  |  | 0
47 | Feature | Story | Teacher | get options where to place my videos/course meterials | my videos/course meterials can be viewed by the students | given I want to place my video in the website, when I'll choose the proper option like free videos/paid videos then students can see the videos in the proper place |  |  |  | 0
48 | Feature | Story | Teacher | upload videos | videos are visible to the audience | given I'm in my profile when I will upload videos after fulfilling criteries likefree or paid and subject check, board check, class check, standard (easy or hard) check then I can upload videos |  |  |  | 0
49 | Feature | Story | Teacher | edit videos before publish | I can publish only error free videos | given I'm uploading my video when I'll check it before clicking publish button then my error checking is done |  |  |  | 0
50 | Feature | Story | Teacher | see the remarks by students | I can answer their remarks | given I'm in my profile when students will ask any question through remarks then I can view them and able to answer |  |  |  | 0
51 | Feature | Story | Student | see the remarks date and time | I can answer accordingly | given I'm viewing the remarks by the students when I click on the remarks then I can see the date and time |  |  |  | 0
52 | Feature | Story | Student | see a notification in my mail | I can understand there is a remark in my profile | given I get a remarks notification when I get a remarks from the student with their UIN about asking any question then I get a system generated notification in my email about the remark so that I can keep a track of remarks from individual sudents. |  |  |  | 0
53 | Feature | Story | Teacher | see remarks by parents | I can answer accordingly | given I get a remark by a parent referring the student's UIN when I get a remark from a parent with their student's UIN then I'll receive a system generated notification in my email |  |  |  | 0
54 | Feature | Story | Teacher | check answers of the test papers | I can do the correction and give marks | given I'm checking a test paper when I'll check test papers for a subject of a class on a standard then I'll be able to correct wrong answers or give marks for right answers |  |  |  | 0
55 | Feature | Story | Teacher | rate students | students get motivation | given I'm rating a student when I student can satisfy certain criteria like course complication within time frame/ getting "A" grade marks in a subject / completing test after finishing course within a time frame then the student will be rated stars |  |  |  | 0
56 | Feature | Story | Teacher | not edit or delete any video or course meterial | editing option is not with me | given I want to delete an uploaded video or course meterial when I try to do this then I should get access denied option |  |  |  | 0
User preference and predicting the most suitable courses for individual user in their home screen
Note on G1: Help: Acceptance Criteria in Product Backlog comprises of 4 fields, namely: Scenerio, Given, When Then. Here all 4 fields should be colated into one. E.g. Acceptance criteria for following should be as below: User Story: As a logged out User I want to be able to sign into the website, so that I can see my profile. Acceptance Criteria: Scenario: Registered User Signs with valid username and password. Given: I am logged out of website. When: I fill in the username and password fields with my valid credentials and click in sign in button Then: I get signed into the website. Here, Acceptance Criteria could be written in 1 sentence as below: Given I am logged out of website, if I fill in the username and password fields with my valid credentials and click in sign in button, I should get signed into the website.
Note on I1: Help: XS : 1 Story Point : 0 to 2 person hours S : 2 Story Points : 2 to 4 person hours M : 3 Story Points : 4 to 8 person hours L : 5 Story Points : 1 to 1.5 person days XL : 8 Story Points : 1.5 to 2.5 person days XXL : 13 Story Points : 0.5 to 1 person weeks XXXL : 21 Story Points : Larger and never used