## Sheet1
# | Size | Type | Item | Status | Due Date
1 | Small | Management | Create a ppt for inviting Content Creation accociates & Quality Control | WIP | 2022-11-04
2 | Small | IT | Wireframe presentation to Swapan Sir | WIP | 2022-11-04
3 | Small | Management | Start MoM / Status Email | Done | 2022-11-03
4 | Medium | Content | Detail Plan to financially engage Content Creation Associates, Any legal signup docs? | Open | 2022-11-07
5 | Medium | Content | Facilities planning (real estate & office and shootin floors) for content Creation | Open | 2022-11-07
6 | Medium | Content | Communication planning, (Meeting / Medium) for content team | Open | 2022-11-07
7 | Medium | Content | Plan props, back grounds, instruments for shooting and software for editing and version control of content | Open | 2022-11-07
8 | Big | IT | Initial App & Website front end | WIP | 2022-11-30
9 | Big | Content | Class 9 - CBSE: Physics Chem Math Bio | Open | 2022-03-31
10 | Big | IT | Initial App & Website | WIP | 2022-03-31
How much time Swapan sir would dedicate per week
How much time each individual Content stake holder need per week. How do we ensure that?