## Sheet1
# | Size | Type | Item | Description | Status | Due Date
1 | Small | Content | Create a ppt for inviting Content Creation accociates & Quality Control | 9-Nov: SR to review | WIP | 2022-11-04
2 | Small | Content | Create budget for IX CBSE Bio | 9-Nov: TBD on 15-Nov Meeting | Open | 2022-11-15
3 | Small | Content | Budgeting for entire Content Creation Project | 9-Nov: TBD on 15-Nov Meeting | Open | 2022-11-15
4 | Medium | Content | Detail Plan to financially engage Content Creation Associates, Any legal signup docs? | 9-Nov: TBD on 15-Nov Meeting | Open | 2022-11-15
| Medium | Content | Get full time manager for Content creation | 9-Nov: SR to recruit | Open | TBD
5 | Medium | Content | Facilities planning (real estate & office and shootin floors) for content Creation | 9-Nov: SR - Rjarhat and Golpark studios. AC - Patuli property. To be finalized | Open | TBD
6 | Medium | Content | Communication planning, (Meeting / Medium) for content team | 9-Nov: SR agreed, TBD after resources onboarding | Open | TBD
7 | Medium | Content | Plan props, back grounds, instruments for shooting and software for editing and version control of content | 9-Nov: SR agreed, TBD after resources onboarding | Open | TBD
9 | Big | Content | Class 9 - CBSE: Physics Chem Math Bio | 9-Nov: Deadline decided - end of March. | Open | 2022-03-31
10 | Small | Content | Start MoM / Status Email | 9-Nov: AC Completed | Done | 2022-11-03
11 | Big | IT | Initial App & Website | 9-Nov: Deadline decided - end of March. | WIP | 2022-03-31
12 | Big | IT | Initial App & Website front end | 9-Nov: Deadline decided - end of November | WIP | 2022-11-30
13 | Small | IT | Wireframe presentation to Swapan Sir | 9-Nov: AC Completed | Done | 2022-11-04