## Cover Sheet
Anodiam
MVP Product Backlog
Rolling Versions
Version | Editor | Reviewer | Date | Note
0.1 | AC |  | 2020-05-04 | Initial version

## MobileProdBacklog
Item # | Item Type | Item Size | As a… | I want to be able to… | So that… | Acceptance Criteria | Notes / References | Task Estimate | Business Value | Priority | Status | Sprint Number
35 | Enabler | Story |  | Jenkins Pipeline |  |  | Follow DevOps Bootcamp | 2 | 5 | 2.5 | Scheduled | 2022-04-13
36 | Enabler | Story |  | Anisible IaC |  |  | Follow DevOps Bootcamp | 2 | 4 | 2 | Scheduled | 2022-04-13
40 | Enabler | Story |  | Istio |  |  | Follow DevOps Bootcamp | 2 | 5 | 2.5 | Scheduled | 2022-04-13
44 | Enabler | Story |  | Promethious |  |  | Follow DevOps Bootcamp | 2 | 5 | 2.5 | Scheduled | 2022-04-13
45 | Enabler | Story |  | Grafana |  |  | Follow DevOps Bootcamp | 2 | 4 | 2 | Scheduled | 2022-04-13
38 | Enabler | Story |  | JWT
39 | Enabler | Story |  | Cloud SQL
37 | Enabler | Story |  | GCP Secret Manager
52 | Enabler | Story |  | PubSub Messaging from Spring Boot
42 | Enabler | Story |  | DNS
41 | Enabler | Story |  | SSL
46 | Enabler | Story |  | Junit Infra
47 | Enabler | Story |  | Jest Infra
48 | Enabler | Story |  | Katalon Studio
49 | Enabler | Story |  | Automated Code Review Infra
50 | Enabler | Story |  | Performance Test Infra
51 | Enabler | Story |  | Pen Test Infra
43 | Enabler | Story |  | Jira
1 | Feature | Story | Unsigned user | Install Anodiam MVP Mobile App from Apple App Store on my iPhone or iPad OR from Android Play Store on my Android device | I can view the Anodiam icon on my Apple iPhone or iPad OR on my Android device | Given I am an unsigned user When Install Anodiam MVP Mobile App from Apple App Store on my iPhone or iPad OR from Android Play Store on my Android device Then I should be able to view the Anodiam icon on my Apple iPhone or iPad OR on my Android device | 006WireframeMVPStudentMobileApp.pptx
2 | Feature | Story | Unsigned user | Tap on the Anodiam icon on my smart phone | I can view the the splash screen of the anodiam Student MVP app | Given I am an unsigned user When I Tap on the Anodiam icon on my smart phone Then I should be able to view the splash screen of the Anodiam Student MVP app | 006WireframeMVPStudentMobileApp.pptx
3 | Feature | Story | Unsigned user | Tap the LOGIN button on the splash screen | I can view the login screen | Given I am an unsigned user When I Tap the LOGIN button on the splash screen Then I should be able to view the login screen | 006WireframeMVPStudentMobileApp.pptx
4 | Feature | Story | Unsigned user | Tap the SIGNUP button on the splash screen | I can view the signup screen | Given I am an unsigned user When I Tap the SIGNUP button on the splash screen Then I should be able to view the signup screen | 006WireframeMVPStudentMobileApp.pptx
5 | Feature | Story | Unsigned user | Tap the SIGNUP button on the LOGIN screen | I can view the signup screen | Given I am an unsigned user When I Tap the SIGNUP button on the LOGIN screen Then I should be able to view the signup screen | 006WireframeMVPStudentMobileApp.pptx
6 | Feature | Story | Unsigned user | Tap the SIGNIN button on the SIGNUP screen | I can view the LOGIN screen | Given I am an unsigned user When I Tap the SIGNIN button on the SIGNUP screen Then I should be able to view the LOGIN screen | 006WireframeMVPStudentMobileApp.pptx
7 | Feature | Story | Unsigned user | Type in Invalid Email format in the "Your Email" field of the SIGNUP screen | I can see validation message: "Invalid email format" | Given I am an unsigned user When I Type in Invalid Email format in the "Your Email" field of the SIGNUP screen Then I should be able to see validation message: "Invalid email format" | 006WireframeMVPStudentMobileApp.pptx
8 | Feature | Story | Unsigned user | Keep "Your Email" field blank in the SIGNUP screen and tap outside | I can see validation message: "Email address is required" | Given I am an unsigned user When I Keep "Your Email" field blank in the SIGNUP screen and tap outside Then I should be able to see validation message: "Email address is required" | 006WireframeMVPStudentMobileApp.pptx
9 | Feature | Story | Unsigned user | Enter an already existing email address in "Your Email" in the SIGNUP screen and tap outside | I can see validation message: "Email address already registered" | Given I am an unsigned user When I Enter an already existing email address in "Your Email" in the SIGNUP screen and tap outside Then I should be able to see validation message: "Email address already registered" | 006WireframeMVPStudentMobileApp.pptx
10 | Feature | Story | Unsigned user | Type in Invalid Email format in the "Inviter's Email" field of the SIGNUP screen | I can see validation message: "Invalid email format" | Given I am an unsigned user When I Type in Invalid Email format in the "Inviter's Email" field of the SIGNUP screen Then I should be able to see validation message: "Invalid email format" | 006WireframeMVPStudentMobileApp.pptx
11 | Feature | Story | Unsigned user | Enter a no existing email address in "Inviter's Email" in the SIGNUP screen and tap outside | I can see validation message: "Email address already registered" | Given I am an unsigned user When I Enter a non existing email address in "Inviter's Email" in the SIGNUP screen and tap outside Then I should be able to see validation message: "Email address not registered with Anodiam" | 006WireframeMVPStudentMobileApp.pptx
12 | Feature | Story | Unsigned user | Tap on the (?) help icon for "Your Email" field in the SIGNUP screen | I see Alert help message: 'Help:', 'Please provide your permanent email address.\n- All communications from Anodiam will be through this email.\n- Also, this is going to be used as your username in Anodiam.' | Given I am an unsigned user When I Tap on the (?) help icon for "Your Email" field in the SIGNUP screen Then I should be able to see Alert help message: 'Help:', 'Please provide your permanent email address.\n- All communications from Anodiam will be through this email.\n- Also, this is going to be used as your username in Anodiam.' | 006WireframeMVPStudentMobileApp.pptx
13 | Feature | Story | Unsigned user | Tap on the (?) help icon for "Inviter's Email" field in the SIGNUP screen | I see Alert help message: 'Help:', 'Enter the exact email address of the person who invited you to Anodiam.\n- Both of you will get benefits!' | Given I am an unsigned user When I Tap on the (?) help icon for "Inviter's Email" field in the SIGNUP screen Then I should be able to see Alert help message: 'Help:', 'Enter the exact email address of the person who invited you to Anodiam.\n- Both of you will get benefits!' | 006WireframeMVPStudentMobileApp.pptx
14 | Feature | Story | Unsigned user | Tap on the (?) help icon for "Password" field in the SIGNUP screen | I see Alert help message: 'Help:', 'Eight (8) or more characters.\n- Letters (a-z, A-Z)\n- Numerals (0-9)\n- Special characters (@,#,$,%,^,&,+,=)' | Given I am an unsigned user When I Tap on the (?) help icon for "Inviter's Email" field in the SIGNUP screen Then I should be able to see Alert help message: 'Help:', 'Eight (8) or more characters.\n- Letters (a-z, A-Z)\n- Numerals (0-9)\n- Special characters (@,#,$,%,^,&,+,=)' | 006WireframeMVPStudentMobileApp.pptx
15 | Feature | Story | Unsigned user | Type on the Password field in the SIGNUP screen | The text should be hidden by default | Given I am an unsigned user When I Type on the Password field in the SIGNUP screen Then I should be able to see that the text is hidden by default | 006WireframeMVPStudentMobileApp.pptx
16 | Feature | Story | Unsigned user | Type on the Confirm Password field in the SIGNUP screen | The text should be hidden by default | Given I am an unsigned user When I Type on the Confirm Password field in the SIGNUP screen Then I should be able to see that the text is hidden by default | 006WireframeMVPStudentMobileApp.pptx
17 | Feature | Story | Unsigned user | Type on the Password field in the LOGIN screen | The text should be hidden by default | Given I am an unsigned user When I Type on the Password field in the LOGIN screen Then I should be able to see that the text is hidden by default | 006WireframeMVPStudentMobileApp.pptx
18 | Feature | Story | Unsigned user | Tap on the Eye icon in the Password field and Type on the Password field in the SIGNUP screen | The text should NOT be hidden and the eye icon will change to closed eye icon | Given I am an unsigned user When I Tap on the Eye icon in the Password field and Type on the Password field in the SIGNUP screen Then I should be able to see that The text is NOT hidden and the eye icon will change to closed eye icon | 006WireframeMVPStudentMobileApp.pptx
19 | Feature | Story | Unsigned user | Tap on the Eye icon in the Confirm Password field and Type on the Password field in the SIGNUP screen | The text should NOT be hidden and the eye icon will change to closed eye icon | Given I am an unsigned user When I Tap on the Eye icon in the Confirm Password field and Type on the Password field in the SIGNUP screen Then I should be able to see that The text is NOT hidden and the eye icon will change to closed eye icon | 006WireframeMVPStudentMobileApp.pptx
20 | Feature | Story | Unsigned user | Tap on the Eye icon in the Password field and Type on the Password field in the LOGIN screen | The text should NOT be hidden and the eye icon will change to closed eye icon | Given I am an unsigned user When I Tap on the Eye icon in the Password field and Type on the Password field in the LOGIN screen Then I should be able to see that The text is NOT hidden and the eye icon will change to closed eye icon | 006WireframeMVPStudentMobileApp.pptx
21 | Feature | Story | Unsigned user | Type on the Confirm Password field in the SIGNUP screen and it does not match the Password field | Validation Error is shown as: Confirm password does not match. | Given I am an unsigned user When I Type on the Confirm Password field in the SIGNUP screen and it does not match the Password field Then I should be able to see that Validation Error is shown as: Confirm password does not match. | 006WireframeMVPStudentMobileApp.pptx
22 | Feature | Story | Unsigned user | Keep Confirm Password field as blank in the SIGNUP screen and press SIGNUP (or tap outside) | Validation Error is shown as: Please retype your password. | Given I am an unsigned user When I Keep Confirm Password field as blank in the SIGNUP screen and press SIGNUP (or tap outside) Then I should be able to see that Validation Error is shown as: Please retype your password. | 006WireframeMVPStudentMobileApp.pptx
23 | Feature | Story | Unsigned user | Keep Email field as blank in the LOGIN screen and press LOGIN (or tap outside) | Validation Error is shown as: Email cannot be blank | Given I am an unsigned user When I Keep Email field as blank in the LOGIN screen and press LOGIN (or tap outside) Then I should be able to see that Validation Error is shown as: Email cannot be blank. | 006WireframeMVPStudentMobileApp.pptx
24 | Feature | Story | Unsigned user | Keep Password field as blank in the LOGIN screen and press LOGIN (or tap outside) | Validation Error is shown as: Password cannot be blank | Given I am an unsigned user When I Keep Password field as blank in the LOGIN screen and press LOGIN (or tap outside) Then I should be able to see that Validation Error is shown as: Password cannot be blank. | 006WireframeMVPStudentMobileApp.pptx
25 | Feature | Story | Unsigned user | Enter invalid Email format in Email field in the LOGIN screen and press LOGIN (or tap outside) | Validation Error is shown as: Invalid Email format | Given I am an unsigned user When I Enter invalid Email format in Email field in the LOGIN screen and press LOGIN (or tap outside) Then I should be able to see that Validation Error is shown as: Invalid Email format | 006WireframeMVPStudentMobileApp.pptx
26 | Feature | Story | Unsigned user | Enter wrong credentials in the LOGIN screen and press LOGIN | Authentication is denied and Entry to the further screens is stopped with Validation Error is shown on top as: Wrong Email or password | Given I am an unsigned user When I Enter wrong credentials in the LOGIN screen and press LOGIN Then I should be able to see that my Authentication is denied and Entry to the further screens is stopped with Validation Error is shown on top as: Wrong Email or password | 006WireframeMVPStudentMobileApp.pptx
27 | Feature | Story | Unsigned user | Enter valid credentials in the LOGIN screen and press LOGIN | Authentication is given and I can view my Home screen | Given I am an unsigned user When I Enter valid credentials in the LOGIN screen and press LOGIN Then I should be able to see that my Authentication is given and I can view my Home screen | 006WireframeMVPStudentMobileApp.pptx
28 | Feature | Story | Unsigned user | Tap on the "Change/Forget Password" link in the LOGIN screen | I could see the Alert message: 'Change/Forget Password','This functionality will be available soon!' | Given I am an unsigned user When I Tap on the "Change/Forget Password" link in the LOGIN screen Then I should be able to see the Alert message: 'Change/Forget Password','This functionality will be available soon!' | 006WireframeMVPStudentMobileApp.pptx
29 | Feature | Story | Unsigned user | Type in the Password field of the SIGNUP screen, anything different from: Minimum 6 Chars, Uppercase, Lowercase, Number & Special Char | I should get validation error: Minimum 6 Chars, Uppercase, Lowercase, Number & Special Char | Given I am an unsigned user When I Type in the Password field of the SIGNUP screen, anything different from: Minimum 6 Chars, Uppercase, Lowercase, Number & Special Char Then I should be able to see validation error: Minimum 6 Chars, Uppercase, Lowercase, Number & Special Char | 006WireframeMVPStudentMobileApp.pptx
30 | Feature | Story | Unsigned user | Type in valid entries for Email, Inviter's Email (not mandatory), Password and confirm Password fields in the SIGNUP screen and press SIGNUP | I am registered as an user into Anodiam App and I am authorised and my Home screen is openned with a toast for 5 seconds saying: Congratulations! You are registered into Anodiam! | Given I am an unsigned user When I Type in valid entries for Email, Inviter's Email (not mandatory), Password and confirm Password fields in the SIGNUP screen and press SIGNUP Then I should be able to see that I am registered as an user into Anodiam App and I am authorised and my Home screen is openned with a toast for 5 seconds saying: Congratulations! You are registered into Anodiam! | 006WireframeMVPStudentMobileApp.pptx
31 | Feature | Epic |  | Forget Password
32 | Feature | Epic |  | Sign in with Google
33 | Feature | Epic |  | Sign in with Facebook
34 | Feature | Epic |  | Web frontend
53 | Feature | Epic |  | Video/Audio/Picture stream upload / Download to GCP storage
Note on G1: Help: Acceptance Criteria in Product Backlog comprises of 3 fields, namely: Given, When Then. Here all 4 fields should be colated into one. E.g. Acceptance criteria for following should be as below: User Story: As a logged out User I want to be able to sign into the website, so that I can see my profile. Acceptance Criteria: Scenario: Registered User Signs with valid username and password. Given: I am logged out of website. When: I fill in the username and password fields with my valid credentials and click in sign in button Then: I get signed into the website. Here, Acceptance Criteria could be written in 1 sentence as below: Given I am logged out of website, if I fill in the username and password fields with my valid credentials and click in sign in button, I should get signed into the website.
Note on I1: Help: XS : 1 Story Point : 0 to 2 person hours S : 2 Story Points : 2 to 4 person hours M : 3 Story Points : 4 to 8 person hours L : 5 Story Points : 1 to 1.5 person days XL : 8 Story Points : 1.5 to 2.5 person days XXL : 13 Story Points : 0.5 to 1 person weeks XXXL : 21 Story Points : Larger and never used

## WebProdBacklog
Item # | Item Type | Item Size | As a… | I want to be able to… | So that… | Acceptance Criteria | Notes / References | Task Estimates (Story Points) | Business Value | Priority | Status | Sprint Number
1 | Feature | Story | Unsigned user | Visit anodiam.com | I can view the Anodiam login page containing link to register and a login section. | Given I am an unsigned user When I type anodiam.com on a web browser Then I should be able to view the Anodiam login page: containing link to register (Not yet registered? Register here) and a login section. | 004MVPStudentAppWireframes.pptx >> Student Login Page | 2 | 5 | 2.5 | Scheduled | 1
2 | Feature | Story | Unsigned user | Click on the Register here link on the login page of anodiam.com | I can view the Anodiam registration page containing a link to login page (Already registered? Login here) and a registration section. | Given I am an unsigned user When I click on the Register here link on the login page of anodiam.com Then I should be able to view the Anodiam registration page: containing a link to login page (Already registered? Login here) and a registration section. | 004MVPStudentAppWireframes.pptx >> Student Login Page | 1 | 5 | 5 | Scheduled | 1
3 | Feature | Story | Unsigned user | Fill up all the fields: (First Name, Last Name, email, username, password, confirm password) (all mandatory) with valid informations in the registration section of the Student Registration Page and click on the Register button. | I can register myself as a student with anodiam.com. Upon successful registration I must be logged in (getting a JWT Token) and forwarded to my profile page. | Given I am an unsigned user When I fill up all the fields: (First Name, Last Name, email, username, password, confirm password) (all mandatory) in the registration section of the Student Registration Page with valid inputs and click on the Register button Then I should be able to register myself as a student with anodiam.com. Upon successful registration I must be logged in (getting a JWT Token) and forwarded to my profile page. | 004MVPStudentAppWireframes.pptx >> Student Registration Page | 5 | 5 | 1 | Scheduled | 1
3.2.1 | Feature | Story | Unsigned user | Enter invalid username (Less than 8 characters long) in the registration section of the Student Registration Page and (fill up legitimate values for email, password and confirm password) and click on the Register button. | I cannot register myself as a student with anodiam.com. I must receive error message: Student registration failure! Username should be 8 or more characters long. | Given I am an unsigned user When I enter invalid username (Less than 8 characters long) in the registration section of the Student Registration Page and (fill up legitimate values for email, password and confirm password) and click on the Register button Then I should not be able to register myself as a student with anodiam.com. I should receive error message: Student registration failure! Username should be 8 or more characters long. | 004MVPStudentAppWireframes.pptx >> Student Registration Page | 2 | 5 | 2.5 | Scheduled | 1
3.2.2 | Feature | Story | Unsigned user | Enter an already existing Anodiam username in the registration section of the Student Registration Page and click on the Register button. | I cannot register myself as a student with anodiam.com. I must receive error message: Student registration failure! This username is already taken by another user. Please try some other username. | Given I am an unsigned user When I enter invalid username (an already existing username) in the registration section of the Student Registration Page and click on the Register button Then I should not be able to register myself as a student with anodiam.com. I should receive error message: Student registration failure! This username is already taken by another user. Please try some other username. | 004MVPStudentAppWireframes.pptx >> Student Registration Page | 2 | 5 | 2.5 | Scheduled | 1
3.2.3 | Feature | Story | Unsigned user | Enter blank username in the registration section of the Student Registration Page and click on the Register button. | I cannot register myself as a student with anodiam.com. I must receive error message: Student registration failure! Username cannot be blank. | Given I am an unsigned user When I enter blank username in the registration section of the Student Registration Page and click on the Register button Then I should not be able to register myself as a student with anodiam.com. I should receive error message: Student registration failure! Username cannot be blank. | 004MVPStudentAppWireframes.pptx >> Student Registration Page | 2 | 5 | 2.5 | Scheduled | 1
3.3.1 | Feature | Story | Unsigned user | Enter invalid password Less than 8 characters in the registration section of the Student Registration Page and click on the Register button. | I cannot register myself as a student with anodiam.com. I must receive following error message: Student registration failure! Invalid password. Password should be 8 to 20 characters long. | Given I am an unsigned user When I enter invalid password Less than 8 characters in the registration section of the Student Registration Page and click on the Register button. Then I should not be able to register myself as a student with anodiam.com. I should receive error message: Student registration failure! Invalid password. Password should be 8 to 20 characters long. | 004MVPStudentAppWireframes.pptx >> Student Registration Page | 2 | 5 | 2.5 | Scheduled | 1
3.3.2 | Feature | Story | Unsigned user | Enter invalid password More than 20 characters in the registration section of the Student Registration Page and click on the Register button. | I cannot register myself as a student with anodiam.com. I must receive following error message: Student registration failure! Invalid password. Password should be 8 to 20 characters long. | Given I am an unsigned user When I enter invalid password More than 20 characters in the registration section of the Student Registration Page and click on the Register button. Then I should not be able to register myself as a student with anodiam.com. I should receive error message: Student registration failure! Invalid password. Password should be 8 to 20 characters long. | 004MVPStudentAppWireframes.pptx >> Student Registration Page | 2 | 5 | 2.5 | Scheduled | 1
3.3.3 | Feature | Story | Unsigned user | Enter invalid password that contains the username string within the password in the registration section of the Student Registration Page and click on the Register button. | I cannot register myself as a student with anodiam.com. I must receive following error message: Student registration failure! Invalid password. Password should not contain your username. | Given I am an unsigned user When I enter invalid password that contains the username string within the password in the registration section of the Student Registration Page and click on the Register button. Then I should not be able to register myself as a student with anodiam.com. I should receive error message: Student registration failure! Invalid password. Password should not contain your username. | 004MVPStudentAppWireframes.pptx >> Student Registration Page | 2 | 5 | 2.5 | Scheduled | 1
3.3.4 | Feature | Story | Unsigned user | Enter invalid password Does not contain at least one small alphabet (a-z), at least one capital alphabet (A-Z), at least one numeric (0-9) and at least one special character among (@,#,$,%,^,&,+,=) in the registration section of the Student Registration Page and click on the Register button. | I cannot register myself as a student with anodiam.com. I must receive following error message: Student registration failure! Invalid password. Password must contain at least one small alphabet (a-z), at least one capital alphabet (A-Z),at least one numeric (0-9) and at least one special character among (@,#,$,%,^,&,+,=) | Given I am an unsigned user When I enter invalid password Does not contain at least one small alphabet (a-z), at least one capital alphabet (A-Z), at least one numeric (0-9) and at least one special character among (@,#,$,%,^,&,+,=) in the registration section of the Student Registration Page and click on the Register button. Then I should not be able to register myself as a student with anodiam.com. I should receive error message: Student registration failure! Invalid password. Password must contain at least one small alphabet (a-z), at least one capital alphabet (A-Z),at least one numeric (0-9) and at least one special character among (@,#,$,%,^,&,+,=) | 004MVPStudentAppWireframes.pptx >> Student Registration Page | 2 | 5 | 2.5 | Scheduled | 1
3.3.5 | Feature | Story | Unsigned user | Starting to type my password in the registration page | I can see a password strength meter line depicting the strength of my password. The line will change color from red to amber to green and grow in length from 0-100% as my password strength gets stronger (according to the above conditions form the above use cases) | Given I am an unsigned user WhenStarting to type my password in the registration page Then I should be able to see a password strength meter line depicting the strength of my password. The line will change color from red to amber to green and grow in length from 0-100% as my password strength gets stronger (according to the above conditions form the above use cases)
3.4.1 | Feature | Story | Unsigned user | Enter invalid email address 1. Does not contain exactly one '@' character. 2. Does not contain one or more '.' characters after the '@' character. 3. Does not contain any alphabet (a-z, A-Z) before '@'. 4. Does not contain any alphabet (a-z, A-Z) in between '@' and '.'. 5. Does not contain any alphabet (a-z, A-Z) after the last '.' character. in the registration section of the Student Registration Page and click on the Register button. | I cannot register myself as a student with anodiam.com. I must receive following error message: Student registration failure! Invalid email address. | Given I am an unsigned user When I enter invalid email address 1. Does not contain exactly one '@' character. 2. Does not contain one or more '.' characters after the '@' character. 3. Does not contain any alphabet (a-z, A-Z) before '@'. 4. Does not contain any alphabet (a-z, A-Z) in between '@' and '.'. 5. Does not contain any alphabet (a-z, A-Z) after the last '.' character in the registration section of the Student Registration Page and click on the Register button Then I should not be able to register myself as a student with anodiam.com. I should receive respective error message: Student registration failure! Invalid email address | 004MVPStudentAppWireframes.pptx >> Student Registration Page | 2 | 5 | 2.5 | Scheduled | 1
3.4.2 | Feature | Story | Unsigned user | Enter already existing Anodiam user email address in the registration section of the Student Registration Page and click on the Register button. | I cannot register myself as a student with anodiam.com. I must receive following error message: Student registration failure! An user with the same email address is already registered. | Given I am an unsigned user When I enter an already existing username in the Student Registration Page and click on the Register button Then I should not be able to register myself as a student with anodiam.com. I should receive respective error message: Student registration failure! An user with the same email address is already registered. | 004MVPStudentAppWireframes.pptx >> Student Registration Page | 2 | 5 | 2.5 | Scheduled | 1
3.5 | Feature | Story | Unsigned User | Enter wrong Confirm Password in the Student Registration Page and click on the Register button. | I cannot register myself as a student with anodiam.com. I must receive following error message: Password and Confirm Password fields do not match. | Given I am an unsigned user When I enter wrong Confirm Password in the Student Registration Page and click on the Register button. Then I should not be able to register myself as a student with anodiam.com. I should receive error message: Password and Confirm Password fields do not match. | 004MVPStudentAppWireframes.pptx >> Student Registration Page | 2 | 3 | 1.5 | Scheduled | 1
3.6 | Feature | Story | Unsigned User | Try to copy or paste in the Password or Confirm Pasword fields of the Registration page | I am not allowed to Copy or paste in the Password or Confirm Pasword fields of the Registration page | Given I am an unsigned user When Try to copy or paste in the Password or Confirm Pasword fields of the Registration page. Then I am not allowed to Copy or paste in the Password or Confirm Pasword fields of the Registration page. | 004MVPStudentAppWireframes.pptx >> Student Registration Page | 2 | 1 | 0.5 | Scheduled | 1
3.7 | Feature | Story | Unsigned User | Try to copy or paste in the Password field of the Login page | I am not allowed to Copy or paste in the Password field of the Login page | Given I am an unsigned user When Try to copy or paste in the Password field of the Login page. Then I am not allowed to Copy or paste in the Password field of the Login page. | 004MVPStudentAppWireframes.pptx >> Student Login Page | 2 | 1 | 0.5 | Scheduled | 1
3.8 | Feature | Story | Unsigned User | Enter Confirm password not equal to password in the registration page. | I cannot register myself as a student with anodiam.com. I must receive following validation error message: Confirm Password: Does not match with password. | Given I am an unsigned user When Enter Confirm password not equal to password in the registration page. Then I am not allowed register myself as a student with anodiam.com. I must receive following validation error message: Confirm Password: Does not match with password. | 004MVPStudentAppWireframes.pptx >> Student Login Page | 2 | 1 | 0.5 | Scheduled | 1
3.9 | Feature | Story | Unsigned User | Check or uncheck the Show password checkbox in the registration page. | I can toggle the password field as unmasked (checked) or masked (unchecked) | Given I am an unsigned user When Check or uncheck the Show password checkbox in the registration page. Then I can toggle the password field as unmasked (checked) or masked (unchecked) | 004MVPStudentAppWireframes.pptx >> Student Login Page | 2 | 1 | 0.5 | Scheduled | 1
4 | Feature | Story | Unsigned user | Click on the Already registered? Login link on the registration page of anodiam.com | I can view the Anodiam Buy Courses page containing link to register and a login section. | Given I am an unsigned user When I Click on the Already registered? Login link on the registration page of anodiam.com Then I should be able to view the Anodiam Buy Courses page: containing link to register and a login section. | 004MVPStudentAppWireframes.pptx >> Student Registration Page | 2 | 5 | 2.5 | Scheduled | 1
5 | Feature | Story | Unsigned registered user | Fill up the valid username and password fields in the login page and click on the Login button. | I can log in to anodiam.com and view the Buy Courses Page. | Given I am an unsigned but registered user When I fill up the username and password fields in the login page and click on the Login button Then I should be able to view the Anodiam Buy Courses Page: containing a welcome message with my (first and last) name at the top. | 004MVPStudentAppWireframes.pptx >> Student Login Page | 5 | 5 | 1 | Scheduled | 1
5.1 | Feature | Story | Unsigned registered user | Fill up the username and password fields with invalid username in the login page and click on the Login button. | I can not log in to anodiam.com and view the Buy Courses Page. I must be sent back to the login page with a login validation message (Unauthorized login attempt! Wrong username or password.) displayed on top in red. | Given I am an unsigned but registered user When I fill up the username and password fields invalid username in the login page and click on the Login button Then I should be not able to view the Anodiam Buy Courses Page. I must be sent back to the login page with a login validation message (Unauthorized login attempt! Wrong username or password.) displayed on top in red. | 004MVPStudentAppWireframes.pptx >> Student Login Page | 5 | 5 | 1 | Scheduled | 1
5.2 | Feature | Story | Unsigned registered user | Fill up the username and password fields with balid username but invalid password in the login page and click on the Login button. | I can not log in to anodiam.com and view the Buy Courses Page. I must be sent back to the login page with a login validation message (Unauthorized login attempt! Wrong username or password.) displayed on top in red. | Given I am an unsigned but registered user When I fill up the username and password fields invalid username in the login page and click on the Login button Then I should be not able to view the Anodiam Buy Courses Page. I must be sent back to the login page with a login validation message (Unauthorized login attempt! Wrong username or password.) displayed on top in red. | 004MVPStudentAppWireframes.pptx >> Student Login Page | 5 | 5 | 1 | Scheduled | 1
5.3 | Feature | Story | Unsigned User | Check or uncheck the Show password checkbox in the login page. | I can toggle the password field as unmasked (checked) or masked (unchecked) | Given I am an unsigned user When Check or uncheck the Show password checkbox in the login page. Then I can toggle the password field as unmasked (checked) or masked (unchecked) | 004MVPStudentAppWireframes.pptx >> Student Login Page | 2 | 1 | 0.5 | Scheduled | 1
6 | Feature | Story | Signed in user | Sign into anodiam and land up to view Buy Courses page | I can see a welcome messaage on top, saying "Welcome {username)" in case my firstname does not exist in my profile. Otherwise the message should display "Welcome {firstname}" | Given I am a signed in user When Sign into anodiam and land up to view Buy Courses page Then I should be able to see a welcome messaage on top, saying "Welcome {username)" in case my firstname does not exist in my profile. Otherwise the message should display "Welcome {firstname}" |  | 2 | 1 | 0.5 | Scheduled | 2
7 | Feature | Story | Signed in user | Sign into anodiam and land up to view Buy Courses page | I can see the following links in the responsive Navbar: 1. Anodiam logo (link to Buy Courses) (on left side) 2. My Courses, My Profile & Logout links at the right. | Given I am a signed in user When Sign into anodiam and land up to view Buy Courses page Then I should be able to see the following links in the responsive Navbar: 1. Anodiam logo (link to Buy Courses) (on left side) 2. My Courses & Logout links at the right. |  | 2 | 1 | 0.5 | Scheduled | 2
8 | Feature | Story | Signed in user | Click on the Logout link of the navbar | I should be signed out of anodiam. I should be sent to the Login page. The navbar links will show only Login and Register links. The welcome message will also not be displayed | Given I am a signed in user When Click on the Logout link of the navbar Then I should be signed out of anodiam. I should be sent to the Login page. The navbar links will show only Login and Register links. The welcome message will also not be displayed. |  | 2 | 1 | 0.5 | Scheduled | 2
9 | Feature | Story | Signed in user | Click on the Anodiam logo (link to Buy Courses) of the navbar | I can visit my Buy Courses page. | Given I am a signed in user When Click on the Buy Courses link of the navbar Then I should be able to visit my Buy Courses page |  | 2 | 1 | 0.5 | Scheduled | 2
10 | Feature | Story | Signed in user | Click on the My Profile link of the navbar | I can visit My Profile page. The logged in Navbar and welcome message will continue to display. In the body of the profile page I can see 1. my profile image (default humanoid image if no image uploaded) (with edit image camera button) 2. A form displaying following Text fields with any existing data pre-populated in those fields: First name. Middle name: Last name: Phone number: ISD code: Guardien's First name. Guardien's Middle name: Guardien's Last name: Guardien's Phone number: ISD code: Guardien's email: Following dropdown fields with any existing data pre-selected in those fields: Langiage: Board: Level: Country:(ISD will be as per Country) State: Text fields for City and ZIP code And a Save button at the end. | Given I am a signed in user When I click on the My Profile link of the navbar Then I should be able to visit My Profile page. The logged in Navbar and welcome message will continue to display. In the body of the profile page I can see 1. my profile image (default humanoid image if no image uploaded) (with edit image camera button) 2. A form displaying following Text fields with any existing data pre-populated in those fields: First name. Middle name: Last name: Phone number: ISD code: Guardien's First name. Guardien's Middle name: Guardien's Last name: Guardien's Phone number: ISD code: Guardien's email: Following dropdown fields with any existing data pre-selected in those fields: Langiage: Board: Level: Country:(ISD will be as per Country) State: Text fields for City and ZIP code And a Save button at the end. |  | 2 | 1 | 0.5 | Scheduled | 2
11 | Feature | Story | Signed in user | Edit the prepopulated profile values (or empty fielsds for first time edit) on My Profile page with all legitimate values and Click on the Save button | I can save my updated values (or empty fielsds for first time edit) of profile form on My Profile page and I get a message displayed on top of My Profile page: Student profile saved syccessfully! | Given I am a signed in user When I Edit the prepopulated profile values (or empty fielsds for first time edit) of profile form on my profile page with all legitimate values and Click on the Save button Then I should be able to save my updated values on my profile page and I get a message displayed on top of my profile page: Student profile saved syccessfully! |  | 2 | 1 | 0.5 | Scheduled | 2
11.1 | Feature | Story | Signed in user | Edit the prepopulated profile values (or empty fielsds for first time edit) on my profile page with wrong format values for email or phone numbers and Click on the Save button | I cannot save my updated values of profile form on My Profile page and I get a proper validation message displayed on top of my profile page: Invalid email OR Invalid phone number | Given I am a signed in user When I Edit the prepopulated profile values of profile form on My Profile page (or empty fielsds for first time edit) on my profile page with wrong format values for email or phone numbers and Click on the Save button Then I should be able to save my updated values on my profile page and I get a proper validation message displayed on top of my profile page: Invalid email OR Invalid phone number |  | 2 | 1 | 0.5 | Scheduled | 2
12 | Feature | Story | Signed in user | Click on the edit profile image camera on My Profile page | I can open my local images folders to select a new profile image. | Given I am a signed in user When I click on the edit profile image camera on My Profile page Then I should be able to open my local images folders to select a new profile image. |  | 2 | 1 | 0.5 | Scheduled | 2
12.1 | Feature | Story | Signed in user | Select a valid image from local images folders and click on save. | I can upload the selected image as my new profile image. | Given I am a signed in user When I select a valid image from local images folders and click on save. Then I should be able to upload the selected image as my new profile image. |  | 2 | 1 | 0.5 | Scheduled | 2
12.2 | Feature | Story | Signed in user | Select an invalid image (not of image jpg, jpeg, png, bmp etc format or larger than 1 mb) from local images folders and click on save. | I cannot upload my profile image and I get an error message: Invalid image, please select an image of bmp, jpeg, jpg, png etc format of size less than 1 mb | Given I am a signed in user When I select an invalid image (not of image jpg, jpeg, png, bmp etc format or larger than 1 mb) from local images folders and click on save. Then I should not be able to upload my profile image and I should get an error message: Invalid image, please select an image of bmp, jpeg, jpg, png etc format of size less than 1 mb |  | 2 | 1 | 0.5 | Scheduled | 2
| Feature | Story | Signed in user | Sign into anodiam and land up to view my Home page | I can see a paginated list of all courses prescribed for me at the body of the home page | Given I am a signed in user When Sign into anodiam and land up to view my Home page Then I should be able to see a paginated list of all courses prescribed for me at the body of the home page |  |  |  |  | Initial
| Feature | Story | Unsigned user | Email Verification of student registration |  |  |  | 13 | 5 | 0.38462 | Initial
7 | Feature | Story | Signed in user | Change the Class, Subject or Board filters in the Student Home Page | I can view the Student Home Page with the paginated list of courses according to the selected Class, Subject or Board, sans the courses I have already subscribed for (purchased), order by rating and total number of students | Given I am a signed in user When I change the Class, Subject or Board filters in the Student Home Page Then I should be able to view the paginated list of courses according to the selected Class, Subject or Board, sans the courses I have already subscribed for (purchased), order by rating and total number of students | 004MVPStudentAppWireframes.pptx >> Student Home Page |  |  | 0
8 | Feature | Story | Signed in user | Click on the Home hyperlink or Anodiam logo image on the menu bar of any page in anodiam.com | I can view the Student Home Page. The details of the fields visible for each course will be according to the wireframe diagram in 004MVPStudentAppWireframes.pptx >> Student Home Page | Given I am a signed in user When I click on the Home hyperlink or Anodiam logo image on the menu bar of any page in anodiam.com Then I should be able to view the Anodiam Student Home Page: containing a welcome message with my (first and last) name at the top, a menu bar and a paginated list of courses recommended for me according to my Board, and Class, sans the courses I have already subscribed for (purchased), order by rating and total number of students. The details of the fields visible for each course will be according to the wireframe diagram in 004MVPStudentAppWireframes.pptx >> Student Home Page | 004MVPStudentAppWireframes.pptx >> All logged in pages >> Top menu bar |  |  | 0
9 | Feature | Story | Signed in user | Click on the Logout hyperlink on the menu bar of any page in anodiam.com | I can log out of anodiam.com and view the Student Login Page. | Given I am a signed in user When I click on the Logout hyperlink on the menu bar of any page in anodiam.com Then I should be able to log out of anodiam.com and view the Student Login Page | 004MVPStudentAppWireframes.pptx >> All logged in pages >> Top menu bar |  |  | 0
10 | Feature | Story | Signed in user | Enter a search string in the search field and click on the search (magnifying glass) icon on the menu bar of any page in anodiam.com | I can view the Student Home Page with the paginated list of courses, matching my search string and ordered by course rating and total number of students. The details of the fields visible for each course will be according to the wireframe diagram in 004MVPStudentAppWireframes.pptx >> Student Home Page | Given I am a signed in user When I enter a search string in the search field and click on the search (magnifying glass) icon on the menu bar of any page in anodiam.com Then I should be able to view the Student Home Page with the paginated list of courses, matching my search string and ordered by course rating and total number of students. The details of the fields visible for each course will be according to the wireframe diagram in 004MVPStudentAppWireframes.pptx >> Student Home Page | 004MVPStudentAppWireframes.pptx >> All logged in pages >> Top menu bar & Student Home Page |  |  | 0
11 | Feature | Story | Signed in user | Click on the My Account hyperlink on the menu bar of any page in anodiam.com | I can view the Student Detail Tab of the Student Detail Page and edit any of the fields of my personal information | Given I am a signed in user When I click on the My Account hyperlink on the menu bar of any page in anodiam.com Then I should be able to view the Student Detail Tab of the Student Detail Page and edit any of the fields of my personal information | 004MVPStudentAppWireframes.pptx >> All logged in pages >> Top menu bar |  |  | 0
12 | Feature | Story | Signed in user | Click on the Study Dashboard tab on the Student Detail Page in anodiam.com | I can view the analytics report (now blank) of my studies in the Study Dashboard tab on the Student Detail Page | Given I am a signed in user When I click on the Study Dashboard tab on the Student Detail Page Then I should be able to view the analytics report (now blank) of my studies in the Study Dashboard tab on the Student Detail Page | 004MVPStudentAppWireframes.pptx >> Student Detail Page
13 | Feature | Story | Signed in user | Click on the Student Details tab on the Student Detail Page in anodiam.com | I can view the Student Detail Tab of the Student Detail Page and edit any of the fields of my personal information | Given I am a signed in user When I click on the Student Detail tab on the Student Detail Page Then I should be able to view the Student Detail Tab of the Student Detail Page and edit any of the fields of my personal information | 004MVPStudentAppWireframes.pptx >> Student Detail Page
14 | Feature | Story | Signed in user | Edit my personal details on the Student Details tab on the Student Detail Page and click on the Save button | The edited (changed) Student Detail personal information gets saved and I can view the updated personal information on the Student Detail Tab of the Student Detail Page | Given I am a signed in user When I edit my personal details on the Student Details tab on the Student Detail Page and click on the Save button Then the edited (changed) Student Detail personal information should get saved and I should be able to view the updated personal information on the Student Detail Tab of the Student Detail Page | 004MVPStudentAppWireframes.pptx >> Student Detail Page
15 | Feature | Story | Signed in user | Double click on any of the courses in the Student Home Page | I can view the Course Detail page for the respective course. The details of the fields visible for each course will be according to the wireframe diagram in 004MVPStudentAppWireframes.pptx >> Course Detail Page | Given I am a signed in user When I Double click on any of the courses in the Student Home Page Then I should be able to view the Course Detail Page with the details of the selected course in the first section. It will be followed by a second section containing a carousel 4 courses at a time of all the courses recommended for me according to my Class and Board, sans the one on the top section and the courses I have already subscribed for (purchased), order by rating and total number of students. The details of the fields visible for each course in either of the two sections will be according to the wireframe diagram in 004MVPStudentAppWireframes.pptx >> Course Detail Page | 004MVPStudentAppWireframes.pptx >> Student Home Page & Course Detail Page
16 | Feature | Story | Signed in user | Click on a course from the list of Recommended for You! on the Course Detail Page | I can view the Course Detail page for the respective course. The details of the fields visible for each course will be according to the wireframe diagram in 004MVPStudentAppWireframes.pptx >> Course Detail Page | Given I am a signed in user When I click on a course from the list of Recommended for You! on the Course Detail Page Then I should be able to view the Course Detail Page with the details of the selected course in the first section. It will be followed by a second section containing a carousel 4 courses at a time of all the courses recommended for me according to my Class and Board, sans the one on the top section and the courses I have already subscribed for (purchased), order by rating and total number of students. The details of the fields visible for each course in either of the two sections will be according to the wireframe diagram in 004MVPStudentAppWireframes.pptx >> Course Detail Page | 004MVPStudentAppWireframes.pptx >> Course Detail Page
17 | Feature | Story | Signed in user | Click on the Buy button on the Course Detail Page | I can view the Buy Course Page | Given I am a signed in user When I click on the Buy button on the Course Detail Page Then I should be able to view the Buy Course Page with the Payment summary of Course Name, details and original, discounted and final price displayed. Aso the final payable price should be displayed. | 004MVPStudentAppWireframes.pptx >> Course Detail Page & Buy Course Page
18 | Feature | Story | Signed in user | Select one or more courses in the Student Home Page and click on the Buy Selected Courses button | I can view the Buy Course Page | Given I am a signed in user When I select one or more courses in the Student Home Page and click on the Buy Selected Courses button Then I should be able to view the Buy Course Page with the Payment summary of all the Course Names, details and original, discounted and final prices displayed. Aso the final payable price should be displayed. | 004MVPStudentAppWireframes.pptx >> Student Home Page & Buy Course Page
19 | Feature | Story | Signed in user | Enter my valid Credit / Debit Card or PayPal account details and click on the Proceed to Pay button. | I can view the My Courses Page with all my subscribed (purchased) courses in the order of recent access. The last purchased courses should be at the top of the list. The details of the fields visible for each course will be according to the wireframe diagram in 004MVPStudentAppWireframes.pptx >> My Courses Page | Given I am a signed in user When I click on the My courses hyperlink on the menu bar of any page in anodiam.com Then I should be able to view the My Courses Page with all my subscribed (purchased) courses in the order of recent access. The last purchased courses should be at the top of the list. The details of the fields visible for each course will be according to the wireframe diagram in 004MVPStudentAppWireframes.pptx >> My Courses Page | 004MVPStudentAppWireframes.pptx >> Buy Course Page & My Courses Page
20 | Feature | Story | Signed in user | Click on any of the courses on My Courses Page | I can view the Course Page | Given I am a signed in user When I click on any of the courses on My Courses Page Then I should be able to view the Course Page with all the following details 1. The header bar should display the Name, Board, Class & Subject of the Course; a logo that is a hyperlink to the Student's Home page; and percentage completion (videos checked or completed divided by the total number of videos in the course) by the student 2. The body section will display the video contents. It will have the following controls: A. Stop Pause video toggle control B. Video Speed control (0.25x, 0.5x, 1x, 1.5x & 2x) C. 5 seconds forward & 5 backword control D. Volume (sound) control E. Full screen and normal screen video display toggle control F. Resolution control up to HD 3. The right section display the contents of the course, broken down into sections and videos 4. The bottom section will hold the following tabs: About this chapter (selected by default), Teacher's Notes (non video contents) and Queries and Resolutions. 5. The right bottom section will be the rating and comments section for the course 004MVPStudentAppWireframes.pptx >> Course Page | 004MVPStudentAppWireframes.pptx >> Course Page
21 | Feature | Story | Signed in user | Click on the About this Chapter tab at the bottom section of the Course Page | I can view the details of the chapter in the About this Chapter tab. This should not refresh the entire Course Page | Given I am a signed in user When I click on the About this Chapter tab at the bottom section of the Course Page Then I should be able to view the contents of the About this Chapter tab at the bottom section of Course Page. This will be a text document supplied by the teacher, similar to a text book contents. . This should not refresh the entire Course Page | 004MVPStudentAppWireframes.pptx >> Course Page
22 | Feature | Story | Signed in user | Click on the Teacher's Notes tab at the bottom section of the Course Page | I can view the Teacher's Notes on the chapter in this tab | Given I am a signed in user When I click on the Teacher's Notes tab at the bottom section of the Course Page Then I should be able to view the contents of the Teacher's Notes tab at the bottom section of Course Page. This will be the non video contents on this chapter supplied by the teacher. It will cobtain important diagrams, notes, points to remember, mneumonics etc. | 004MVPStudentAppWireframes.pptx >> Course Page
23 | Feature | Story | Signed in user | Click on the Queries & Resolutions tab at the bottom section of the Course Page | I can view the Queries & Resolutions on the chapter in this tab. This should not refresh the entire Course Page | Given I am a signed in user When I click on the Queries & Resolutions tab at the bottom section of the Course Page Then I should be able to view the contents of the Queries & Resolutions tab at the bottom section of Course Page. This should not refresh the entire Course Page. This will contain of 2 sections: 1. The top section will display all the queries raised by all the students in a recent first order (with student name, date, attachment) and also each query (if already answered) followed by the answer / resolution provided by the teacher (with attachment, datetime of resolution). If the query is not yet ansererd then I should be able to see just the query. 2. The bottom section will contain the form to raise a new query. | 004MVPStudentAppWireframes.pptx >> Course Page
24 | Feature | Story | Signed in user | I can write a new query, attach a supporting image / text / docx file and click on the Post button in the bottom section of the Queris & Resolutions tab at the bottom section of the Course Page | My query gets saved and attachment file stored in the system and everyone can view the query I raised. This should not refresh the entire Course Page | Given I am a signed in user When I write a new query, attach a supporting image / text / docx file and click on the Post button in the bottom section of the Queris & Resolutions tab at the bottom section of the Course Page Then My query gets saved and attachment file stored in the system. This should not refresh the entire Course Page. Everyone should now be able to view the query I raised along with the attachment and date time of my query and my name. Once it is answered, everyone should also be able to view the resolution, datetime and attachemt (if any resolution is put in by a teacher). | 004MVPStudentAppWireframes.pptx >> Course Page
25 | Feature | Story | Signed in user | Click on any of the video lessons under any of the units in the right section of the Course Page | I can start viewing the same video lesson on the main section of the Course Page | Given I am a signed in user When I click on any of the video lessons under any of the units in the right section of the Course Page Then I should be able to start viewing the same video lesson on the main section of the Course Page. The checkbox on the immidiate left side of this listing of the video lesson on the right panel shows checked. | 004MVPStudentAppWireframes.pptx >> Course Page
26 | Feature | Story | Signed in user | Complete viewing any video lessons under any of the units in the right section of the Course Page | I can start viewing the next video lesson according to the list on the right panel until the last video lesson I reached. | Given I am a signed in user When I complete viewing any video lessons under any of the units in the right section of the Course Page Then I should be able to start viewing the next video lesson according to the list on the right panel until the last video lesson I reached. If the next video corresponds to a new section, the new section should show openned in the right section of the main page. Also the checkbox on the immidiate left side of this listing of the next video lesson on the right panel shows checked. | 004MVPStudentAppWireframes.pptx >> Course Page
27 | Feature | Story | Signed in user | Click on any of the 5 stars at the right bottom of the Course Page to rate the course | My rating gets saved and I can view my rating now on. The rating is no longer ediatble any more. This should not refresh the entire Course Page | Given I am a signed in user When I click on any of the 5 stars at the right bottom of the Course Page to rate the course Then my rating gets saved and I can view my rating now on. The rating is no longer ediatble any more. This should not refresh the entire Course Page | 004MVPStudentAppWireframes.pptx >> Course Page
28 | Feature | Story | Signed in user | Write a comment on the respective text area at the right bottom of the Course Page to rate the course | My comment gets saved and I can view my comment now on. The comment is no longer ediatble any more. This should not refresh the entire Course Page | Given I am a signed in user When I write a comment on the respective text area at the right bottom of the Course Page to rate the course Then my comment gets saved and I can view my comment now on. The comment is no longer ediatble any more. This should not refresh the entire Course Page | 004MVPStudentAppWireframes.pptx >> Course Page
29 | Feature | Story | Signed in user | Click on Change This Rating link on the right bottom of the Course Page | The ratings section (5 stars) becomes editable again I can select another rating for this course. This should not refresh the entire Course Page | Given I am a signed in user When I click on Change This Rating link on the right bottom of the Course Page to rate the course Then the ratings section becomes editable again I can select another rating for this course. This should not refresh the entire Course Page | 004MVPStudentAppWireframes.pptx >> Course Page
30 | Feature | Story | Signed in user | Click on Change This Comment link on the right bottom of the Course Page | The comments text area becomes editable and is prepopulated with my previous comment for this course. This should not refresh the entire Course Page | Given I am a signed in user When I click on Change This Comment link on the right bottom of the Course Page Then the comments text area becomes editable and is prepopulated with my previous comment for this course. This should not refresh the entire Course Page | 004MVPStudentAppWireframes.pptx >> Course Page
31 | Feature |  | Signed in user | Click a check box on the immediate left of a video lesson in the list of videos in the course | The video lesson's status can toggle between completed (checked) and incomplete (unchecked). This should not refresh the entire Course Page. The percentage completion dial on the top band of the page also shows the changed count | Given I am a signed in user When I click a check box on the immediate left of a video lesson in the list of videos in the course Then the video lesson's status can toggle between completed (checked) and incomplete (unchecked). This should not refresh the entire Course Page. The percentage completion dial on the top band of the page also shows the changed count | 004MVPStudentAppWireframes.pptx >> Course Page
Note on G1: Help: Acceptance Criteria in Product Backlog comprises of 3 fields, namely: Given, When Then. Here all 4 fields should be colated into one. E.g. Acceptance criteria for following should be as below: User Story: As a logged out User I want to be able to sign into the website, so that I can see my profile. Acceptance Criteria: Scenario: Registered User Signs with valid username and password. Given: I am logged out of website. When: I fill in the username and password fields with my valid credentials and click in sign in button Then: I get signed into the website. Here, Acceptance Criteria could be written in 1 sentence as below: Given I am logged out of website, if I fill in the username and password fields with my valid credentials and click in sign in button, I should get signed into the website.
Note on I1: Help: XS : 1 Story Point : 0 to 2 person hours S : 2 Story Points : 2 to 4 person hours M : 3 Story Points : 4 to 8 person hours L : 5 Story Points : 1 to 1.5 person days XL : 8 Story Points : 1.5 to 2.5 person days XXL : 13 Story Points : 0.5 to 1 person weeks XXXL : 21 Story Points : Larger and never used

## 13Apr
Item # | Item Type | Item Size | NFR | Acceptance Criteria | Notes / References | Task Estimate | Business Value | Priority | Status | Sprint Number
35 | Enabler | Story | Jenkins Pipeline |  | Follow DevOps Bootcamp | 2 | 5 | 2.5 | WIP | 2022-04-13
36 | Enabler | Story | Anisible IaC |  | Follow DevOps Bootcamp | 2 | 4 | 2 | WIP | 2022-04-13
40 | Enabler | Story | Istio |  | Follow DevOps Bootcamp | 2 | 5 | 2.5 | WIP | 2022-04-13
44 | Enabler | Story | Promethious |  | Follow DevOps Bootcamp | 2 | 5 | 2.5 | WIP | 2022-04-13
45 | Enabler | Story | Grafana |  | Follow DevOps Bootcamp | 2 | 4 | 2 | WIP | 2022-04-13
Note on E1: Help: Acceptance Criteria in Product Backlog comprises of 3 fields, namely: Given, When Then. Here all 4 fields should be colated into one. E.g. Acceptance criteria for following should be as below: User Story: As a logged out User I want to be able to sign into the website, so that I can see my profile. Acceptance Criteria: Scenario: Registered User Signs with valid username and password. Given: I am logged out of website. When: I fill in the username and password fields with my valid credentials and click in sign in button Then: I get signed into the website. Here, Acceptance Criteria could be written in 1 sentence as below: Given I am logged out of website, if I fill in the username and password fields with my valid credentials and click in sign in button, I should get signed into the website.
Note on G1: Help: XS : 1 Story Point : 0 to 2 person hours S : 2 Story Points : 2 to 4 person hours M : 3 Story Points : 4 to 8 person hours L : 5 Story Points : 1 to 1.5 person days XL : 8 Story Points : 1.5 to 2.5 person days XXL : 13 Story Points : 0.5 to 1 person weeks XXXL : 21 Story Points : Larger and never used