## Cover Sheet
Anodiam
Sprint Burndown
Sprint Number 002
Version | Editor | Reviewer | Date | Note
1.0 | AC | AM | 2020-07-07 | Initial version

## SprintNumber002
Feature ID | Task ID | Task Description | Story Points | Status | Completion Day | Day | Completed Points | Points Left | Median Line
1 | 1001 | CSS Creation and Bootstrap Selection | 8 | To Do |  | 0 |  | 44 | 44
1 | 1002 | HTML Page Creation | 5 | To Do |  | 1 |  | 44 | 39.6
1 | 1003 | Responsive HTML page creation | 3 | To Do |  | 2 |  | 44 | 35.2
1 | 1004 | Selecting Images for Corousal | 2 | To Do |  | 3 |  | 44 | 30.8
1 | 1005 | Slecting the Blackboard Image | 1 | To Do |  | 4 |  | 44 | 26.4
1 | 1006 | Selecting the headings, messages (including font and color) of the corousel images | 1 | To Do |  | 5 |  | 44 | 22
2 | 2001 | Front End Design with Validation | 3 | To Do |  | 6 |  | 44 | 17.6
2 | 2002 | Database and Fields Design | 1 | To Do |  | 7 |  | 44 | 13.2
2 | 2003 | Java Code | 3 | To Do |  | 8 |  | 44 | 8.8
2 | 2004 | Code Review | 3 | To Do |  | 9 |  | 44 | 4.4
2 | 2005 | Testing | 3 | To Do |  | 10 |  | 44 | 0
2 | 2006 | Encryption - Decryption Logic | 3 | To Do |  |  | 0
2 | 2007 | Https Security Tokens | 8 | To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do