## Cover Sheet
Anodiam
Sprint Burndown
Sprint Number 001
Version | Editor | Reviewer | Date | Note
1.0 | AC | AM | 2020-06-20 | Initial version

## SprintNumber001
Feature ID | Task ID | Task Description | Story Points | Status | Completion Day | Day | Completed Points | Points Left | Median Line
1 | 1001 | Create CRUD functionality in a Data Access Layer using JPA and MySQL inside a developer machine | 5 | In Progress |  | 0 |  | 34 | 34
1 | 1002 | Test the above task # 1001 using Junit | 3 | To Do |  | 1 | 0 | 34 | 30.6
1 | 1003 | Create CRUD functionality in a REST API web service inside the developer machine using the above Data Access layer from Task # 1001 | 5 | To Do |  | 2 |  | 34 | 27.2
1 | 1004 | Test the above task # 1003 using Postman Tool | 3 | To Do |  | 3 |  | 34 | 23.8
1 | 1005 | Containerize the .jar file from above task # 1003 into a docker container and check it into docker hub | 5 | To Do |  | 4 |  | 34 | 20.4
1 | 1006 | Deploy the Docker container from above task # 1005 on a Kubernetes Cluster in GCP | 8 | To Do |  | 5 |  | 34 | 17
1 | 1007 | Test the above task # 1006 using Postman Tool | 5 | To Do |  | 6 |  | 34 | 13.6
|  |  |  | To Do |  | 7 |  | 34 | 10.2
|  |  |  | To Do |  | 8 |  | 34 | 6.8
|  |  |  | To Do |  | 9 |  | 34 | 3.4
|  |  |  | To Do |  | 10 |  | 34 | 0
|  |  |  | To Do |  |  | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do