## StakeholderMgmt
Anodiam
Stakeholder Management
Specific Info
Version | Editor | Reviewer | Date | Note
1.0 | AC |  | 2021-02-23 | Initial version

## MoM&Agenda
Sl# | Stakeholder Group | Stakeholder Sub Group | Role Name | Person Name | Last Meeting |  |  | Next Meeting
[5 empty] | Date Time | Agenda | Notes | Date Time | Agenda | Notes
1 | Compscience |  | Reviewer | Debasish Dutta | 13/03/2021: 2:30 PM AUEST | Content Creation Kick Off | Complete | Recurring Sunday 3:00 PM AUEST | Content Creation
2 | Compscience | 9 CBSE ICSE | Teacher | Jayesh Debnath | 13/03/2021: 2:30 PM AUEST | Content Creation Kick Off | Complete | Recurring Sunday 3:00 PM AUEST | Content Creation
3 | English |  | Reviewer | Arati Chakraborty | 16/03/2021: 4:30 PM AUEST | Content Creation Kick Off | To start with Planning Spreadsheet | Recurring Sunday 8:30 PM AUEST | Content Creation
4 | English | 9 10 CBSE | Teacher | Susmita Bhattacharya | 16/03/2021: 4:30 PM AUEST | Content Creation Kick Off | To start with Planning Spreadsheet | Recurring Sunday 8:30 PM AUEST | Content Creation
5 | Biology |  | Teacher 9-10 | Nayanika Sarkar | 22/02/2021: 3:30 PM AUEST | Icebreaker | Complete | 17/03/2021: 7:30 PM AUEST | Content Creation Kick Off
6 | Chemistry |  | Teacher 9-10 | Saujanya Gupta | 23/02/2021: 3:30 PM AUEST | Icebreaker | Assignment: Create schema | TBD
7 | Chemistry |  | Reviewer | Jayanta | 05/03/2021: 8:30 PM AUEST | Icebreaker | Complete | TBD
8 | Physics |  | Reviewer | Sujit Kar | 20/02/2021: 6:00 PM AUEST | Icebreaker | Finished up to #10 Stakeholders | TBD
9 | Admin |  | Manager | Arati Chakraborty | 26/02/2021: 1.30PM AUST | Icebreaker | Complete | TBD | Next Steps with Jayesh Debnath
10 | Admin |  | Officer | Bikas Paul | 26/02/2021: 1.30PM AUST | Icebreaker | Complete | TBD | Bapi Da's Daughter English teacher + Next Steps with Jayesh Debnath
11 | Economics |  | Teacher 11-12 | Santanu Mukharjee | 28/02/2021: 8:00 PM AUEST | Icebreaker | Complete | TBD | Next step to start to make syllabus, Recommendation of other teachers
12 | Mathematics |  | Reviewer | IRC |  |  |  | 22/03/2021: 7:00 PM AUEST | Icebreaker
13 | Videography |  | Editor | Avishek Pradhan | 21/02/2021: 8:00 PM AUEST | Icebreaker | Complete | 21/03/2021: 2:30 PM AUEST | Next steps with Jayesh Debnath Content Creation | Suddho CV, Digital Marketing Strategy
14 | Videography |  | Reviewer | Anup Moitra | 27/02/2021: 10.30PM AUST | Icebreaker
15 | Videography |  | Videographer | Amit Das | 12/03/2021: 3:30 PM AUEST | Icebreaker | Complete
16 | Videography |  | Reviewer | Parag Biswas
17
18