## Cover Sheet
Anodiam
Product Backlog
Rolling Versions
Version | Editor | Reviewer | Date | Note
1.0 | AC |  | 2020-06-20 | Initial version

## ProductBacklog
Item # | Item Type | Item Size | As a… | I want to be able to… | So that… | Acceptance Criteria (inserta note) | Estimates (Sum of Story Points of Tasks) | Business Value | Priority | Status | Sprint Number
1 | Enabler | Story |  | Deploy the SEED APP and a basic MySQL database on one Kubernetes cluster on GCP. This will be a REST API web service capable of doing a complete crud operation. | Details on Sprint Backlog 001 | 1. Given the application is running on a developer desktop, connected to a local MySQL Instance, if Junit Testing of CRUD operations are run on this local set up it should pass: Select should return a valid data set. Insert, Update. Delete shou;d return an Integer type, showing the number of rows affeced or -1 in case of an error or error code. 2. Given the application is deployed on a GCP cluster, if GET, POST, DELETE operations are performed on the exposed REST API through the Postman tool on a remote client, the client should get expected results. | 34 | 5 | 0.14706 | Scheduled | 1
2 | Feature | Story | Student | sign up | I can register myself and see the free courses and best options for me before buying | given I'm signing up for the website when I sign up with fulfilling valid criteria like name, date of birth, email id and click in the sign up button then I will be able to sign up in to the website. |  | 5 | 0 | Initial
3 | Feature | Story | Student | Login | I can go to my profile | given I,m logged in to the website , when I fill in the user name and password field with my valid cridentials and click in the sign in button then I get signed into the website. |  | 5 | 0 | Initial
4 | Feature | Story | Student | create password | I can get into my profile | given I'm creating my password when I'm putting password followed by the instructions like one capital letter, one character, one numner and minimum eight character then the password is created
5 | Feature | Story | Student | confirm password | I can get into my profile | given I've created password when I'll confirm the password in confirm password firld then I'll be able to access my profile
6 | Feature | Story | Student | put secure Password | my profile is secure | given I'm putting the password in the password field, when I give my valid password and click in the password button then I'll be able to go to my profile after validation . |  | 3 | 0 | Initial
7 | Feature | Story | Student | see comment if put wrong password | I can change password | given I put wrong password , when the password I give doesn’t match with my saved password then I'll receive a comment saying my password is wrong and then I can click on forget password button to change password
8 | Feature | Story | Student | access forget password | able to access password if forgotton/change password | given I want to change my password or I forget the password , when I click on forget password button then I'll be able to validate my account by giving the email id I provided in the website during account creation so that the password change link can be sent in my email and I can change the password by clicking in the link and get in to the website |  | 4 | 0 | Initial
9 | Feature | Story | Student | get a unique identification number | only me or my designated gurdian or one of the parent's can access my profile | given I want to study thorugh the website when I create my profile with validated criteria then an unique student number will be generated
10 | Feature | Story | Student | have my own profile | I can put my personal details | given I want to make my profile , when I give my details in the form like Name, DOB, Standard, Board, Subjects then I am creating my basic profile |  | 5 | 0 | Initial
11 | Feature | Story | Student | have my own profile | I can put some further details | given I put further details in my profile for assistance , when I select which subject I'm best in and I'm weak in from the drop down menu then I'll be able to get assistance for the best courses designed for me |  | 1 | 0 | Initial
12 | Feature | Story | Student | set the access of my profile | the private things in my profile are not visible by others | given I'm in my rpofile and I'm adult, when I'll set the access as private then no one can see my profile
13 | Feature | Story | Student | set the access of my profile | I can set access public | given I'm in my profile and I'm minor when I'll set the access to parents/gurdian then one of the parents (who is liked with the profile) or gurdian (who is linked with the profile) can see my profile
14 | Feature | Story | Student | have my own profile | I can see my courses which I've bought already | given I'm inside my profile when I buy courses then I can see them inside my profile |  | 3 | 0 | Initial
15 | Feature | Story | Student | have my own profile | I can see the videos I bought or got free | given I'm inside my profile when I buy videos then I can see them inside my profile |  | 4 | 0 | Initial
16 | Feature | Story | Student | have my own profile | I can see my test papers of all subjects which ive appeared for and results of all of them | given I'm inside my profile when I give tests on one or many subjects or many tests in on esubjects then the results should be there with the test papers in my profile |  | 5 | 0 | Initial
17 | Feature | Story | Student | have my own profile | I can see the remarks given by the teacher on test papers | given I'm inside my profile when I will see my checked test papers then I can see the special notes from teachers |  | 1 | 0 | Initial
18 | Feature | Story | Student | have my own profile | I can make notes for future reference | given I'm inside my profile when I will make notes about which area to improve based on teacher's remarks so that I can refer it when I appear for the test next time then I'll be able to make the notes with the subject as a tag or comment |  | 2 | 0 | Initial
19 | Feature | Story | Student | have my own profile | I can make notes for teachers to check | given im inside a subject in my profile when I want to keep note for the teacher about any clarification then I can see that |  | 3 | 0 | Initial
20 | Feature | Story | Student | have my own profile | I can make notes with date and time mentioned | given I'm inside my profile when I'm making notes for the teacher's reference then a date and time should be metioned for further reference |  | 4 | 0 | Initial
21 | Feature | Story | Student | have my own profile | I can see the notes from teachers with date and time reference | given I'm inside my profile , when I'll check the response of my notes then I'll be able to see answers from the teacher's with date and time reference |  | 5 | 0 | Initial
22 | Feature | Story | Student | edit my profile | I can change details when needed | given I'm editing my profile, when I change/add or alter details in m profile then I'll be able to edit them by clicking on edit profile button
23 | Feature | Story | Student | see my rating given by the teachers | I can be motivated | given I'm inside my profile when I'm given rating by teachers then I'll be able to see it |  | 1 | 0 | Initial
24 | Feature | Story | Student | get rewarded from Anodiam | I can be motivated | rewaards can be given by Anodiam as a free course or badge which can be shared in social media |  | 2 | 0 | Initial
25 | Feature | Story | Student | not download the videos | I can always see the videos online | given I'm watching the video when I want to save or download the video then it should not be downloaded or saved in the local mechine
26 | Feature | Story | Student | not take the screenshot | I can not keep any document saved | given I'm taking screen shot when I'll try to capture then it should not allow to take the screen shot.
27 | Feature | Story | Student | not copy and paste from the document | I can not keep any document saved | given I'm copying the text when I'll copy and paste the text then it wont allow to do so
28 | Feature | Story | Student | signup | I can register | given I'm signing up for the website when I sign up with fulfilling valid criteria like name, date of birth, email id and click in the sign up button then I will be able to sign up in to the website.
29 | Feature | Story | Teacher | login | I can go to my profile | given I,m logged in to the website , when I fill in the user name and password field with my valid cridentials and click in the sign in button then I get signed into the website.
30 | Feature | Story | Teacher | create password | I can get into my profile | given I'm creating my password when I'm putting password followed by the instructions like one capital letter, one character, one numner and minimum eight character then the password is created
31 | Feature | Story | Teacher | confirm password | I can get into my profile | given I've created password when I'll confirm the password in confirm password firld then I'll be able to access my profile
32 | Feature | Story | Teacher | have a secure password | my profile is secure | given I'm putting the password in the password field, when I give my valid password and click in the password button then I'll be able to go to my profile after validation .
33 | Feature | Story | Teacher | access Forget Password | able to access password if forgotton/change password | given I want to change my password or I forget the password , when I click on forget password button then I'll be able to validate my account by giving the email id I provided in the website during account creation so that the password change link can be sent in my email and I can change the password by clicking in the link and get in to the website
34 | Feature | Story | Teacher | have my own profile | I can put my personal details | given I want to make my profile , when I give my details in the form like Name, DOB, profession, experience, Subjects that I teach then I am creating my basic profile
35 | Feature | Story | Teacher | have edit profile option | I can change/add or alter my personal details if needed | given I'm editing my profile, when I change/add or alter details in my profile regarding my personal data like experience, qualification, then I'll be able to edit them by clicking on edit profile button
36 | Feature | Story | Teacher | have direction to upload course/videos | I can make the videos available for students | given I upload videos/course meterials, when I'll follow the instructions how to upload a video/course meterial then I'll be able to upload the course/videos
37 | Feature | Story | Teacher | get options where to place my videos/course meterials | my videos/course meterials can be viewed by the students | given I want to place my video in the website, when I'll choose the proper option like free videos/paid videos then students can see the videos in the proper place
38 | Feature | Story | Teacher | upload videos | videos are visible to the audience | given I'm in my profile when I will upload videos after fulfilling criteries likefree or paid and subject check, board check, class check, standard (easy or hard) check then I can upload videos
39 | Feature | Story | Teacher | edit videos before publish | I can publish only error free videos | given I'm uploading my video when I'll check it before clicking publish button then my error checking is done
40 | Feature | Story | Teacher | see the remarks by students | I can answer their remarks | given I'm in my profile when students will ask any question through remarks then I can view them and able to answer
41 | Feature | Story | Student | see the remarks date and time | I can answer accordingly | given I'm viewing the remarks by the students when I click on the remarks then I can see the date and time
42 | Feature | Story | Student | see a notification in my mail | I can understand there is a remark in my profile | given I get a remarks notification when I get a remarks from the student with their UIN about asking any question then I get a system generated notification in my email about the remark so that I can keep a track of remarks from individual sudents.
43 | Feature | Story | Teacher | see remarks by parents | I can answer accordingly | given I get a remark by a parent referring the student's UIN when I get a remark from a parent with their student's UIN then I'll receive a system generated notification in my email
44 | Feature | Story | Teacher | check answers of the test papers | I can do the correction and give marks | given I'm checking a test paper when I'll check test papers for a subject of a class on a standard then I'll be able to correct wrong answers or give marks for right answers
45 | Feature | Story | Teacher | rate students | students get motivation | given I'm rating a student when I student can satisfy certain criteria like course complication within time frame/ getting "A" grade marks in a subject / completing test after finishing course within a time frame then the student will be rated stars
46 | Feature | Story | Teacher | not edit or delete any video or course meterial | editing option is not with me | given I want to delete an uploaded video or course meterial when I try to do this then I should get access denied option
Note on G1: Help: Acceptance Criteria in Product Backlog comprises of 4 fields, namely: Scenerio, Given, When Then. Here all 4 fields should be colated into one. E.g. Acceptance criteria for following should be as below: User Story: As a logged out User I want to be able to sign into the website, so that I can see my profile. Acceptance Criteria: Scenario: Registered User Signs with valid username and password. Given: I am logged out of website. When: I fill in the username and password fields with my valid credentials and click in sign in button Then: I get signed into the website. Here, Acceptance Criteria could be written in 1 sentence as below: Given I am logged out of website, if I fill in the username and password fields with my valid credentials and click in sign in button, I should get signed into the website.
Note on H1: Help: XS : 1 Story Point : 0 to 2 person hours S : 2 Story Points : 2 to 4 person hours M : 3 Story Points : 4 to 8 person hours L : 5 Story Points : 1 to 1.5 person days XL : 8 Story Points : 1.5 to 2.5 person days XXL : 13 Story Points : 0.5 to 1 person weeks XXXL : 21 Story Points : Larger and never used