## Cover Sheet
Anodiam
Product Backlog
Rolling Versions
Version | Editor | Reviewer | Date | Note
1.0 | AC |  | 2020-06-20 | Initial version

## ProductBacklog
Item # | Item Type | Item Size | As a… | I want to be able to… | So that… | Acceptance Criteria (inserta note) | Estimates (Sum of Story Points of Tasks) | Business Value | Priority | Status | Sprint Number
1 | Enabler | Story |  | Deploy the SEED APP and a basic MySQL database on one Kubernetes cluster on GCP. This will be a REST API web service capable of doing a complete crud operation. | Details on Sprint Backlog 001 | 1. Given the application is running on a developer desktop, connected to a local MySQL Instance, if Junit Testing of CRUD operations are run on this local set up it should pass: Select should return a valid data set. Insert, Update. Delete shou;d return an Integer type, showing the number of rows affeced or -1 in case of an error or error code. 2. Given the application is deployed on a GCP cluster, if GET, POST, DELETE operations are performed on the exposed REST API through the Postman tool on a remote client, the client should get expected results. | 34 | 5 | 0.14706 | Scheduled | 1
2 | Enabler | Story | [5 empty] | 1 | 0 | Scheduled | 1
2 | Enabler | Story | [5 empty] | 1 | 0 | Scheduled | 1
3 | Enabler | Story | [5 empty] | 1 | 0 | Scheduled | 1
4 | Enabler | Story | [5 empty] | 1 | 0 | Initial
5 | Feature | Epic | [5 empty] | 1 | 0 | Initial
6 | Enabler | Epic | [5 empty] | 1 | 0 | Initial
7 | Feature | Story | Student | sign up | I can see the free courses and best options for me before buying | can access free |  | 5 | 0 | Scheduled | 1
8 | Enabler | Story | Student | Login | I can go to my profile | login validation |  | 5 | 0 | Scheduled | 1
9 | Feature | Epic | Student | put secure Password | my profile is secure | password validation, forget password option |  | 3 | 0 | Initial
10 | Enabler | Epic | Student | access forget password | able to access password if forgotton/change password |  |  | 4 | 0 | Initial
11 | Feature | Story |  |  | able to understand the steps to retrive password |  |  | 5 | 0 | Initial
12 | Enabler | Story | [5 empty] | 1 | 0 | Initial
13 | Feature | Epic | [5 empty] | 3 | 0 | Initial
14 | Enabler | Epic | [5 empty] | 4 | 0 | Initial
15 | Feature | Story | [5 empty] | 5 | 0 | Initial
16 | Enabler | Story | [5 empty] | 1 | 0 | Initial
17 | Feature | Epic | [5 empty] | 2 | 0 | Initial
18 | Enabler | Epic | [5 empty] | 3 | 0 | Initial
19 | Feature | Story | [5 empty] | 4 | 0 | Initial
20 | Enabler | Story | [5 empty] | 5 | 0 | Initial
21 | Feature | Epic | [5 empty] | 1 | 0 | Initial
22 | Enabler | Epic | [5 empty] | 2 | 0 | Initial
23 | Feature | Story | [5 empty] | 3 | 0 | Initial
Note on G1: Help: Acceptance Criteria in Product Backlog comprises of 4 fields, namely: Scenerio, Given, When Then. Here all 4 fields should be colated into one. E.g. Acceptance criteria for following should be as below: User Story: As a logged out User I want to be able to sign into the website, so that I can see my profile. Acceptance Criteria: Scenario: Registered User Signs with valid username and password. Given: I am logged out of website. When: I fill in the username and password fields with my valid credentials and click in sign in button Then: I get signed into the website. Here, Acceptance Criteria could be written in 1 sentence as below: Given I am logged out of website, if I fill in the username and password fields with my valid credentials and click in sign in button, I should get signed into the website.
Note on H1: Help: XS : 1 Story Point : 0 to 2 person hours S : 2 Story Points : 2 to 4 person hours M : 3 Story Points : 4 to 8 person hours L : 5 Story Points : 1 to 1.5 person days XL : 8 Story Points : 1.5 to 2.5 person days XXL : 13 Story Points : 0.5 to 1 person weeks XXXL : 21 Story Points : Larger and never used